Seven out of every 10 construction

projects run over budget and miss their

deadlines. And it's not because people

are lazy or the weather's bad. It's

because people don't have the right

systems and skills. So, in this complete

guide to construction project

management, I'm going to teach you the

systems and skills you need to

effectively run any sort of construction

project profitably. From estimating and

scheduling to quality control and risk,

I'm going to talk through all the

systems and steps to effectively manage

any construction project so you generate

a profit, finish on time, and most

importantly, nobody gets hurt. The

course is broken down into eight focused

modules. Each module focuses on a

specific domain of construction project

management. Construction management

isn't one giant topic. It's a set of

repeatable practical skills. In the

first module, I'll explain the different

types of skills which matter most and

skills you need to successfully manage

and run a construction project. Module

two is on how to manage a construction

project. This is your end to end road

map. Here we go through the full life

cycle of a construction project from

tendering to planning to delivery to

close out. You'll see how each of these

core skills fit into the bigger picture

and what happens at each stage of a

construction project. Module three is on

estimating. Profit on construction

projects is set long before anybody

starts work. If you can't price projects

accurately, you lose money even before

you start. This module covers how to

build realistic estimates that cover

direct and indirect cost, set fair

margins, and protect you from under

quoting. Module four is on scheduling.

Time is money in construction. A good

schedule doesn't just tell you when work

happens. It controls cost. It manages

contracts. And it ensures you finish on

time and keep your client happy. This

module teaches you how to develop,

implement, monitor, and control the

schedule to ensure your project finishes

on time and avoid liquidated damages.

Module number five is contract

management. Contracts are the backbone

of any construction projects. We need to

sign one with our client and then we

need to sign them with our supply chain.

If you don't set them up and manage them

properly, you'll lose money very fast.

This module is going to give you a

practical understanding of how to read,

negotiate, and administer contracts so

you get paid for the work you've done

and avoid disputes with your client and

subcontractors. Module number six is

risk management. Unlike factories,

construction projects happen in

unpredictable environments. We can't

control the weather, the site

conditions, who we're working with, or

who we're working for. A variety of

factors contribute to the uncertainty

that is characteristic of any

construction project. And risk

management teaches you how to plan,

prepare, and manage this uncertainty.

We'll teach you how to plan for,

prepare, and mitigate risks before they

become problems. Module number seven is

quality and completions. Rework and

defects kill your profit margins and

delay handover. In this module, we'll

show you how to build it right the first

time to ensure everything's done

correctly, on time, and there's no

delays to handing over the finished

project. The final module of the course

is going to be on project controls.

Plans mean nothing if they don't match

reality. We need to set up a feedback

system that links the way we plan the

work with the way we deliver the work.

And that's where project controls fits

in. Learn all about the essential cost

tracking, schedule management, and

project controls functions to ensure

that you deliver the project profitably

and on time. Each module is

intentionally self-contained, so you can

watch them all together or you can watch

them module by module. On top of that,

I'm going to put a link in the

description to a bunch of free

resources, templates, and tools that you

can use to enhance your construction

project management.

Let's start off with module one, the

fundamental construction management

skills. Construction management isn't

magic. It's simply a set of practical,

repeatable skills. When I first started

out, I used to think experienced

supervisors and project managers just

knew everything. But over time, I

quickly realized that those 10, 15, 20

years of experience simply boiled down

to a set of skills. a set of skills that

if you deliberately try to learn and

master them won't take you nearly as

long. Construction management isn't

magic. It's not luck. It's a repeatable

system with a specific set of tools and

processes that we need to follow. You

master the skills, you learn how to

manage a project successfully. There

three core categories of skills you'll

need to master throughout your career.

There's technical skills, so trade or

discipline specific knowledge. You can't

manage a mechanical or HVAC project if

you have no idea about mechanical or

HVAC. Similarly, you can't manage a

civil construction project without some

understanding of civil engineering and

civil construction methodologies. You

need soft skills. You need to be able to

work with communicate with people. And

then the focus of this course are the

construction management skills. The six

practical core construction management

skills you need to master. So starting

with construction management skills,

these are our ability to plan, organize

and oversee construction projects from

start to finish. The focus is on the

planning, the organizing and the

coordination. The purpose of these

skills is to complete the project scope.

So do what we set out to originally

achieve without harm. So without anybody

getting hurt, without any damage to the

environment, disruption to the community

on time. So we finish all these tasks by

our planned finish date under budget

without spending too much money to the

and to the required quality standards.

What we've said we're going to build, we

build in accordance with the design and

the specifications.

Construction management is all about the

ability to apply the tools and processes

to achieve the project objectives. These

construction management skills are

broken down into a set of subs skills

which are the subs skills that we're

going to focus on in the modules of this

course. So the first one we've got is

estimating which is developing the bas

the cost baseline. Working out how much

something's going to cost to build

before we build it and before we

importantly commit to signing a contract

to say we're going to build it.

Scheduling. It's about planning when the

work will going to be h is going to

happen and then coordinating and

implementing the schedule so that we

complete the task in the right sequence

to both save money and finish on time.

Contract management which is all about

understanding the terms of contracts,

scope of works, managing claims and

variations and payment fairly. The end

of the day to achieve any sort of

project we're going to have to work with

other companies. We're going to have a

client who's paying us to do the job.

We're going to have subcontractors who

in turn we pay to complete the project.

Risk management. So any construction

project is characterized by uncertainty.

There's a whole lot of variables that we

can't control. We need to be able to

identify what could go wrong and put in

place controls to minimize surprises and

losses. Quality and completions. So

setting standards, inspecting the work,

fixing and closing out defects,

understanding what our client needs us

to fulfill. doing all this so that we

can finish and hand over the project on

time. And project controls is about

tracking our actual cost, our actual

progress, comparing it to the plan, and

putting in place a feedback loop. So,

we're always comparing what we plan to

do with what we actually do. We're

fixing

and we're taking corrective actions when

there's any deviations from the plan.

Then finally, design management, which

is managing and controlling the

technical solution to the project. So

when we develop a design that we're

developing a design in accordance with

the client requirements and then we're

managing changes to this design in a

controlled fashion during execution. Now

it's important to understand that these

are skills. These aren't phases of a

project. These are skills that get

applied across each phase of the

project. For example, if we think of a

skill like design management where we

typically would think of that as only

occurring during the initial project

design, design management occurs in all

of the phases of the construction

project life cycle. So in tendering or

workw winning, design management is used

to develop a concept design sufficiently

and to understand the client

requirements. If we're doing a design

and construction project during the

design and pre-construction phase,

that's when we develop the design from

detail to IFC. During construction where

typically we wouldn't think about design

management taking on a big role we

manage design changes through RFIs. In

commissioning and completions we close

out and develop the asbuilt drawing set.

Another skill for example like

estimating or financial management

during work winning we need to develop

an estimate for the tender. During

design and pre-construction we then take

this estimate and transfer it into a

budget and set up our cost tracking

systems. During construction, we track

and manage our costs, manage variations,

and then during completions, we close

out, do all our final payment claims,

manage our cash flow, and then capture

any financial or cost lessons learned.

So, you can see each of these skills

plays out across the entire life cycle

of a construction project. They're not

just used in one single stage. We're

going to go through this example of a

bridge construction project to talk

about how all these different skills are

used. So when we're talking about

construction management skills, we're

talking about addressing issues like

we're over budget. What we can can we do

about it? We could look at options to

change the design. So this would be a

design management process where we look

at raising an RFI. We could look at it

from a procurement lens or subcontractor

management where we say, can we find

cheaper subcontractors and suppliers to

save money? Can we look at our schedule

and find efficiencies to finish the

project faster and reduce our indirect

costs? Can we optimize the sequence of

activities so the actual activities are

completed cheaper? Or is there some

other contractual reason that we're over

budget? Has the client added additional

scope that we need to claim a variation?

So you can see we've got an issue. The

bridge construction is over budget. And

then there's all these different

construction management skills we're

using to try and solve the problem.

Okay. Next up, we've got technical

skills. So technical skills is all about

understanding

what we're building and how to build it.

The reality is, and there's a bit of a

misconception around it, you can't just

be super good at construction management

and understand all the processes and

then manage a project successfully. You

do need to have some technical

understanding of what you're building.

This is going to allow you to understand

drawings and specifications, solve

constructibility issues, know material

requirements, what materials you're

ordering, and basically identify and

implement smart building and

construction methods and value

engineering opportunities. Technical

skills are the domain to which we apply

construction management. So this could

be mechanical engineering project,

commercial construction project which

would require you to have an

understanding buildings services basic

civil work maybe it's a bulk civil

construction project or maybe it's a

renewable energy project. So this is the

domain we're applying our construction

project management skills to it. I

really break these technical skills down

into three broad sets. Got engineering

which is understanding of the

fundamental technical concepts like

civil, mechanical and electrical. We've

got construction which is understanding

the materials and methods to deliver a

project. So civil engineering we might

understand what a structure is, why

concrete's used, why there's steel

reinforcement in concrete. Construction

is all about what steel reinforcement do

we buy? What's the methodology? Do we

need false work or formwork? How do we

get the temporary works designs

approved? That's all about the

construction methodology. And then we've

also got the ability to use tools. So

the ability to read engineering drawings

and interpret them, the ability to use

3D models, the ability to use scheduling

and estimating software. So these are

our more or less our technical skills.

If I go back to our bridge construction

project, what when when we're talking

about technical skills, we're talking

about things like to save money, we

could look at an option to use pre-cast

or insitue bridge deck construction.

Technical skills are going to help us

understand what is it, how does it work,

how would it be built in practice when

the construction management side of this

solution would be the RFI, the client

design approval, assessing the schedule

impact, assessing the cost impact. So

the next set of skills we've got are

soft skills. So soft skills are arguably

the most important because anything that

involves construction involves a lot of

different people. So soft skills the

interpersonal and behavioral abilities

that individ influence how individuals

interact and communicate and work with

each other because again construction

involves a lot of people. It involves a

lot of dealing with a broad different

range of people and basically getting

them to all work together collaborative

collaboratively. So soft skills could be

broken down into communication which is

the clear and concise expression of

ideas leadership inspiring and guiding

others towards shared goals. Problem

solving, identifying issues and

implementing effective solutions. Time

management, organizing and prioritizing

tasks to meet deadlines, emotional

intelligence, understanding and managing

emotions to oneself and others.

Teamwork, collaborative, collaborating

effectively with diverse groups.

Adaptability.

Flexibility in responding to changing

circumstances. A big one in

construction. And finally, conflict

resolution, navigating and resolving

disagreements. constructively. If we

talk about how soft skills are going to

play into our bridge construction

project, we had the original

construction management problem that

building the bridge would be over

budget. We had our technical solution

which was to use a pre-cast deck as

opposed to an institute deck which we

identified would save us money. Where

does soft skills come in? Well, soft

skills it's the ability to convince a

client, the project team that the

pre-cast construction method is the

preferred method. the human element of

construction. I simply want to leave you

with this idea that construction

management doesn't take 20 years to

master. It's simply a set of skills. A

set of skills that with dedicated effort

you can learn.

Physics, AI, and electrical engineering

are complex. It's not easy, but it's

also not complex. Managing construction

projects is simple. Physics, AI, and

electrical engineering are complex. The

end of the day, construction management

doesn't get much more complicated than

reading drawings, communicating

effectively, and some very basic maths.

Importantly though, it doesn't mean that

construction management is easy. It just

means it's not complicated. Think of it

like assembling IKEA furniture. If you

rush, skip steps, and cut corners, it's

an absolute nightmare. If you follow

structured, systematic approach, don't

cut any corners. Yes, it might be

difficult, but you control it. A project

at the end of the day is just a big set

of steps. So, in this video, I'm going

to give you a step-by-step framework to

manage any construction project. Here's

a step-by-step framework to manage a

construction project from tender to

completion. So, there's two core phases

to any construction project. Phase one

is to secure a contract you can make

money on. Phase two is then to deliver

the project profitably. The end of the

day, that's all it is. You have to find

and win work at the right price. Then

you have to deliver the project for less

than this price. So phase one of this

process is securing a contract you can

make money on. It's much harder than it

sounds. Why is this hard? Because

construction companies, the core

challenge isn't winning projects. It's

winning projects at the right price. Why

is this? Because there's tons of

competition in the construction space.

There's lots of companies chasing the

same work. It's a largely commoditized

industry, meaning the thing clients care

about the most is the price. There's a

ton of risk and complexity in projects,

meaning you often end up in a situation

where the client chooses the cheapest

price. And the cheapest price is the

contractor who's underestimated the risk

and complexity of the project. Which

leaves us to complete phase one

successfully and secure a contract we

can make money on, we need to convince a

client to choose us and pay us a

reasonable fee to do them work to do the

work. It's actually a very challenging

thing to do and the core challenge of

any construction business. So step one

in this process is we need to review and

understand scope. The rule I like to use

is if you understand the scope, you've

built the job in your head. You

understand what you're building and the

steps it takes to build it. It's why in

the previous section when I was talking

about the skills it takes to be an

effective construction manager, you need

to have technical skills. You need to

have a solid understanding of what

you're building. What happens if you

don't understand what you're building?

You miss scope. You end up with budgets

blowouts later on. So what we're going

to do is we're going to review the scope

of works, the drawings, specifications,

and schedule. With this metric of being

able to build the job in our head and

also we want to try and identify

contradictions. We want to ideally

generate a lot of RFIs and questions to

our client and clarifications. And the

output of this stage is we know exactly

what we're pricing. So once we've got

our tender package, we've reviewed and

understood scope. The next step in this

process is we need to prepare our

response. Preparing our response is

really answering the questions. What are

we doing? How much is it going to cost?

And how long is it going to take? We

need to define our price, the cost of

doing the work, our program, the

duration we need to do it, and the terms

and conditions that surround our offer.

Now, when I use the expression terms and

conditions here, I'm not purely talking

about contract clauses and terms. I'm

talking about the scope. A client may

request from us that they want us to do

all the concrete works, buy all the

materials. We need to clearly define

what we're allowing in our offer. Are we

providing the permanent materials or is

our client freeissuing them to us? Are

we doing concrete testing or is our

client doing that for us? That's what I

mean when I say terms and conditions. To

do this effectively, we're going to

apply quite a few of the different

construction management skills. We're

going to need estimating to prepare cost

to do the work. Need scheduling to work

out how long it's going to take and

capture our methodology. We need

contract management to define the terms

and conditions and the scope we're

proposing to because again this may not

align with exactly what the client's

requesting. And to some degree, we're

going to need procurement or market

engagement. For your offer to be

comprehensive, it needs to cover all

these key parts because they all are

related to each other. The schedule you

develop, how long you think it will

long, how long you think it will take to

deliver the project will affect your

cost because of your preliminary ongoing

cost. The contract you sign, the terms

and conditions you accept, for example,

whether you accept liquidated damages or

consequential loss will affect the risk

and margin you need on the project. So,

you need a comprehensive approach to

preparing a tender response. The output

of this, you need to know exactly how to

deliver the project, how much it's going

to cost, how long it's going to take,

and the terms and conditions you're

proposing. Now, once we've prepared

that, we then need to submit our offer

to do the work. We need to package

clearly our price, how much it's going

to cost us, our program, how long it's

going to take, and the terms and

conditions that surround our offer.

Worst thing we can do is just send a

price. We need to clearly articulate our

inclusions and exclusions. For example,

we've allowed for all the concrete

works, including steel fixing and

formwork supply and installation. We've

excluded the supply of any permanent

materials. A program is based on

continuous work, a 12-month defect

liability period, no liquidated damages,

or whatever the offer is. The key here

is you need to be extremely detailed and

specific. Any ambiguity will come back

to bite you. I can say that with 100%

confidence. The more specific and clear

you are, the better. If you just send

back a price, your client will assume

you're accepting all their terms and

conditions, which you may be, but you

may also not be. So, always package your

offer in a way that in excruciating

detail explains exactly what you're

proposing to do. The final step in this

process is to negotiate and finalize the

deal. This is all about clarifying the

expectations. The client's asking for

one thing, you're offering to do

another. You need to close the gap. Come

to terms and conditions that you're both

happy with. That means agreeing on the

price, the program, and the terms and

conditions. There's typically going to

be a lot of back and forward with this.

And I always think when you're talking

about step step three, submitting your

offer, you're always better to because

of the commoditized nature of the

construction industry, you're always

better to have a lower price and more

exclusions. Because typically, a client

will choose you on price. then you can

negotiate your price back up or you can

negotiate your exclusions to come to a

deal. So, it's always better to have

more exclusions and a lower price than

it is to have a higher price that covers

everything because they might not

actually want everything they're asking

for. And then the output of this phase

is a signed contract and you're ready to

begin work. You're ready to start

spending money to deliver the project

and that's the output of phase one.

Phase two is delivering the project

profitably or as I like to put it doing

the work and getting paid for it. The

core challenges to this sticking to the

plan and managing the chaos. As I said,

construction projects complex and

involve a lot of risk. You have almost

certainly missed things in your

estimate, your schedule. There's almost

certainly going to be gaps between what

your client expects and what you're

offering to do. Again, that's why I

always say you want your letter of offer

to be in excruciating detail. What

happens now is you've signed a contract,

you've agreed on a price. Unfortunately,

construction now becomes a zero sum

game. Every dollar a client pays you in

variations is a dollar out of their

budget for the project. In this

situation, under a lump sum contract, it

often becomes quite adversarial. So,

what can go wrong? You can spend more

than you plan to do it. You'll lose

money. You could get delayed in

completing the work and incur liquidated

damages or have to pay additional

preliminary costs. You could have safety

incidents where you're not managing risk

properly. Somebody gets hurt. Could have

scope creep where you do additional work

without getting paid for it or an

extension to your program. Your client

may you may get in a dispute with your

client. They may be late in paying you

and cause cash flow issues. Or you could

just have disputes that damage your

reputation. So these are all the things

that can go wrong. What are the steps

we're going to follow to try and avoid

anything like this happening? Step one

in the process after we've signed the

contract, we've got money to deliver the

project. The first step, and this is a

very broad step which has a lot of sub

activities to it, is to plan and

mobilize. What we want to do, we want to

convert tender into a working plan. The

tender is just an estimate. It's just a

bucket of money, a calculation of cost

to the work. It's a highle schedule.

It's terms and conditions. What we need

to develop is we need to start setting

up our project. We need to develop a

budget. We need to be able to track our

cost. We need a detailed schedule that

captures our methodology and exactly how

we want to do it. Wanting to set up all

our processes, our process to manage

safety, quality and reporting. We need

to do all our procurement. So we need to

find our subcontractors and suppliers,

the people who are actually doing the

work. We need to order our materials.

And then we need to finalize the design

and any shop drawings. So drawings from

vendors, any detailed design we have to

do. Now again, step one, plan and

mobilize. It's a very broad step, but

the output is everything being 100%

ready to go. The way I like to phrase

this is with pool planning. So you think

about the t the first task in the

schedule, breaking ground, earthworks,

whatever it is. What is everything that

needs to be in place for that activity

to start? For example, we've got

concrete foundations we're starting

with. We need the earthworks complete.

We need the survey set out. We need the

design drawings. We need to order all

the materials. We need the subcontractor

and the labor on site. We need the site

facilities. Whatever it is, always work.

I I like the framework of pool planning

where you're working back from what's

coming up next. And what is everything

that needs to be in place for that to be

ready. Step two is then we've set up our

project, we've developed our detailed

plans, we've got everything ready to go.

We then need to execute and implement

the plan. This is the daily management

of the site, sequencing of the works,

progress meeting, short range program,

dealing with issues as they come up,

communicating with our subcontractors,

our suppliers, the client, managing

safety, doing toolbox talks, safe work

methods statements, site inspections,

and then doing our regular QA checks

like inspections and test plans, other

inspections, client signoffs, these

sorts of things. So this is executing

the plan, putting everything in place.

Step three is then to monitor and

control the work. So we've planned,

we've implemented the plan. Step three,

monitoring and controlling is when we we

put in place our feedback loop. So we

want to connect our plan with what's

actually happening. We do this by

tracking our cost, our schedule, how

long activities are taking, measuring

all the quantities of work being

completed, subcontractor performance,

qualities, inspection and test plans,

and all we're doing is comparing this to

the original plan. So, for example, for

our cost, how much have we spent versus

how much did we plan to spend? We want

to maintain our registers, so any design

issues that come up. We have an RFI

register. We record all our defects. We

record any delays and QA records.

Registers are a critical part of

construction management. And

effectively, we're always asking the

question, are we sticking to the plan?

What's changing? And identifying and

fixing problems early. While all this is

happening, we're planning, we're

implementing the plan, we're checking,

we're staying on track. We also need to

manage the contract. That's why we've

got step four, which is getting paid.

Doing the work is different to getting

paid for the work. We need to stay on

top of our contract with both the client

and our subcontractors and vendors. So,

you need to deal with payment claims and

payment terms and dates. Managing

progress claims both submitting them to

our client and approving them from our

vendors. We need to deal with

variations, prepare them, submit them,

negotiate them, get them approved. Any

delays or client delays, we need to

issue notices and EOT claims. We need to

maintain really, really good records of

instructions, meeting minutes, approvals

they've given us. The goal here is not

to do extra work without getting paid to

manage our subcontractors properly to

ensure they're doing the work that they

said they were doing. Also, one of the

key elements of a contract that managing

contract effectively is also managing

our cash flow. We want to basically make

sure we're getting paid before we're

paying our vendors and suppliers to

ensure that we're not going to run into

massive cash flow issues. Then while all

this is happening, very related to

contracts as well is we need to manage

change. Change is just a reality of

construction. Whether it's from not

planning or preparing for something

properly or some unforeseen circumstance

happening, there will be change. change

can be identified early through

monitoring controlling. Then we need to

both manage it practically and

commercially. So commercially if it's a

variation we'll need to provide notice

to the client. We'll need to price it

fairly, claim it formally and wait for

formal approval. And then practically

we'll need to put the change into

action, update our schedules, our

budgets, our plans, and coordinate the

change. Throughout this entire process,

we also want to be managing uncertainty.

Uncertainty, as I've said, is inherent

to construction. It's unavoidable. We

need to be proactive. We need to have a

risk register. Identify the sources of

uncertainty that matter to the project.

Rank them, prioritize them, focus on the

important ones, identify the core

uncertainties, and plan responses to

them, and then mitigate them. The goal

is, yes, things are going to change,

unpredictable things are going to

happen, but we want no nasty surprises.

We want to have planned the worst case

scenarios. We want to have thought of

everything that could go wrong. We want

to consistently be asking ourselves what

could go wrong and have plans in place

to deal with it. Then step seven is to

complete. We want to hand over and close

out the project. We want to complete all

our inspection and testing. Rectify our

defects. Organize our handover

inspections with the clients. Do our

walkthroughs with them. Identify punch

list. Close out the punch list. Prepare

all the handover documentation we need

to such as O andM manuals asbuilt

documentation. Maybe we need to provide

them with spare parts for any special

products we've ordered and close out all

our final accounts and claims. We want

to fulfill all our obligations and

provide evidence of these obligations.

Those are the steps to deliver a

construction project across two phases.

Phase one was to secure a profitable

project by reviewing and understanding

the tender documentation, preparing a

response, submitting an offer, and then

negotiating the offer. Phase two is then

to deliver the project profitably by

planning and mobilizing, executing in

accordance with the plan, monitoring,

controlling, managing uncertainty and

change, getting paid for the work we're

doing, then completing and closing out

the project successfully. Again, this is

a very brief overview. Comes back to

this idea that construction management

is simple but not easy. These steps

aren't rocket science. They're not

complicated. relatively straightforward,

but following them requires diligence,

determination, and staying on top of

everything.

Estimating is the make or break skill of

any construction business. It will

determine whether you win work and keep

your business alive. And if you do win

work, whether you make money on those

projects, whether you like it or not,

and regardless of what anybody says, the

construction industry is largely

commoditized. Nine times out of 10,

clients go for the lowest price. As a

contractor, we need to be able to bid

competitively, but also to manage our

risk so we make sure we make money on

our projects. That's why any contracting

business needs to be able to estimate

both accurately and strategically. So

whether you're an employee or a business

owner, if you work in the construction

industry, you need to be able to

estimate. So, in this video, we're going

to teach you everything you need to know

about construction estimating. We're

going to teach you what is estimating,

when estimating matters, and why

estimating is really a game more than a

process. When and how to estimate, the

components of a construction estimate,

the two main estimating methodologies,

how to prepare top-down budget

estimates, and how to prepare detailed

bottom-up estimates, then how to

properly calculate and applied risk,

profit, and overheads. And finally, how

to review and submit your estimates to

your clients to eliminate risk.

Throughout this, we'll do a couple of

examples and we'll be using our

specialist estimating spreadsheet that

I'll attach a link to in the description

below. Okay. To start with, what is

estimating? So, estimating put simply is

the process of forecasting the cost

required to complete a construction

project. It's about quantifying the

resources we need, materials, labor,

equipment, subcontractors, working out

how much we need, and then assigning

cost to these. So we get a total project

cost. A simpler way to think about it

was we take a set of drawings and

specifications and we turn these into a

dollar value it would take to construct

them. It's the goal is to accurately

calculate the costs to complete a

project. So there's three broad

categories when we need to use

estimates. We use them during the

feasibility stage of a project. So this

would be if we're working for a project

developer and we need to work out

whether it's feasible to build a

project. So, we need to determine how

much the project will cost before we

make a financial investment into it. Say

you want to build a new apartment

complex. You need to work out the total

cost of building the apartment complex.

Then work out how much you could sell

the apartments for. If you can sell the

apartments for more than what you can

build it for, it would be feasible. But

the key bit of information here to know

is how much it costs to build the

building. We also use it as contractors

for bidding in Qua. So this is when we

prepare competitive tender submissions

for our clients. And finally, we use it

in cost control. So this is when we're

managing the project costs during

delivery and we need to forecast out our

cost to complete so we can manage the

total expenditure. So who needs

estimates and estimators? Well, first

one would be project developers when

they're preparing feasibility studies,

working out whether it's worth building

a project. head contractors or general

contractors need them as part of their

quoting process and same subcontractors

need them. Finally, the other school or

group of companies that need estimators

tend to be banks. So banks use them a

lot to audit the viability of projects

if they're lending to developers and

these sorts of things. So what about the

different types of estimates? So

basically we can group estimates based

on how accurate they are. We've got

rough order of magnitude estimates which

would be like plus or minus 30% costs

based on minimal design and concept. Got

budget estimates. So these would be on

schematic or early design drawings which

would give you a plus or minus 20% to

the actual price. Got detailed

estimates. So these are based on full

construction drawings which will give

you plus or minus 10%. And then finally

we've got definitive or tender

estimates. This is when we're actually

quoting to complete a project. We're

putting money on the line. We need to

know exactly how much something will

cost. So, we've established what

estimating is, when it's used, and who

needs estimates. Now, let's talk about

why estimating matters specifically. Why

is estimating a skill that can make or

break a business? So, I want to start by

talking about some unfortunate realities

of the construction industry. Now

whether you say these are unfortunate or

not depends on your perspective but the

reality is these factors make it harder

for contractors to make money. The first

one is the construction industry is a

relatively commoditized industry. That

means clients choose contractors based

on price rather than other

characteristics. You look at a

non-commoditized industry maybe

something like a clothing brand like you

would choose a shirt based on the fact

that you like a brand. You're not

looking exclusively at the cost.

Construction industry though is a highly

commoditized industry. Clients will

choose a contractor based on a price

they're submit. What this does is it

drives down profit margins for

contractors because they need to sharpen

their pencil, lower their cost to give

themselves the best chance of winning

the work. Second factor is the amount of

risk there is in projects. So over 30%

of business insolvencies occur in the

construction industry. That's going to

be a factor of the fact that it's

commoditized as well. But also there's

just a huge amount of risk in projects.

They're technically complicated. There's

a lot of uncertainty. There's a lot of

unknowns. You don't know how much it's

going to rain for the duration of your

project. It might rain a lot which case

you have a lot of downtime. You spend a

lot on delays from inclement weather

which eats into your profit margins.

There's huge amount of uncertainty that

impacts our ability to deliver our

projects for less than what we forecast

them to cost. Next factor is that the

construction industry is highly

contractual. There's a lot of contracts

with huge risk transfers from owners to

contractors to subcontractors and

there's strict terms and conditions that

surround us. There's penalties if people

are late. All these factors impact the

ability of a contractor to deliver a

project profitably. And finally, which

also feeds into how contractual things

are, is that scope tends to be complex

and technical. It's hard to understand

as low factors. Every project is

different and unique. So, the key

takeaway for a contracting business

would be that the lowest bidder

typically wins the project. One bad

project can send your business broke

because of how much risk there is in

these contracts. And finally, this is an

important part to draw attention to now.

I want to talk about it consistently as

we go through the estimating course. But

the offer and your estimate isn't just

your price. It's also the terms and

conditions that surround the price. What

this means is that if you say it's going

to cost $100,000 for you to deliver this

project, an important part of that

$100,000 figure is what are your

inclusions and exclusions? Now, that is

something that people often don't pay

attention to, particularly the very

detailed estimators who just love

crunching numbers. So, if you can

understand the commercial framework that

surrounds your estimate, then you're

going to drastically improve your

performance as an estimator. If you

understand that estimating is as much

about the business side of construction

as it is about the raw number crunching,

you'll do much better. So this leads in

to the role of the estimator in a

contracting business and why they

fundamentally matter. How they help

drive profits for a business. Role of an

estimator is to secure work at a price

we can deliver a project. Now this is an

uphill battle because of all these

factors I've spoken about with the

commoditized industry, the amount of

risk and contracts. But the core goal of

an estimator is to secure work at a

price that the business can reliably

deliver the project. It's much more than

just plugging numbers into a

spreadsheet. So I want to draw attention

to another point that estimating is an

art, not a science. Two estimators can

price the same job with the same

drawings and come up with completely

different prices and both be 100%

correct. That's because estimating isn't

just the science of take doing quantity

takeoffs, plugging numbers, taking

resources. It's a business decision.

It's based on assumptions, productivity

rates, programs, procurement strategies,

your relationship with your client, your

relationship with your subcontractors,

what risks you're willing to take, all

these factors. There's no correct price

for any job. only a price that makes

sense for your business that maximizes

your chances of securing profitable

work. Estimating is fundamentally a

business decision. Your estimate is a

function of how much your company wants

to win the project, how much risk you're

willing to carry, what profit margin

you're targeting, how you can spread

your overheads, whether you've got 10

projects or you need to allocate all

your business overheads to two or three

projects, what terms and conditions

you're willing to accept, and accurately

pricing the project isn't the goal. It's

a step in the process. So what I mean by

this is accurately doing the quantity

takeoffs, preparing the rates, the

resources, calculating the total cost is

a step in the process, but the goal is

to secure the project at a price you can

deliver the project. That's the end

goal. The process of accurately pricing

it is simply a step in that process.

Now, I know I keep going over and over

the same point, but it's really

important. Estimating is the basis of a

contract you're going to sign with your

client. So you prepare a quote

associated with this quote, your terms

and conditions. You negotiate these

terms and conditions. Eventually you'll

sign a contract with your client that

has your quoted price in it. You'll sign

up to their terms and conditions or

whatever the terms and conditions you

negotiate and associated this will be

the contract price which you've prepared

through your estimate. So when you

submit an estimate, you're not just

calculating the cost. It's not just an

academic exercise. You're preparing to

make a contractual commitment. This

means any estimate has two core

components. The price you prepare and

the terms and conditions. The exclusions

and inclusions. What scope you're

willing to price, what you're excluding.

I'm going to keep stressing this as we

go throughout this, but your terms and

conditions are just as important as your

price. This means the scope of work, the

exclusions, and your qualified

assumptions. And the more you understand

that it's as much about the terms and

conditions as it is the price, you'll

drastically improve the quality of your

estimates and their usefulness in how

they help you achieve the overall goal

of securing profitable work. So to

summarize the key points, the

construction industry makes decisions on

price. It's a commoditized industry. If

you price too high, you're never going

to win work. If you price too low, you

win work, but you'll lose money on the

project, which is a much worse result

and sends construction businesses broke

all the time. Estimating is how you find

the right balance between the two to win

profitable work.

Okay, so we've established the role of

the estimator and the goal of the

estimating process. Let's now talk about

construction costs. What are all the

different types of construction costs

and how do you put them together to

prepare a cost estimate? So before we

can talk about how to prepare an

estimate, you need to understand

construction costs. This is the

foundation to understanding estimating

the different types and where and how we

spend money on construction projects. So

this diagram I love because it

simplifies all the different components

of construction costs. We go through

each of these in more detail, but

broadly we can break down all the

different costs we incur to deliver a

construction project into the following

categories. We've got our direct cost,

the costs of doing the physical

construction work. It consists of labor,

materials, plant, and subcontract costs.

Then we've got our indirect cost. So

these are the costs to supervise,

manage, and facilitate the work. So

we've got recurring costs, so ongoing

costs we incur throughout the duration

of the project. and we've got

non-recurring cost. So, oneoff indirect

cost. Sum our indirect and direct cost

together. We've got our total project

costs. And then on top of this, we need

to provide our markup. So, we've got our

margin, our corporate overhead, and our

risk and opportunity. Okay. So, direct

costs are directly tied to completing

the physical works on site. So, these

are costs we incur to complete what's

shown on the drawers and specifications.

pouring concrete, excavating, installing

electrical cables, procuring plant that

we need for the project. These are all

direct costs. They're measurable and

vary based on the scope of the project.

For example, if we need bigger concrete

foundations, we'll incur more cost to

build these. Four main types of direct

costs. We've got labor, materials,

plants and equipment, and subcontract

costs. The first type of direct costs

are labor costs. So labor costs include

wages, allowances on costs such as super

or workers compensation that are paid to

the people completing the physical works

on site. These are always going to be a

function of the labor rate we have and

the labor productivity. So for example,

how many meters squared per day of

formwork can a form worker install? How

many tons of steel can a steel fixer

install? These productivity rates would

drive the total project cost. Labor

costs are going to vary depending on the

skill level or type of labor we need.

So, for example, do we need an

electrician or do we need an unskilled

laborer, the work type they're doing,

and the project location. The next

bucket of direct costs we've got are our

material costs. So, these are the raw

inputs to delivering the project. The

concrete, the reinforcement, the

electrical cables, maybe we have to buy

air conditioning units if we're building

a building. These are our material

costs. And included in these we need to

allow for the actual supply of the

materials, the freight to site and

delivery and any wastage impacting this.

These are prices are often going to be

the most volatile and subject to

escalation. So for example, if copper

prices go up significantly, then the

cost of buying electrical cables is

going to also increase. Then we've got

our plant and equipment cost. So we've

got hide or owned equipment needed for

construction. So for example, cranes,

excavators, concrete pumps, tooling,

specialist equipment like that. Within

these costs, we need to include the

mobilization and demobilization cost. So

for example, getting the piece of

equipment to and from site, any fuel

servicing, and operating costs, but they

will typically be included under labor

costs unless we have some sort of wet

hire supply agreement. These will need

to align with the productivity

assumptions we're using for the labor as

well. So for example, we have an

excavator operator and an excavator will

typically combine these rates together

to get our builtup excavation rate based

on the expected productivity per day.

But again, I'm going to cover all this

when we go through how to actually build

up our direct cost. For now, we're just

talking about understanding these

different types of costs. The final type

of costs we've got are our subcontracted

costs. These are quoted prices for

packages of work such as electrical,

plumbing, formwork. If we package up a

section of work, we get a lump sum price

from a subcontractor to complete all the

electrical work on our project.

Typically, we'll get lumpsum pricing.

It's also a good practice when we're

going through this to understand and

validate the cost build up the

subcontractor has given us in case

they've made some big mistake or error

and how they're doing it. We could get

more complex in our contractual

relationships with how we engage the

subcontractors. We could do certain risk

sharing agreements with them or we could

have or they could have certain

exclusions that we'll need to account

for. So subcontractor costs not as

simple as just letting and forgetting.

We really need to understand their cost

build up and how they price the work and

what they're excluding and including. So

those are our direct costs. The cost of

completing the physical construction

works. Let's now talk about our indirect

costs. And again there's two main

categories of these. We've got our

recurring indirect costs. So, you're

going to be driven by the duration of

the project. And we've got our

non-recurring one-off costs. So, our

indirect costs are costs required to run

the project, but they're not tied to

individual work items. So, these are big

costs like site supervision, site office

setup and operation. temporary work. So

if we need to put in a temporary access

road, site utilities, so getting power,

water, gas to site as required, safety

compliance, permits and approvals, and

they typically form a very large portion

of the overall project cost for maybe

around 30% would be a standard industry

figure, but it will vary a lot based on

the specific type of the project. So

recurring costs are ongoing costs

incurred throughout the project life

cycle such as staff salaries and the key

point here is they're driven by the

overall duration of the project which

means to accurately calculate them we

need a schedule. The other type are the

one-off costs. So these are incurred at

a single point in time during the life

cycle of the project such as mobilizing

to site or maybe freight costs. To get

our total project cost, we sum our

direct costs and our indirect costs. Now

the total project cost is what it would

cost us to complete the project based on

our assumptions and understanding of the

scope. So that's what we would need to

spend to deliver the project. Okay. So

total project cost is an estimate of the

total project cost and it's missing an

important number of elements. The first

one is contingency and risk. So these

are used to covers unknowns and

uncertainties certain events and

conditions. We don't know how much it's

going to rain. We don't know exactly

what the ground conditions are like.

Maybe the design is only a concept

design. There's going to be further

design revisions which might cause us to

incur additional cost. All these factors

will contribute to the amount of

uncertainty in the project. More

uncertainty, the more contingency we

need to allow. The less uncertainty, the

less contingency we need to allow.

Ideally, we'd have some sort of risk

register with estimated dollar values

against all of these. But the other way

to do it is simply have a percentage

marker on the total project cost. Now,

so far we haven't actually applied any

profit margin to our project. So if we

submitted the price we' prepared to the

client, we'd be doing the job free. We

need to apply some sort of profit margin

or markup to the cost to ensure that

it's worth doing the project. That's our

profit margin. This is going to be

business decision, not a cost. It's

based on the market, what we can get

away with. Some projects if we're

contendering them, there's no

competition. We could have a much higher

margin. There's lots and lots of

competition and we need to have a very

competitive price to win. We'd have to

have a very low profit margin. Profit

margin should reflect the overall risk.

So any unknown unknowns, the level of

competition, the desired profit and our

corporate overhead. So in competitive

markets, this is going to be squeezed

down. So that's why it's essential to

understand our true costs. So now we

understand all the different components

of construction cost. We understand

direct cost, indirect cost, risk and

opportunity and our markup margin and

corporate overheads. Now I'm going to

start talking about how you actually go

about calculating these costs. We're

going to start talking about different

estimating methods and the two main

types of estimating methods you need to

understand. So there are two main

estimating methods we use. There's the

top down budget estimating approach and

there's the bottom up first principles

approach. They vary based on the level

of accuracy and the level of effort.

More effort you put in, you'll get a

more accurate price. The less effort,

the less accurate. Pretty obvious. The

top down approach is a quick highle

method of estimating based on cost from

similar past projects or even past

estimates you prepared that you're very

confident in. Rather than breaking down

the project into every single activity

and calculating costs associated with

it, we simply apply unit rents or

multipliers to the overall project

scope. For example, if project A cost

$10 million and project B is 50%

smaller, we assume that project B will

cost $5 million subject to any

adjustments to the scope. Remember back

to the types of estimating when we spoke

about different types of estimating and

the percentage range of accuracy with

these. The top down approach is where we

would be we would use when we've got

higher variabilities in the accuracy and

getting a finalized price isn't

particularly important. So we use it

with early feasibility studies, early

stage client discussions, rough order of

magnitude pricings when the design isn't

finalized and when you're scoping out

whether to pursue a project or not.

Basically, you use it whenever there's

not money on the line and you're not

signing a contract to commit to a price.

The top down approach is good when you

want fast and easy pricing, when you're

just making highle decision making. It's

also a really good way to verify a

bottom up estimate. So, a good way to

check a bottom-up estimate is to first

prepared a top- down estimate so you

know roughly how much the total project

should cost. When you're doing a

detailed estimate, the two should align.

So the limitations of a top- down

estimate is they lack the detail and

miss unique scope differences. They rely

heavily on historical accuracy and

similarity and they're not suitable for

formal bids or signing contracts. Bottom

up estimating on the other hand is where

instead of taking an estimate from the

top down, you build the estimate from

the bottom up. So this is where you

build the project costs by individually

breaking the project scope down into

component pieces and against each piece

calculating the cost of doing that

scope. The process would be you create a

work breakdown structure of the overall

project. You price all of the individual

activities. You sum the direct cost

together. You estimate the indirect cost

and you'll need to prepare a proper

project schedule to do this. Then apply

profit and overheads. You should use the

bottom up approach when you're preparing

detailed tender submissions. You're

using detailed cost planning. You're

preparing pricing to sign a contract.

And basically anytime you need accuracy,

traceability, and defensibility. You're

putting money on the line. If you're

preparing to sign a contract, you need

to do a bottomup estimate. So the

advantage of a bottom-up estimate is you

get a high level of accuracy and

control. You get transparent and

traceable pricing. It allows better

analysis and change management and it

supports confidence in your pricing. So

limitations of a bottomup estimate is

it's time consuming and resource

intensive to do it properly. It requires

detailed design and scope clarity. You

actually need detailed drawings and

specifications to prepare it and it

demands more skill and expertise. And

add to that final point that is easier

to make mistakes in a bottom-up estimate

than there's in a top down estimate.

It's very easy to miss scope, use the

wrong rates, misquantify things. It's

much more errorprone. It needs to be

checked more thoroughly. The approach I

like to use is always to combine the

two. So for example, if you're preparing

bottom up estimate, you'd start with the

top down estimate, prepare a rough order

of magnitude approach based on the

budget estimating approach, and then you

could do a detailed bottom-up price to

check and validate these two prices.

Okay, so so far we've covered what

estimating is, the different types of

construction costs, how and why

estimating is used, and the two main

estimating approaches. Now, let's talk

about when to estimate. When during the

typical life cycle of a construction

project do you need to prepare

construction cost estimates? Okay, so if

we look at the four main phases of a

construction project life cycle, we've

got feasibility, tendering,

construction, and close app. ing

feasibility. We use estimating to help

us determine the initial feasibility of

a project. Say we're working for a

project developer. We then use

estimating during the tendering phase to

secure new work from clients to quote

jobs. This is the main use of the

estimating what people traditionally

think of. We then use estimating a lot

during the construction phase of the

project. This is when we're pricing

variations and change. We also use it as

a forecasting and cost control tool.

Then finally, we use estimating a little

bit in the closeout phase to help us do

retrospective analysis, look at our

actual costs versus our plan costs.

Basically to review the project and

improve our estimating processes going

forward. So estimating during the

feasibility phase. This is where we use

estimating to help us make the business

case for a project. Say we're working

for a renewable energy project

developer. We want to decide whether

it's worthwhile to build a solar farm.

Part of this equation is working out how

much electricity will produce by the

solar farm, our revenue, but also part

of it is working our anticipated capital

cost to build the solar farm, which we

use estimating for to calculate the cost

of building the project. During the

feasibility phase, we typically won't do

detailed bottom up estimates for the

sole purpose that we don't have any

design drawings or concept

documentation. So in the physibility

stage, we tend to use top- down

estimating to prepare rough order of

magnitude prices. We compare these to

benchmark projects. For example, dollar

per square meter rate for earthworks or

buildings or we might use dollar per

watt for a solar farm. We factor in

highle risks such as site conditions,

escalations, inclement weather. And we

use this information to provide input

for our business case approvals,

investor board presentations, and

preliminary funding estimates. The

feasibility stage is characterized by

rough order of magnitude estimates. So

design is usually low, incomplete or

conceptual at best. This results in low

accuracy estimates and it's ultimately

used as a basis for key decision-

making. We don't have to be plus or

minus 1%. We're not signing a contract

to deliver the project for this cost.

but more or less using estimating as a

tool to make informed decisions that

feasibility and viability of building a

project. Okay. Next, the tendering and

procurement phase of a project. The

developer has decided to proceed with

building the project. They now need a

contractor to deliver the project and

then that contractor will eventually

need subcontractors. This is typically

when we think of estimating being used

when we think of estimating. So we use

it to submit competitive accurate offers

that win projects at a price we can

deliver them for. So estimating in this

phase is used by the contractor or the

general contractor quoting to the

developer or the subcontractors quoting

to the general contractor. Instead of

using top- down order of magnitude

estimating because we're getting ready

to sign a fixed lump sum contract, we

use bottom up estimating based on a

detailed scope of works and design

drawings. We'll conduct quantity

takeoffs, calculate direct and indirect

cost, obtain our own subcontractor and

supplier pricing so we have a very

accurate understanding how much the

project will cost to deliver. We review

contract terms, identify risk, apply

contingencies, set our profit margins,

and as the contractor, we will produce a

submission with clarifications,

assumptions, value engineering

opportunities that ultimately a

finalized price that we're willing to

sign a contract to deliver the project

for. So during the tenering procurement

phase, estimating is used as a tool to

sign a contract. the value we estimate

the project to cost. We will eventually

sign a contract to say we can deliver

the project for that value. So it's

essential that our estimating here is

incredibly accurate. This is where

contractual commitments are made around

scope inclusions exclusions and

ultimately price. Poor estimates here

lead to loss losses for contractors,

disputes and delivery issues and

strategic pricing decisions need to be

made. So whether we want to get more

work, so we opt to go in with a lower

profit margin and more risk, or whether

we've got a big pipeline of work, so

we're not particularly keen to win the

project, unless we can do it at a very

healthy profit margin. So while

estimates must be grounded in real

costs, ultimately here is where a lot of

the strategic pricing decisions around

the project are made as well. So we sign

a contract and we begin completing work.

Estimating is also used in the

construction phase to help us manage

costs to track performance keep delivery

aligned with the budget and also

importantly to help us prepare and

submit and get variations approved. So

how is estimating used in this phase of

the project? Well tender estimate what

we prepare to tender our price to

deliver the worked will eventually

become our budget to complete project.

It's used to set our package budgets,

our procurement targets, our cash flow

forecast. So ultimately to set up this

budget, we need to understand how the

estimate was put together. As conditions

change during construction, what we also

use estimating to reestimate our costs

to complete the project. In addition to

using estimating to price variation, so

when the client changes a contract work,

we'll need to prepare estimates and get

them approved. We use estimating through

subcontractor negotiations. So to

understand their own price buildups to

negotiate efficiencies and identify

value engineering opportunities to

review and approve progress claims and

for forecasting our cost to complete to

manage our own budgets. Okay. So, while

we're not going to be doing the heavy

intensive estimating like we did in the

pre-construction procurement and

negotiation phase, we're still going to

be using estimating here a lot as a

tool, but more of a tool to understand

our own cost builds and to prepare and

submit variations. So, we still need to

have a really good firm understanding of

construction estimating to manage this

phase of the project properly. Okay.

Finally, during the closeout phase of

the project, we use estimating to

compare our actual performance, our

estimated performance and refine future

estimating accuracy. So, we're not

necessarily using estimating to improve

the performance of the current project

we're on. We're going to use estimating

to improve the performance of our

business processes going forward. How's

estimating used in this phase of the

project? We're going to conduct cost

reconciliation exercises. So looking at

our estimated cost versus our actual

cost to understand what the difference

is. We want to identify the key

differences and the root causes. Did we

have poor productivity assumptions? Did

we have scope crit? Did we actually do

additional work that we didn't get paid

for? Or did we miss tasks when we were

preparing our estimates originally? This

feedback is going to help build our

historical cost database for our

project, our productivity benchmarks,

and our risk and pricing assumptions

going forward. This whole purpose is to

help us improve future tenders,

understand how we can price more

strategically, but also help us to

improve construction going forward. So

the key considerations here is a robust

closeout review can improve your

tendering going forward because you

actually better understand how much

things cost, where you're making

mistakes, where you're missing things,

and how to improve this. So you can be

leaner and sharper with your pricing,

but have a better understanding of

project risk.

Okay, so now we've spoken about how

estimating is used in the different

phases of project delivery. Now we're

going to do a deep dive into top down or

budget estimate. This is where we

prepare our rough order of magnitude

prices using comparison data from other

projects. Okay, so what's the process

for preparing an order of magnitude or a

top down estimate? The first thing is we

need to identify a relevant or reference

project. Now, this could be multiple

projects. This could be one project. Or

this could even be if we don't had an

exact replica, an accurate estimate

we've previously prepared. That would be

the worst form of budget comparison.

You're much better going off actual cost

data. Next, we want to calculate the

relevant unit rate. So, what is the key

quantity that describes the project?

Building a solar farm, it'll be dollar

per megawatt. For building a railroad,

it'll be dollar per meter. If we're

doing drainage, it will be dollar per

meter. If we're doing an earth words

project, it might be dollar per meter

cube. We then want to scale that rate to

the quantity of the new project. So we

multiply the unit rate by the no known

quantity for this new project. We adjust

for known scope differences. If there's

specific changes to the scope, we can

use more of a bottomup approach to

adjust the cost by these. Then we

finalize our estimate and document our

assumptions clearly and how we've

repaired this so it's traceable and

understandable if anybody wants to

review it. Okay. Okay, so I'm going to

give you a quick example of estimating

the cost of a solar farm based on

historical data from a 25 megawatt solar

farm. So step one, we're using our

historical data to get a benchmark rate.

So this 25 megawatt solar farm we

previously delivered for $30 million. So

we divide $30 million by 25 megawatt to

give us a unit rate of $120 per watt.

Step two is then to scale the cost to

the new project. So the new project will

be 20 megawatt. we apply the same unit

rates. So we take a $120 per watt

multiplied by 20 megawatt gives us a

cost of $24 million. Okay, so on this

project we need to adjust for some known

scope differences. The key one being

that on this project the client is going

to free issue the inverters to us. So we

know the inverters cost around 10 cents

per watt. So we change our unit rate. We

take a $120 per watt. We adjust for the

known scope differences which is the

client free issuing inverters. we get a

new rate of $110 per watt which gives us

a new total cost for the project of $22

million.

Then we document our key assumptions. So

based on similar project scope, scale

and site conditions, we document that

we've excluded the inverter supply and

we've made no allowance for escalation

design variation or sight specific

challenges. So anyone who reviews

estimate knows clearly how it was

prepared and what key qualifications and

assumptions associate the price. As you

can see, rough order magnitude pricing

is quick and easy. Simple and

straightforward. The key thing is it

relies on historically accurate past

project data. If you don't have good

cost data on a previous project makes

doing a rough order of bank price almost

impossible. Now, in this section, what

we're going to move on to talking about

is first principles estimating. So,

taking the opposite approach, rather

than just simply copying another project

and adjusting it as needed, we're going

to build up our estimate from the bottom

up. We're going to break the project

scope into pieces, price each individual

activity in detail. Okay. So, what's the

process to build a bottom-up estimate?

Well, first off, we need to calculate

our direct cost. We determine the cost

of physical deliverables. We then

calculate our indirect costs, the cost

of supervising and managing and

facilitating works. We then apply our

risk and opportunity and markup. So our

profit markup and our corporate

overheads. We then need to review this,

check it for errors, make sure we're

confident in it, draft it into a letter

of offer, and submit it to our client.

Okay, so step one is calculating direct

cost. The cost of completing physical

construction works. This is four steps.

So step one is to create a work

breakdown structure where we decompose

the project scope into deliverables.

Step two is to form a quantity takeoff

where we measure each of the key

quantities. Step three is to estimate

the direct costs. So we've got our

activities, our quantities. Then against

each of these activities, we calculate

the labor plant material and subcontract

costs to complete that activity. Step

four is to summarize these group the

costs to calculate our total direct

costs. Next step is to calculate our

indirect cost. So the process of

calculating the cost to supervise and

manage the work. First step and this is

critically important when calculating

indirect costs is we need to identify

what they are. So unlike direct costs

where we can look at a drawing that

shows we have to excavate, we have to

pour concrete, we have to install

electrical conduits, indirect costs are

costs that we will have to identify what

they are. What are the costs we need to

supervise and manage the work. So step

one is to identify the applicable

indirect costs. We then need to

determine what our recurring indirect

costs are. So we need to determine how

long the project will take us to

complete. So we need to calculate a

schedule. Then we calculate the cost per

unit of time for each of these indirect

costs. The recurring indirect costs we

need multiply them by the project

duration and then we need to calculate

our non-recurring indirect cost. So

these are costs we calculate in the same

way using the same process as our direct

costs. We then combine our direct our

indirect costs and we need to add our

marker. So our risk and opportunity an

estimate is uncertain. It's a prediction

of what we think it's going to cost. So

we need to adjust for the uncertain

events and conditions that can impact

our price. We can either make allowances

on a percentage basis or we can do a

full risk and opportunity register and

apply costs and probabilities to each

items. Once that's done, we need to

apply our margin. So this will be our

profit margin, what money we want to

make for the business from the project

and also our corporate overheads. What

non-specific project costs do we need to

recover a portion of? You don't need to

submit our estimate. We've prepared our

cost, our markup, we've got our sell

price. We need to then review this. We

need to check it for errors, emissions,

and accuracy. Then we need to draft up a

letter of offer where we clearly

detailed the scope. We've priced, our

inclusions, our exclusions, our

allowances, and then put in our pricing

schedule and submit this to the client.

So, that's the overall process we use to

prepare a bottomup estimate. Now, we're

going to dive deeper into each of the

stages of this process, and we're going

to start by talking about preparing our

direct cost, the cost to do physical

construction works. So, direct cost is a

cost that can be directly traced to

specific construction activities such as

earthworth, concrete foundations,

installing electrical cables and

services. the cost of physically doing

the project, the cost of physically

doing the work. They vary based on the

size, complexity, and scope of the

project. There's four core types of

direct costs. We've got our labor costs,

our plant and equipment costs, our

material costs, and our subcontract

costs. So, the first type of these

costs, and most likely depending on

specific type of your business, the

labor costs. The labor cost will be the

wages, allowances and on costs

applicable to the people doing the work.

So this is going to the total labor

costs will be dependent on your

productivity factor. So your task

productivity such as manh hours per

meter squared and formwork your overall

productivity factor. So what percentage

of the time that somebody's at work are

they working? So typically this will be

something like 85% once you factor in

the setting up in the morning, lunch

breaks, smoker, these sorts of things.

And your daily productivity per crew. So

if instead of working as an individual

such as someone doing formwork, you

might have a daily productivity. So a

crew of three people can trench 50 m per

day. This will depend on crew size and

composition. So whether you're using

form workers, steel fixes, electricians,

all these different types of labor will

have different labor rates. Now most of

that is pretty obvious. One key

consideration I'd like to draw your

attention to is that when people think

of labor costs, they think of salary

times time. But they miss an important

component of this, which is the on cost.

So on costs contribute significantly to

overall labor cost. So on cost to cost

like superanuation, workers compensation

insurance, payroll tax, leave

entitlements. So if you're employing

someone, you still need to pay them sick

leave, annual leave, public holidays,

and any sight specific allowances. So

within the EBA, they might have travel

allowances, site allowances, and tooling

allowances. So to calculate labor cost,

we take the base hourly rate that

someone's paid. Say someone's paid $50

an hour. We then apply our on costing to

this. So this will be typically in the

order of 25% to 40% the total cost. So

we take someone who makes $50 an hour.

We apply 30% on cost. The cost rate the

cost of them working 1 hour is $65 per

hour. We then take the productivity

factor. So for example, if we're using a

crew can trench 50 m per day, we then

get a labor cost per meter. So, if we

take 30 hours of work by $65 per hour

divided by 50 m, our co our labor cost

per meter of trenching is $39 per meter.

We can then apply this to the total

volume of trenching to get a total labor

cost that activity. An important point

I'm going to draw your attention to is I

use the daily productivity there. If

you're using an hourly productivity, you

have to adjust by the productive time.

what percentage of the time that

somebody's at work and they're working

as opposed to being on lunch breaks

setting up for the task and these sorts

of things. That's why in my mind it's

easier to use daily productivities when

you're doing this. The next bucket of

direct costs are our plant and equipment

costs. So plant equipment costs include

things like machinery and equipment used

for the construction work. These might

be cranes, excavators, concrete pumps,

scaffolding,

tooling, these sorts of things. We have

to factor in the actual usage of a plant

and equipment as well as mobilization

and demobilization costs, fuel,

servicing and maintenance. With our

plant and equipment costs, we can either

have hired plants or owned plant. We can

own a piece of equipment or we can hire

it from someone else. With our hired

plant, much easier to calculate is we

just charge the daily or hourly rate

that we use. This can include the

operator, so being wet, hire, and basic

servicing. We need to look at the

specific terms and conditions of the

hire. For example, we might for a

concrete pump, we might get charged

$1,200 a day. With owned plant, we still

need to charge the plant to the project

we're working on or the business won't

recover the cost of owning the plant.

The costs of own plant include

depreciation, so the original capital

investment minus the final sale price

spread over the lifetime of the asset.

any financing, so interest or lease

payment costs were incurring, servicing

and maintenance on the plant, and fuel

and consumables. So, own plant rates are

a bit more complicated to calculate.

Some key considerations with plant costs

are utilization rates, so not factoring

in idle time for plant. The easiest way

to do that is simply use the same

productivity and hours for your labor

for your plant. So, for example, you're

trenching 50 m per day. That excavator

that's being used for the trenching is

allocated for the full shift to the

trenching activity, even if it's only

used half the time. Overestimating plan

costs is also a problem when we're

overallocating cost to the project and

missing mobilization and demobilization

costs, which depending on where your

project is, are often significant. Okay.

The next bucket of costs are our

subcontractor costs. So these are costs

we pay to external subcontractors and

suppliers. This can be on a lump sum

basis where we get a full quote to

deliver a package of works as per the

drawings or it can be on unit rate cost.

For example, we get a rate per lineal

meter of saw cutting. Typical

subcontractors that might be used on a

project could be electrical, plumbing,

structural steel, roofing. Within the

subcontractor's lumpsum price, they'll

provide all labor, plant, materials in

their fixed cost. Okay. So, how do we

handle subcontractor costs? Well, the

first thing is we need to develop a

detailed scope of works with clear

inclusions and exclusions and then with

verified quantities. It's always better,

particularly when you're tendering work

and you're not necessarily in a position

where you're ready to sign a contract

with your subcontractor. It's always

better to do your own quantity takeoffs

of their work so you understand

everything and you ensure that they

don't just give you some quick dirty

price and a miskeeping. So perform your

own quantity takeoffs the

subcontractor's work. Give them scope of

works with clear inclusions and

exclusions. What are they providing?

What are you providing? And get three to

six quotes for the work. Don't rely on

the cheapest price. Take the average

price. Perform a detailed gap analysis

and make sure you adjust their prices

accordingly for any scope they've

excluded that you're not aware of.

Perform a high for big important

subcontracts. perform a highle first

principles check and include the middle

price in your estimate but not the

cheapest one. The final cost bucket are

material cost. So the cost of the raw

materials, concrete, steel,

reinforcement, electrical cables,

plumbing materials, these sorts of

things. It's going to depend on our

quantities and our unit rates. We need

to factor in freight and wastage. When

we're doing this, the actual process to

counter the material cost is incredibly

similar to subcontractor cost. Unless we

have some sort of unique business model

where we also make our own materials.

Most in 99% of cases, we'll be getting

quotes from external suppliers. So, we

can use the process of getting

subcontractor pricing to get our

material pricing. Okay. So, where are we

at? At direct cost, the cost of

completing the physical construction

works for each activity. We need to

calculate the labor cost associated with

it, the plant and equipment cost, the

materials and the subract subcontract

cost. We sum those together. We get the

direct cost for a specific construction

activity. As an example, let's do direct

cost estimate of building a concrete

slab. Now, all we're going to be doing

is supplying, installing the concrete,

the reinforcement, and formwork. We're

not going to worry about excavation or

any preparation work such as survey set

out. The scope of the project is to

construct a 100 m squared 150 mil thick

concrete slab. So first thing we need to

do is we need to get our key quantities

by doing our quantity takeoff. So our

concrete volume is 100 m squared by 150

mil thick. We need 15 m cubes of

concrete. A formwork which we need

around the perimeter of the slab is 40

linear meters by 0.15 m deep and we so

we require 6 m square of formwork and we

need the reinforcement. We're going to

use a ratio method to calculate this. So

we need we're going to assume there's

100 kg per me cubed of reinforcement for

the 15 m cubed gives us 1,500 kg of

reinforcement. Then each of these tasks

we can take the quantity and the rate to

calculate the cost. The concrete supply

we need 15 m cubed of concrete. Our rate

is $250 per me cubed which gives us

$3,750

for the supply. For our reinforcement

supply, we need 1,500 kg at $1.50 per

kilogram gives us $2,250 for

reinforcement supply. For labor, we're

assuming to install the formwork, to

place the reinforcement, and then to

pour the concrete, we need three workers

for 8 hours to do the entire slab. Our

cost rate, so our uncosted rate of labor

is $60 per hour, which is $1,40

for labor. And we're going to need a

concrete pump for one day at $1,200 a

day. This gives us the total cost of

performing a slab of $8,940.

Now, these numbers are just made up.

They don't mean anything. If I look at

those labor numbers, that looks very

lean to construct that slab. You get the

general point. You go through each of

the items. We take the quantity, the

rate to get total. We sum those

together. We get our total direct cost

for constructing the concrete slab.

Okay. So, let's go back to our estimate

components and let's look at where we're

up to. So, we've done our direct costs.

We've worked out for the construction

activities we're needing to deliver the

project. We worked out our labor,

material, plant, the subcontract costs.

We've done this for every activity in

our work breakdown structure. We sum all

these together. We get our total project

direct cost. Now, we need to move on to

calculating our indirect costs. Let's

move on to doing our indirect cost. So

indirect costs are the cost of

supervising, managing and facilitating

the work. Now remember our direct cost

we can calculate by looking at the

drawings, going through all the

different drawings and working out

everything that needs to be done to

complete the project. Indirect cost is a

bit more challenging because we need to

come up with what are the costs as the

contractor we're going to incur to

manage the work. It's not going to be

shown on any drawings. We're not going

to see the crib facilities, the toilets,

whether we need a security guard at

night. That's why the challenge with

indirect cost is making sure we've

covered everything. So indirect costs

are expenses necessary to run the

project, but cannot be directly linked

to a specific construction activity or

work packages. They support the overall

project delivery, covering site

operations and compliance, but they're

not going to be shown on any drawing.

also known or referred to as preliminary

prelims or site overhead and running

costs. So, why are indirect costs so

important? First off, they are often

underestimated eating into profit

margins when you're delivering the work.

They're also driven by the project

duration, which is an incredibly hard

figure to calculate. So, there's a lot

of risk in estimating the duration of

the project, which will ultimately drive

the total indirect costs. Finally,

they're hard to quantify. Unlike direct

costs where we can look at a drawing to

identify them, indirect costs are much

more subjective and project dependent.

So now we've got to go through a key

categories of indirect costs. First one

are our site supervision and management

costs. It is costs like project

managers, site engineers, foremen or

even some salary or wages workers that

are working to help supervise and manage

the work such as logistics people. We've

also got support staff such as document

controllers and safety officers. And

these costs are going to be like with

our labor costs. These are going to be a

combination of their salaries and any on

costing that applies. Salaries are going

to be duration based. They're going to

be recurring costs that are driven by

the overall project duration and length.

Next category are our site establishment

and facilities. This would be the setup

and removal of our site compound,

purchasing or renting a site office and

the fit out and setup, any amenities we

need such as toilets, lunchrooms, first

aid stations or site fencing, signage

and security systems or security guard

at night to prevent people breaking in.

Then we've got any temporary works we

need to perform to facilitate the works.

These would be things like access roads,

scaffolding, shoring, formwork not part

of the permanent structure. If we had to

do like a working platform for a crane,

hoardings, traffic management setups,

these are all necessary to carry out the

work safely and efficiently, but they're

not going to be shown in any drawings.

So, these are temporary works that we

have to install and then reinstate at

the end of the project. Now in a lot of

situations you would cover these within

the direct cost of the task. For

example, if you're doing a concrete

structure and you need false work on

scaffolding for that, I would recommend

including that as it's associated with

one specific task in the direct cost.

However, if you're erecting a scaffold

tower to get access to a roof where

three or four different trades need to

work, then that would be covered as a

separate indirect cost because it's

related to multiple different costs. the

line is a little bit gray and blurry and

particularly around temporary works is

where it's incredibly easy to miss

things. So just make sure you've thought

through the actual construction

methodology and what temporary works

need to be in place to facilitate the

works. And we've also got utilities and

consumables. So these are things that be

like power, water, fuel for generators,

consumables like PPE, office supplies,

cleaning materials, waste disposal,

environmental compliance. So waste

disposal can be quite a significant cost

on projects. The logistics of how you

manage the bins, how much waste you

produce, whether subcontractors are

taking away their own waste. All these

things need to be considered and covered

in your indirect costs. Next, we've got

costs by permits, insuranceances, and

compliance. So local council permits,

road closures, environmental fees,

project specific insuranceances like

contract works insurance, public

liability, bank guarantees, retention,

financing costs, and safety compliance.

So training cost, audits, documentation,

all sorts of costs that we need to

comply with laws, regulations, and

contract requirements. Now the next cost

which might be huge if you're working in

a remote area of Australia or might not

really be that significant if you're

working in the middle of the city and

mobilization and demobilization cost. So

this is transportation of equipment and

personnel to and from site including the

mobilization of plant cranes and heavy

machinery. Setup costs for

subcontractors.

All these sorts of things will need to

be covered in your preliminary costs.

Okay. So broadly speaking, those are all

the buckets of indirect costs you incur

to deliver the project. They will be

specific to the project you're working

on, where you're working, the country

you're working in, all these sorts of

things. So how do you calculate these

costs? The first step is you need to

understand how long your project will

take. Most of these costs will be driven

by time, which means the longer the

project is, the more of these costs will

acrue. The shorter the cheaper the

project will drive the staffing, the

site facility needs, the utility costs,

all of these timebased costs. The next

thing you need to do is you need to

quantify and identify all the applicable

indirect costs. So how many people do

you need for how long? What sort of

people do you need project managers? Do

you need site engineers? What facilities

do you need? Do you need an office

building? Is the client for issue that?

All these sorts of things you need to

work through and identify every single

applicable indirect cost. Now, as I

said, because these aren't going to be

shown on the drawings. This is where you

need experienced people who've delivered

the exact type of project you're working

on to help you identify the specific

indirect costs you're going to incur.

Then, depending on whether they're a

recurring or reoccurring cost, you need

to apply unit rates to salaries, higher

rates, and utilities. For example, a

site engineer, they cost $100,000 a

year. 12 months, that might be like

$8,000 a month. For an office rental,

that would be $2,000 a month. And then

you multiply these by the durations of

the project. Then for your nonrecurring

indirect cost, you'll simply add these

on and calculate them in the same way as

you would any direct cost. So these are

things like mobilization, permits,

one-off compliance fees, insurance

premiums based on the contract value.

these sorts of things. You add these on

and these are your non-recurring

indirect costs. Okay? So, when you're

talking about indirect costs, time is

such an important driver of these costs.

If you have a 40week program as opposed

to a 30week program, you've increased

your indirect costs by 33%. So, it's

really important to understand the

duration of the project. Now, I'm going

to dive more into the realms of contract

management, but it's why it's so

important to have a program that you've

based your price on. And that program

forms part of the contract with the

client because for whatever reason the

client delays access the site, delays

free issuing you materials, holds you up

in any way, you need some mechanism to

cover the additional indirect costs

you'll incur by them extending the

duration of the project. The other

important thing to note is that even if

you remove direct costs, whatever the

client descopes you, reduces the amount

of work you need to do, often your

indirect costs will still be incurred.

So, it's really important to understand

what these are and to also show them to

your client in a way that makes

negotiations much more easier and

they're not necessarily built into the

direct cost items into the pricing

schedule. But also understand the

contract specifics and because some

indirect costs may be reimburseable or

they may be covered by your client if

they're free issuing you site

facilities, office rooms, toilets, first

aid, these sorts of things. Okay, going

back to our breakdown of the total

project costs, where are we up to? Well,

we've done our direct costs, we've done

our indirect costs, we've calculated our

total project costs, we know how much

money we will need to spend to deliver

the project. Now I need to move on to

working out our markups, our risk and

opportunity, our profit margin, our

corporate overheads. Okay, so the first

of these we're going to talk about is

risk and opportunity. Our estimate is an

estimate. It's based on uncertainty.

It's based on uncertain events and

conditions. We don't know exactly how

much it's going to rain throughout the

execution of the project. If it rains a

lot, we have a lot of standown. We have

a lot of people sitting in cryptions

that we're still paying while they're

delivering the project. We have to do a

lot of rework to our earthworks because

it's ran so much. Then we're going to

incur a lot of additional costs. On the

other hand, if it doesn't rate at all,

we're going to have saved a lot of money

if we've made allowances. Our estimate

is based on uncertainty. So, we need to

understand how to properly manage risk

and opportunity. Okay. So, put simply,

what is risk? So risk is the chance your

project will cost more or take longer

than you estimated due to unknown or

uncertainties. An opportunity is the

opposite. It's the chance of reducing

your cost, increasing your margins,

getting additional revenue that all add

value to your project again based on

unknown and uncertainty. Process of

estimating properly is the process of

controlling uncertainty. Every estimate

contains assumptions. things we believe

to be true but can't fully guarantee.

Risk and opportunity management is how

we stay realistic and competitive in the

face of uncertainty. So now I'm just

quickly going to go through the major

sources of risk in any typical

construction project depending on the

specifics of your project. Some of these

might be very applicable, some of them

might not be applicable at all or there

might be completely other categories

that you need to think about and

consider. The first one which happens on

most projects is unclear or incomplete

scope. There might be inadequate design

or design details as you're pricing the

job on a 30% or even a 15% design. There

might be poor client expectations being

defined poorly in the scope of works or

the contract. And the risk is that you

underpric the job because you don't

fully understand what's involved in

delivering it. Okay. The second type of

estimating risk would be material and

supplier price increases. So typically

around 70% of a project's total cost

will be outsourced to subcontractors and

suppliers. Of this there's always a

chance that when you're getting quotes

when preparing your estimate from

suppliers and subcontractors, but by the

time you go to then sign a contract and

deliver the works, their prices may have

increased substantially. So there's

always a risk what you're allowing in

your tender isn't going to be enough to

cover yourself when they're delivering

the works. The next source of

uncertainty is productivity assumption.

So this would be overestimating how fast

crews can work. Then when it comes to

actually doing the work, their

productivities are less than what you

anticipated for. Meaning your budgets

for labor and plant are going to be

insufficient. This might be because you

haven't taken into account site access

issues, weather, or the complexity of

the task. The next one is subcontractor

risk. So, this tends to be a bit of a

problem in more building and commercial

construction projects where you have a

lot of really small contractors that go

out of business and have high insolveny

rates. So, that means you get prices

from a certain subcontractor either

before they sign the contract or as

they're even delivering the work, they

go broke. This leads to incomplete work.

You having to take on other

subcontractors at higher rates. The next

one is specific site conditions. Now

this is a bigger challenge in earth

works and any sort of excavation

activities where you have unknown ground

conditions. You might have a lot of rock

making digging much harder or you might

have a lot of groundwater where you have

to procure expensive pumps and

dewatering systems. You might even have

contaminated soil and have to pay a high

cost to dispose of it. So this could be

higher excavation, earthworks, disposal

or compliance costs. The next source of

risk are unfavorable contract terms. Now

you can say this isn't a risk. This is

something you can just manage by

reviewing the contract. But in my

experience, the contracts construction

contractors sign always very ownorous

and you can't negotiate away every

single ownerous term. Really comes down

to your relationship with the client and

how they enforce the terms of the

contract. For example, liquidated

damages in a lot of cases will never be

enforced by a client. But if you have a

really poor relationship with them or an

incredibly aggressive client, they may

choose to enforce these. They can

enforce things like delayed payments,

retention clauses, cashing your

security. The risk is you're going to

face cash flow issues and penalties that

eat into your margin. So now the major

sources of opportunity in any typical

construction project. First one is value

engineering is opportunity you have when

you start to get into the detail of

planning your works that you can propose

alternative materials and methods that

help you reduce your cost. For example,

there's a beam that you're going to have

to do with expensive propping and

temporary works. You could offer to do

it as a pre-cast beam. Your client

accepts it. You might be able to save a

ton of money. So, there's always going

to be value engineering opportunities if

you put in the time and attention to

exploring them. The next opportunity is

bulk procurement or supplier agreement.

So this is where your business will be

taking on multiple projects will be

procuring a large volume of a certain

good and across all their projects they

might be able to get discounted rates

because they commit to working with one

supplier. For example, your project

might need 200 me cubed of concrete but

the business might be procuring 10,000

meters cubed of concrete in the next 6

months. they could package this all up,

go to a series of vendors and get the

best possible rates because of the big

volume of work. There's always an

opportunity to make buying gains with

strategies like this. Now, the next

opportunity is going to be the opposite

of the risk we spoke about before, which

is higher productivity. Before we spoke

about lower productivities, we'll talk

about higher productivities and

efficient execution. This is when we get

optimized sequencing, experienced crews,

and we can really smash out the work. We

might get favorable weather, minimal

delays, and basically save a lot on our

labor and plant costs. Now, again,

client relationships is a huge

opportunity because it's the opposite of

the risk I spoke about before with

contractual relationships. This is where

you get build a good relationship with

your client. You manage the contract not

so much with letters and EOTS, but

you're managing it as a personal

relationship and you get repeat business

and lower risk of poor negotiations. Now

the final one which is very contract

dependent. Some contracts actually have

within them an early completion bonus to

incentivize contractors to finish early.

So if you have something like that and

you can deliver the works faster, you'll

be able to capitalize on it. Okay. So

how do you include risk and opportunity

in your estimates? Well, there's a

couple of different ways you could do

this. The first one is a percentagebased

risk allowance. So this is where you add

a flat percentage on top of the

estimate. You could add 5 to 10%. It's

simple, but it's broad. And it's better

to use this when you're dealing with

unknown unknown. So these are things you

couldn't possibly foresee. So you just

want some broad project level

contingency that you can draw down on as

you complete the works. The second one

is performing a proper risk buildup. So

a bottomup analysis where you go through

every single risk in the project. You

give it both a consequence if it occurs

and a likelihood of occurring. And you

actually calculate your risk contingency

bucket. This is much more detailed, but

what it's not going to cover is the

unknowns unknown. So, you're still going

to need some sort of percentage based

risk allowance, but on top of that, you

can have a detailed bottom-up analysis.

The final thing, which is my favorite

strategy, and I think by far the best,

is rather than focusing on pricing in

risk, you focus on the terms of the

contract. So, you exclude certain items

from scope or qualify your offer or make

it clear what your assumptions are based

on. So instead of pricing these items

and bidding yourself out of a job, you

can qualify your offer and focus more on

the specific terms and conditions. Okay.

So, so far we've calculated our cost.

We've worked out uncertainty around this

cost and we've got a reasonable figure

of what we think we're going to need to

spend to deliver the project. Final

thing we need to do is we need to mark

up our cost to get our sell price. What

are we actually going to build the

client for the work? This means we need

to cover our profit margin to the profit

generated for the business and any

corporate overheads, costs we'll incur,

running the business that we can't

directly allocate to a project. So up

until now, estimating has been largely a

technical process. We've measured

quantities, we've determined unit rates,

and we've applied and analyzed risk. But

when it comes down to profit and

corporate overheads, margin of markup,

we move into business strategy.

Estimating becomes much less of a

science and much more of a game. What is

the maximum we can bill our client for

and still secure the work? So firstly,

corporate overheads, what are they?

Well, corporate overheads are costs you

incur to run your business that are not

allocated to a single project. So these

are things like head office rent, admin

staff, salaries, accounting, HR, company

vehicles, IT systems, insuranceances,

marketing, legal, executive salaries,

the cost of bidding more work. These

overheads are typically recovered by

allocating a percentage across all

projects. So, for example, if your

annual overheads at $2 million a year

and you forecast $20 million of revenue,

to recover your overhead costs, you need

to put a 10% markup on all your revenue.

So, how do you apply these? You

calculate a required overhead recovery

rate, which will be a percentage, and

then you apply this to your direct and

indirect cost. And basically, you need

to work out a rate that ensures your

business is sustainable. If you can't

cover your overheads, you either need to

reduce them or you're in the wrong

business. Profit is the money you make

after you've covered all your costs. It

is your direct project costs, your

indirect cost, so your staff salaries,

your supervision, and your business

overhead. So, the business running costs

you can't allocate to a project. What

you've got left over after this is your

profit margin. Profit margins and the

margins you put on it is a pure business

decision. Some projects you could have a

50% margin and get away with it. Some

you wouldn't be able to get away with a

5% margin. It depends on how much risk

you're taking, how much competition you

face, how much backlog you already have,

and how much you want to secure this

project specifically, and your company's

financial goals. When setting your

profit margin, there's a couple of key

questions you should ask. How much do

you want to win the work? Are you

desperate for the pipeline for the

prospective project? Then you're going

to bid with a lower margin. If you're a

selective premium contractor, you only

want to take on a handful of projects,

then you can put in a higher margin.

Next question is, how competitive is the

market? Is it niche or specialized work?

Then you can justify a higher profit

margin. If there's huge amounts of

competition, there's 20 contractors all

tendering for the same project, then

it's going to be a lot of pressure on

your profit margins. The next question

is, what margins do you need to be

confident in doing the work? Now, when

we're talking about risk and opportunity

management, we spoke about unknown

unknowns. There is always going to be a

chance that your costs exceed your

revenue. The way to minimize this is to

have a higher margin on your cost. If

you have a 50% margin, your estimate

could be 50% wrong and you still make

money. If you have a 5% margin, then you

have very little room to move. So,

high-risisk jobs should require higher

margins and lowrisk repeat clients where

you know that exact type of work. You've

got a really good cost library. you

understand exactly how much this type of

project costs, you can justify a much

lower margin. Okay. So, what are typical

profit margins? Again, this is so

location project work type of work

dependent, but big contractors typically

sit on a project margin of around 7 to

10%. These will be so these numbers are

profit and corporate overheads. Mid-tier

contractors would be more like 10 to 15%

and specialty subcontractors would be

getting around the 20% mark. Again, so

estimating is the scientific approach to

calculating cost, profit and overheads

of business decisions. They need to be

made by business managers, people who

understand the competition, the market

and the business strategy. Great

estimators need to understand both. They

need to understand the scientific

approach to calculating cost, the

objective side of estimating. They also

need to understand the subjective side,

which is the business decisions that

surround pricing projects. Okay, so now

we've determined our sell price, what

we're proposing to charge the client for

our work. Final thing we need to do is

we need to review our estimate. We need

to check it's correct, comprehensive,

and we're not going to lose money on

this job. Then we need to submit it to

our client and come up with a format

that we can provide them our quotation.

So why is reviewing your estimate so

important? Well, for the simple reason

that under quoting jobs sends

construction businesses broke every

single day. Warren Buffett had a famous

saying which was never lose money. And

you should 100% apply that in your

tendering approach. Is always better to

have no work than to lose money on a

project. People say you should buy

projects. I doesn't make any sense to

me. If you structure your business in

such a way that you have incredibly low

corporate overheads, then there is no

pressure to secure work at a price that

there's every chance you lose money. To

protect against this, you should review

your estimate in detail and also

structure your offer to make sure the

terms and conditions align with what

you've priced. That's the key to this

step. Not just focusing on the price,

but also focusing on the terms. The

first step in this process is to

document and qualify. So, an estimate is

only valid if it reflects what you

believe the scope of the job is. Clients

may have different expectations. That's

why it's important when you're preparing

the estimate to document what you're

pricing and to qualify. This means

clearly articulating in your letter of

offer what's included in your price,

what's excluded, so the scope you're not

pricing, even if they've asked you to

price it, and any assumptions. I like to

go to the next level of detail where for

every line item in the pricing schedule,

I write a description of exactly what's

included, what drawings I've referenced,

and every single assumption and

qualification that is relevant to how

they would review the price. Now, every

estimate you submit, every quotation

should be accompanied by a letter of

offer or bid clarification sheet. This

should include a scope summary. So,

what's included in your price, your key

exclusions, what you have not priced,

any assumptions that your price is

reliant on. So, any assumptions that you

don't want to taste take the risk for,

and the terms and conditions of your

offer. So, payment terms, the validity

of your offer, escalation clause,

anything you want to cover like this.

What will typically happen with a

construction tender is the client will

send you a draft contract. Now,

depending on how serious you are about

winning the work, you might as part of

your tender actually review this

contract and come back with a list of

departures. What I'm guessing is that if

you're tendering a lot of work, you

don't really want to waste time doing

this until you get to the negotiation

table, in which case you can then review

the contract and get the terms and

conditions of your letter of offer to

align with their contract. To me, one of

the most overlooked parts of estimating

is terms and conditions. Your pricing is

based on your understanding of the scope

and the terms and conditions of

contract. If the contract changes, if

what you need, the work you need to do

changes, then your price must change.

Always align your price to your

commercial terms or you risk pricing for

one thing and being forced to deliver

something else. So part of reviewing and

submitting your offer is getting the

terms and the price to align, but the

other part is just factchecking and

studying your estimate to make sure

nothing's missed. So first step in this

process would be a detailed review. I

apply the 8020 rule where 80% of your

costs will probably only be in a handful

of items. For those big ticket costs, go

through them line by line. Even do them

again to make sure that the numbers you

have spot on. When you're doing this,

the key areas to review critically would

be any major cost items, subcontractor

quotes, productivity assumptions, risk

allowances, and your indirect costs.

Once you've completed your detail

review, you're confident with what's in

the estimate, you think it's correct,

you should then do some highle sanity

checks. So you could compare the total

cost of the project. For example, if

it's earthworks job, you might do cost

per meter squared. Or if you're building

a solar farm, you might calculate a

dollar per watt figure and compare it to

previous similar projects or accurate

estimates you've created in the past.

And you just want to get an idea of does

the total price feel right? Are the

buckets of money correct? And if not, to

dig deeper and explore why. The next

thing I always like to check is review

the scope. So, not putting the estimate

aside, just looking at the work packages

you've come up with, the work breakdown

structure. Does it cover the entire

project scope? Often what happens is

people tend to price things correctly.

The issue they have is that they miss

scope. So, it's much easier to check, is

all the scope covered as opposed to,

have I priced everything perfectly? And

then you can do mathematical checks. But

again, this would be error checking the

big cost items of your estimate. It's

probably going to take too long to go

through every line in your cost estimate

to check the formulas are correct. For

labor and plant costs, a useful check

you can do is to check that your costs

are aligned with your program. If it's a

big tender and you are preparing a

construction program and you know you

have a 20we construction program and

that you're planning on having six

full-time workers on it, you can easily

calculate from that your total manh

hours which should align with your

bottomup estimates. That's one of the

easiest ways to check your labor and

plant costs. And the final one, which to

me is a non-negotiable, is to get

somebody else to go through and check

your work. not so much explain it to

them, but to just get them send them the

estimate and get them to review it in as

much detail as they want. That's why,

this is a comment I probably should have

made earlier, but that's why when you're

actually preparing your estimate, it's

really important to write notes and to

set it out in a very clear and

repeatable fashion. for example, your

direct cost to have a template where you

put all your quantities into it and then

have a structured line by line estimate

that anyone in your business can pick up

and critically assess. Now, once you've

checked your estimate, you're happy with

your terms and qualification, the final

step is to submit it. Your final

submission should include your summary

of your estimate. So, this would be the

client's pricing schedule, bill of

quantities filled out. Your letter of

offer detailing your assumptions, your

exclusions, and your key terms and

conditions. Any supporting documentation

such as a bill of quantities, schedule,

a program, and also any contact details

for clarifications.

Okay, awesome work. That's it. That's

estimating 101. We took you from

understanding the fundamental principles

of what is an estimate, what are they

used for. Then we went through the

process of calculating a detailed

bottom-up estimate,

calculating your indirect costs, putting

on your profit margins, your risk, and

then how to finally summarize and submit

this to a client. Estimating, as I said

in the beginning, is the make or break

skill of construction businesses and is

fundamental to the success of any

business. Now, I said a couple times in

there that one of the key things I think

a lot of people overlook in estimating

is terms and conditions. So, if you are

keen to learn more, then check out this

video next on construction contract

administration. If you understand

contracts, you're going to be a way

better estimator.

A study by McKenzie found that eight out

of 10 construction projects finished

late. These were all major construction

projects with experienced project

managers and planners. So given this,

why do so many construction projects get

delayed? The clients set unrealistic

finish dates? The planners get the

methodology wrong? And do the

construction teams ignore the plan as

soon as they start building? Well, yes.

All these factors probably contribute.

But the reality is project scheduling is

super difficult. To build a good project

schedule, you need to understand the

project scope and the quantities of

work. You need to plan the construction

methodology and sequence it logically.

You need to define task dependencies

correctly and you need to factor in

resourcing across different tasks. Then

to manage the schedule during the

construction phase, you need to

communicate and constantly refine the

plan. You need to track progress against

the baseline correctly. You need to

predict issues before they become

problems, and you need to adjust for

delays, clashes, and resourcing issues.

So, in this video, we're going to teach

you exactly how to do that. We're going

to teach you construction project

scheduling. We'll cover what is

scheduling and how it's actually used on

projects, why scheduling matters, and

how it makes contractors more money, the

core scheduling concepts. Then we're

going to cover in detail the core stages

of construction scheduling and the one

that everybody ignores. And then we're

going to finish with some pro tips and

mistakes to avoid. This is the exact

scheduling system I use. It's a blend of

boring critical parts scheduling, but

also the best parts of lean construction

and agile scheduling. Whether you're a

business owner, project manager, project

engineer, these techniques will work for

you. And if you want to get the slides,

I'll put a link to download them in the

video description. Before we dive too

much into the content, we need to

address the important question of how is

scheduling actually used on projects. If

you take any project management course

or go through any project management

textbook, they're going to tell you that

scheduling is the most important skill.

You need a 10,000line GAN chart to

deliver a project. But the reality is

that's just not how things happen on

real world construction projects. This

is what we actually see happen. Starts

with a client setting some unrealistic

finish date. They say they want the

project completed in the next 12 months.

They then go to market. Three to six

contractors quote to deliver the

project. The most aggressive contractor,

the one who's desperate to win the job,

will say, "Yep, we can meet that." They

reverse engineer the schedule and they

come up with some completely unrealistic

baseline schedule. They submit this

schedule. They sign a contract saying

that they'll meet the client's finish

date. As soon as construction starts,

the schedule becomes a reporting tool

only. It's a tick and flick exercise,

and it doesn't reflect how the job's

actually being built. The actual

decisions on site are driven by

instinct, deadlines, and chaos. That

finish date remains fixed, so the team

throws money and resources at it to meet

their contract completion date.

Extensions of time claims are made and

argued with pretty poor substantiation.

Now, I'm not saying that this happens on

every single projects. Sure, some

projects implement scheduling

beautifully, but most projects I've

worked on, this tends to be the pattern

you see, which leads me into the dirty

secret of scheduling. You don't actually

need a schedule to deliver a project.

You need a contract. You need an

estimate. You need quality assurance and

compliance certifications, but the

reality is you can deliver a project

without a schedule. Lots of experienced

construction project managers

effectively run the job in their head.

They know the methodology, they know the

constraints, they know the resources,

and they work backwards almost from

their gut feel. And the reality is a lot

of experienced construction managers

actually do a fantastic job of this. I

call it scheduling without schedules.

Experienced project managers can

visualize the full build sequence, the

key constraints for risks and the

resourcings they need week to week. They

don't need prima vera or Microsoft

project to tell them this. But the

problem is this tends to only work from

there. So what's wrong with this

approach? Well, it tends to fall over

with scale. Does not scale with

complexity, team size, and it's hard to

delegate to other team members. leads to

missed tasks and clashes, mistakes, the

inability to substantiate claims like

EOT claims, frustrated stakeholders, and

poor forecasting. So yes, experienced

construction managers can run a lot of

things in their head or using their own

methodology, but the best project

managers know how to use scheduling

effectively. Okay, this leads on to my

next point which is why scheduling

matters and how does it make contractors

more money. So the number one reason is

that it just gives you planning clarity.

The best schedules take gut feel,

experience, the knowledge of the most

experienced construction managers and

turn it into a plan that everyone

understands and can follow. It's a

famous quote by Dwight D's. Eisenhower

that plans are useless but planning is

essential. And it captures this idea

that a plan that everyone can see,

everyone agrees on helps to identify

clashes, identify constraints, optimize

the sequence of the build, and gives you

smoother delivery. Better plans mean

fewer mistakes, rework, and changes. As

an extension to this, it helps with

communication and delegation. The

schedule becomes the source of truth.

There's a clear plan that shows who

needs to be where and when. It aligns

the project team, subcontractors, and

suppliers with the baseline. The

schedule is the source of truth. It

helps answer questions like when do I

need to be on site? How long do I need

to allow for material procurement and

that this is all captured in the project

methodology and it helps to communicate

this to everyone who needs to work. So,

scheduling helps with coordinating

delivering the project. It's also a

fundamental part of construction

contract management, particularly with

negotiating and getting claims approved.

Contracts typically require contractors

to maintain a program. So you have your

tender baseline program you initially

created, then weekly, fortnightly,

monthly, whatever the contract says,

you'll need to report on your progress

against this program. Doing so will help

you keep your client happy, but it will

also help you be protected from

liquidated damages by helping you to

substantiate any EOT and delay claims.

If you've got a program, it shows

everything your client was meant to

provide you. Maybe they were meant to

approve the design by a certain date. if

they're missing these dates. It's

incredibly easy to claim delays and

protect yourself from liquidated

damages, but also easier to claim

additional costs if you've been fairly

delayed. Without a program, it's almost

impossible to claim these things. Now, a

good schedule also helps you to manage

the project stakeholders. I've already

talked about the benefits of

communication by having a source of

truth in the schedule, but it also keeps

your client and other key stakeholders

happy. makes you look professional,

makes you look like you know what you're

doing, and it also helps to set

realistic expectations and timelines for

when the project will be completed. It's

an easy way to report on progress. It's

an easy as a basis for progress meetings

and it's going to help reduce disputes

because everyone can see the plan.

Everyone can see the methodology. Again,

there's a source of truth for everyone

to agree on. Next, scheduling helps you

save money. So helps you to optimize

with smart resourcing such as avoiding

downtime having multiple mobilizations

from subcontractors clashes between

workg groups. Also helps you to better

plan your methodology. It helps to

inform decisions like whether to

self-perform works or subcontract them.

For example, if you have a long

continuous run of work, it might be

better to set up your own self-perform

team. But if you have big pet peeves

where you need a lot of work done and

then downtime, it's going to be better

to subcontract. You can use that same

principle for whether you hire in plant

or whether you've got consistent use of

plant throughout the duration of the

project. So you might choose to buy it

and then sell it at the end of the job.

Scheduling helps you really optimize

your cost and come up with the best

methodology and also just leads to less

chaos and fewer cost blowouts. Okay. So

instead of just boosting your

profitability by reducing your cost,

scheduling also helps a lot with

managing your cash flow. helps you to

align your payment claims with progress.

It can be used to actually substantiate

payment claims. Can also be used to

forecast material and labor costs more

accurately so you know when you're going

to be spending money in the future so

you can manage your cash in your bank.

And it also helps you to avoid

overordering materials or delayed

deliveries which can again impact your

cash flow. More predictable cash flow as

any contractor knows is essential to

keeping a business running. Look, in a

lot of ways, scheduling can be a

competitive advantage for your business

because a lot of contractors just don't

do a very good job at it. It's going to

help you finish early, which is going to

help you save money with higher margins.

It's going to help you to consistently

deliver, which is going to make you look

better to your clients to actually get

you more work in the future because it

demonstrates your professionalism. And

it's also going to give you confidence

to scale. Okay, so to answer this

question, how does scheduling made

contractors more money? How does it

maximize their profits? On the revenue

side, it's going to help you to deliver

faster and to get paid what you're owed

if your client delays you and avoid

penalties and lost income by being able

to claim for delays. It's also going to

help you to limit your cost. It's going

to help you to plan more efficiently,

reduce waste, come up with the optional

methodology, optimize your resources,

but also reduce your indirect cost. So

if you finish the project faster, you're

going to be paying less staff salaries,

higher of equipment, higher of temporary

office building. So you can see on both

sides, revenue and cost side. Scheduling

has a range of benefits. So now we

understand why we should schedule. Let's

get into the guts of the technical side

of the topic and begin by answering the

question, what actually is construction

scheduling? Okay, so put simply,

scheduling is just planning and managing

when each part of the project happens.

It's taking all the tasks and saying

when each task needs to happen, what

needs to happen before and what can

happen after. It's the process and tools

we use to manage time. So there's two

key things the schedule captures. It

captures how the work's going to be

delivered and when it's going to be

delivered. So how is the methodology

we're using to deliver our project. So

it captures both mandatory linkages. For

example, we need to order materials

before we install them. But also

discretionary linkages. So for example,

do we want to use 10 crews to do this or

do we want to use one crew and do it

soil? So that's the how our methodology.

And based on this, it captures the when.

So for every task we need to do to

complete our project, when is this

activity going to happen? What's the

plan start and finish date? What are the

linkages? What needs to happen before?

What can happen after? And what is the

duration? The output of this is the

schedule. Nine times out of 10, it's

going to be a GAN chart. A GAN chart is

simply, as you can see on the screen, a

list of activities, their duration,

their plan start and finish dates, and

then each activity is represented as a

bar. So the bar shows when the activity

starts, when it finishes. Then there's

lines drawn between the activities which

show the relationships to the following

activity. So the Gant chart is the

document that captures our schedule. The

construction schedule lists all of the

tasks, the activities we need to

complete to complete our project. It

shows the start and finish date of each

task. It maps the dependencies between

the tasks. So, what has to happen

before, what can happen after. It

highlights milestones, any critical

deadlines, for example, our contract

commencement date, our contract

completion date, any milestones we have

along the way, and it also identifies

the critical path. So, that is the

series of activities within our

schedule. We'll explain this more later,

but that if get delayed delay project

completion. These are the series of

tasks that determine our project's

finish date. The schedule is then the

plan that's followed during

construction. So, we develop it during

the planning phase. It's then our

baseline for what we follow as we

deliver the project. We refer to this as

the baseline schedule. We update it

during delivery and we also derive from

it a whole lot of subscription.

For example, construction teams usually

have some sort of 3 to six week look

ahead that they use to plan and

coordinate the day-to-day construction

activities. The procurement team might

have a separate procurement schedule

that shows all the packages when they

need to be awarded, when the materials

are needed on site and will have some

sort of daily plan. So all these are

subscules that get derived from the

master project schedule the baseline

schedule. Okay. So now you understand

the idea of a schedule and the baseline

schedule. Let's talk about some core

scheduling concepts you need to

understand. So the first one is an

activity or a task which is the base

unit in the schedule. We have a list of

tasks, a list of activities like placing

form work, steel fixing, pouring

concrete that we need to complete to

complete the construction work. Each

task needs to have the following

attributes. It needs to have a start

date and finish date. It needs to have a

duration and it needs to have

dependencies. So every task will have

work that needs to be done before and

work that needs to be done after. We

also have milestones. So milestones is

zero duration events that mark key

achievements. For example, you might

have one for contract award, foundations

complete, handover of the entire

project. These are the deadlines that

drive progress. These are the fixed

dates that our stakeholders, our

clients, these are the dates everybody

cares about and the dates that

everybody's working towards. So people

usually don't focus too much on task.

They set the finish dates and these are

the dates that actually drive progress.

The duration of an activity is the time

an activity takes to complete. This is

going to be based on things like the

quantity of work you have to do. For

example, if you do have to do 100 m of

trenching versus,000 m of trenching. The

productivity. So whether you can do 50 m

a day or whether you can only do 20 m a

day. And the number of resources,

whether you're going to use 10 crews or

whether you're going to use two crews.

Key concept with an activity duration is

whether you have a productionbased

duration which means it's purely based

on the number of resources you apply to

it or a programbased duration. So some

activities have fixed durations no

matter what. For example, if you order

steel reinforcement might have a 4-we

lead time or if you order an electrical

transformer might have a 70we lead time.

These are referred to as programbased

durations. Now resources are always a

contentious issue when we talk about

scheduling because it can add a lot of

confusion to a schedule. But a proper

construction project schedule is

resourced. What this means is that

there's the assignment of labor plant

and materials to a task. For example, a

trenching activity might have an

excavator, an operator, and a spotter

assigned to it. What this does, it helps

to align the estimate with the schedule,

but it also helps you to understand the

relationship between tasks based on your

available resources. This is a really

core concept in scheduling and something

that makes scheduling very complicated.

You can level resources or you can

smooth resources. So leveling resources

means you're avoiding overloading

resources depending on the number of

crews you have. For example, if you only

have one crew and you've got all these

tasks occurring at the same period of

time, you would need to level your

resources because you've only got

availability of one crew. It's going to

push out the durations of these

activities. Smoothing, on the other

hand, is where you spread work without

extending project time. So, you optimize

the usage of your resources to avoid

delays. Okay? So you can see an easy

visual explaining this. But say for

example, you can only work 45 hours a

week and there's all these tasks that

come out of the schedule. In the first

week, there's 60 hours of work, but in

the sixth week, there's only 10 hours of

work. Resource leveling is saying that

we can only work a maximum of 45 hours a

week. So we have to take some of these

tasks where we've got more than 45 hours

per week. We need to move them from week

one into week two, from week two into

week three. What this does is it pushes

the duration of the project from week

seven to week 9. Resource smoothing on

the other hand is without violating that

constraint of 45 hours of work per week.

It's taking the ups and the downs and

it's turning in into a consistent 38

hours per week. Next, the critical path.

And I would say this is one of the most

misunderstood terms in construction

project scheduling. Critical path is the

series of tasks that if delayed delay

project completion. It's the longest

path of dependent task. Controls the

earliest possible finish date of the

schedule. And if you can delay the task

without impacting the finish date by

definition, it's not on the critical

path. And the other thing you need to

understand is this isn't a scientific

set in stone term. Often when we look at

a schedule and something has say you're

talking about a 12-month project and it

has two days float. Yes, theoretically

it's not on the critical path but

practically it is. No schedule is

accurate down to the day. So the idea

that something has two days float means

it's on the critical path. The other

really important thing you need to

understand is the critical path is

dependent on resourcing. You can have

critical path activities that are

programmed driven. So there's nothing

you can do about the duration of the

task. That's different to a critical

path activity where we can adjust the

resourcing and do it faster. So these

are some of the things you have to keep

in mind and it's some of the things you

have to understand when you're looking

at a schedule and it's where it really

scheduling becomes as much as an art as

a science to understand the actual the

data that's driving these program

durations. When we talk about optimizing

the schedule, trying to bring forward

the completion date, the only way to do

this is by reducing the critical path,

working out how we can take tasks on the

critical path and make them shorter.

Okay. So, if you look at a really simple

GAN chart, you can quite easily

visualize on this what is a critical

path task and what's not. For example,

site preparation. If site preparation

gets delayed, it pushes all the inground

services back. Therefore, it's on the

critical path. If we delay site

preparation by a week, it's pushing out

our finish date. Look at the next set of

tasks, the ingground services, you can

see that the power inground services, if

they get pushed back, they're going to

push back excavation. But water services

on the other hand or the data services,

we could push those back a week or two.

It's not going to push back the

excavation activity. So those activities

are not on the critical path. They have

some float associated with them. But if

you do delay them enough, they will

start pushing back the next activity,

which is where we're going to talk about

float. Okay. So float is basically how

much you can delay an activity before it

impacts your critical path. Total float

is your impact, how much you can delay

an activity before it impacts the

critical path. Free float is how much

you can delay an activity without it

affecting the next task. The difference

between these two is if your next

activity is on the critical path, your

total float will be equal to your free

float. If you delay the next activity,

you're delaying a critical path

activity. But if you delay an activity

that's not on the critical path, then

you have some free float. Okay. Next, we

have constraints. A constraint is any

limit or restriction that affects how

and when activities can be carried out

in a project schedule. You can have a

time constraint, for example, a

deadline, a fixed start or a fixed

finish date that you have to work

around. You can have resource

constraints, for example, you might have

limited access to labor, plant or

materials. You might have a physical

constraint, for example, due to site

access, you can only have one entry in

and out, which might impact how your

deliveries go. Or you might have a

certain number of days that it's raining

where you can't work. Or you could have

a contractual constraint which might be

some fixed contract completion date. So

all of these are restrictions of how and

when activities can be performed. Okay.

Next we've got the idea of schedule

optimization which I brought up when we

were talking about the critical path.

But this is how we reduce the duration

of the project by optimizing the

schedule. By definition the only way we

can do this is by reducing the critical

path. critical path the longest series

of activities that we need to complete

to complete the project. We have to

reduce the length of the critical path

to reduce the length of the project.

There's two ways we can do this. We can

fast track activities which is if you

look at the diagram that's where we

overlap tasks. This adds risk because

you introduce the risk that if task one

has to be completed before task two can

start but you want to bring them

forward. So you overlap the activities.

there's more of a risk that task two

will get delayed because they'll run out

of work to do because task one's not

complete. The other way we can

accelerate the schedule is with

crashing. So this is adding resources to

accelerate progress which adds cost to

the project because you're adding more

people. They're going to be working less

effectively. You have to pay for more

inductions. You have to pay for more

onboarding. Generally adding resources

will increase the cost of the project.

Okay. Next, we've got activity linkages.

The linkages between tasks define the

workflow or the methodology. For

example, we need to do the excavation.

Then we can start the concrete works. We

need to install the underground

conduites before we can start pulling

cables. The task linkages capture the

methodology how we're going to build the

job. Key types of task linkages are

mandatory. So, things that have to be

done in sequence. For example, you need

to order materials before you install

them. Or you can have discretionary

linkages. So these are choices in the

way we do the work. Classic example is

resourcing. We can have 10 crews or we

can have one crew. That's a choice we're

making that captures our methodology and

how we're proposing to build the

project. Okay. So there's four main

types of activity linkages we can have.

The classic is the finish to start

relationship. Activity A has to finish

before activity B can start. We can have

a start to start relationship. Activity

A and activity B need to start together.

Or we can have a finish to finish

relationship. For activity B to finish,

activity A must finish. Or we can have

the least common, which always confuses

me and every time I see an example of I

get slightly confused, but it's a start

to finish relationship. For activity B

to finish, activity A must start. Okay.

So, let me give you some more concrete

examples of these to help you better

understand. So, the finish to start

relationship is the most common one,

which is task B cannot start until task

A finishes. For example, task A might be

pouring concrete. Task B might be

structural framing. You need to finish

the concrete foundations before you can

stand the frames on them. That's a

classic example. And that'll be 95% of

the activities in our schedule. The next

type is a start to start relationship.

Task B cannot start until task A starts.

For example, when you start excavating,

so say you're digging like quite deep

foundations, you can start the shoring

at the same time. So as you dig down,

you put the shoring around the walls. So

as soon as excavation starts, shoring

can begin in parallel. So these

activities would typically have a lag

between them. They wouldn't start

exactly the same time. You might start

with 2 or 3 days lag. The next type is a

finish to finish. So task B cannot

finish until task A finishes. For

example, if task A is installing a

ceiling grid and task B is installing

the tiles for the ceiling to be

complete, both both tasks must finish at

the same time. And by far the most

confusing one is start to finish

relationship. So task B cannot finish

until task A starts. So say the only

good example of this I've seen is that

say you're decommissioning an old power

system. So task A is to start your new

switchboard. Task B is to decommission

your existing switchboard. You can't

turn off the old system until the new

one comes online. Again, there's this

key concept of mandatory verse

discretionary linkages. And this is

really important to understand when

you're creating your schedule because

one of the biggest mistakes I see people

make is they put in a whole lot of

discretionary linkages and their

schedule becomes too complicated too

fast. A mandatory link is something that

must be carried out in order. For

example, you can only complete the

concrete pore once the foundation is

excavated. It is physically impossible

to do it any other way. Discretionary

linkage is where tasks are sequenced to

save money, optimize resources or other

benefits. For example, you might choose

to use less resources and extend the

duration of the project because you want

to use less supervision. So that's an

example of a discretionary linkage. Now

you can have activities just finish and

start as they come or you can have the

leads and lags between activity. A lead

time is starting a task before the

previous task is fully finished. A lag

time is delaying the start of the next

task before the next one starts. Another

important term to understand is the

baseline schedule. The baseline schedule

is the approved plan. It's the contract

schedule. It's what we said we were

going to build at tender. It's what we

signed a contract to deliver. This is

the basis of how we're going to deliver

the project and it's going to be used to

assess and track progress. So, we're

going to report on progress against our

baseline and it's going to be used to

assess variation. So if there's a change

the way we're working change the

completion date always going to refer to

the baseline schedule versus what we

have currently. Another important

concept to understand is schedule

levels. So schedule levels refer to

level of detail in the schedule. We have

level one which is the highle master

schedule which is what the client will

be seeing. It's just very high level

showing key things like design,

construction, commissioning, handover.

Level two would be a package or area

schedule where you've broken out say

construction, you've got it broken into

earth works, concrete works, structural

works and it's broken out into more

detail. Level three is a target schedule

where you break down again say

excavation into a couple of key

activities with milestones and this is

where you sort of capture the interfaces

between the different areas. Then below

that, your level four to six schedules

is the schedules the construction teams

or the relevant disciplines use to plan

out their work in detail. They might

have a two to six month program, a 3we

look ahead, and then a daily plan. So a

daily plan of exactly what's going to be

done each day, which will roll up into

your 3-week plan. So what are we getting

done in the next 3 weeks? What's every

single task we need to do? And this will

be captured in your midterm program. But

these all need to align with the level

three schedule, the level two schedule,

the level one schedule. So I like to

think of scheduling into two broad

categories of activities. We've got

development and we've got

implementation. So development is where

we create the initial schedule. It's

where we create our baseline schedule of

plan for how to deliver the work.

Implementation is then when we put this

plan into action. A lot of people refer

to this as monitoring control, but to me

that's wrong. We're not just monitoring

and controlling a schedule. We actually

need to put the plan into action. The

schedule baseline is our vital that

tells us what needs to happen and when.

We need to take this plan and we need to

follow it. And if things change, we need

to change the plans. What happens so

often on projects is people ignore

implementation. They create this super

detailed amazing schedule, put a ton of

effort into it. Then when it comes to

delivery, they just ignore it. So that's

why I like to think of it not so much as

monitoring and controlling but

implementation taking the plan and

putting it into action. So development

is creating a plan for how to deliver

the project. Our plan is our project

schedule. Tell us all the work we need

to do the start and finish date of all

the activities the durations and the

linkages. What needs to happen before?

What needs to happen after? So there's

six steps to building a schedule. Step

one is to identify all the activities.

what is all the work we need to do to

deliver the project. Step two is to

sequence the activities. We take these

activities, put them into a logical

order. We then estimate the durations,

develop the model. So put all this

together, the tasks, the sequence, the

durations. It gives us our schedule

model, our Gant chart. We then optimize

and analyze this. Is it breaking any

constraints? Are we running over our

finish date? What do we have to change?

And then we get feedback and input from

our stakeholders to check that

everyone's happy with it. Makes sense.

It captures how we're going to deliver

the project. And then we've got

implementation. So building a plan and

doing nothing with it is pointless. It's

a waste of time. But it happens all the

time in constructor. People spend so

much time planning and then they do

nothing with their plans. The only value

a plan has is when it's followed. So

schedule implementation is putting the

plan into action. So how do we put a

plan into action? We need to understand

and interpret the initial plan. We need

to take our master project schedule and

we need to work out what's going on.

What do we actually have to deliver? We

then take a chunk of this our scope of

works what we need to deliver and we

develop a short range program. So

depending on the type of project you're

doing, this might be a 3we look ahead.

This might be a three-month look ahead.

We then focus on our enablers. What do

we need to get ready? What do we need to

have in place to deliver the project? We

then manage our lead times. We look

ahead far enough. How far ahead do we

have to order materials? We get

everything ready in time. We then track

and monitor. We look at how much work

we're getting done, what the plan's

telling us. What do we need to change?

And if things are deviating from the

plan, we implement corrections. Don't

worry, I'm going to cover all these

steps in a lot more detail in just a

second. So schedule development is how

we build a schedule that complies for

the project requirements, captures the

construction methodology, optimizes the

construction methodology, so comes up

with the best solution both in terms of

cost, time, safety, quality, factors in

our constraints, so limited resources,

access to site. It's easy to understand

and follow and it can be used as a tool

to manage the construction work. So the

schedule we develop has to tick all of

these boxes. So the first step in this

process number one is we need to

identify all the activities. This is

creating our activity and task list. All

the tasks that need to be completed to

complete the project. We do this with

our work breakdown structure which is

our hierarchical decomposition of the

project scope. We take the overall

project scope. We break it down into

component pieces. Now our activity list

is going to be a function of two things.

The scope of the project, so the

drawings and specifications, what we

need to do, but also our methodology. So

our methodology is an important factor

to consider when we're creating our work

breakdown structure. We're going to make

important decisions around how to

deliver the project which will actually

influence task list. For example, are we

going to use pre-cast concrete or we

going to do insitue concrete works? Can

we get stuff fabricated off site? We're

going to build it on site. We're going

to break an area down into four separate

areas and have four separate crews in it

or we just going to have one big area. A

lot of the steps we go through when we

create our work breakdown structure are

going to be driven by the methodology we

choose. As an example, the work

breakdown structure for a road project.

So, this is what we need to create for

our project before we can begin building

a schedule. A road project we might

break down into earthworks, structures

and bridges, utilities, and road works.

Under each of these tasks, we then break

them down into another level of detail.

For example, earthworks. We could break

down into clearing and grumbing, bulk

earthworks, drainage, and subgrade

preparation. Our utilities might be

broken down into services,

installations, street lighting, traffic

signals, utility relocation. So each of

these tasks then break down into another

level of detail. Again, within the

utility scope, we had street lighting.

So street lighting we could break down

into the pits, conduites and

foundations, the lighting poles, the

distribution boards, the power supply

boards and the circuits and luminers.

From this level we can then create our

list of work packages. Work packages are

the tasks in the schedule. To create our

actual work packages, we've taken the

project and we've broken it down into

three zones. So pits, conduites and

foundations. We've got zone A, zone B,

zone C, zone D. We've done this for all

the different tasks. pits, conduits and

foundations, lighting poles,

distribution boards, circuits and

luminers. Based on this, if we were

turning this into a schedule, we would

have a task in our schedules for pits,

conduites and foundations in zone B.

We'd have a task in our schedule for the

circuits and luminires in zone C. So,

this is our work breakdown structure

dictionary, our task list for the

project. So, when you're doing this, I

just want to stress the point that

methodology is an important input to

creating your task list. For example,

you might have a 200 m cubed concrete

slab. You could do this in two pores or

you could do this in one paw. Depends on

whether you're going to add a

construction joint or not, whether

you're allowed to, whether you can get

approval from your client. If you have

two pores, obviously have to reflect

that in the schedule. You have one pour,

your schedule will look different. So,

actually, how you choose to build it

will impact your total task list. Again,

as an example, let's build a really

simple schedule for this concrete slap.

So you can see this concrete slab here.

We're going to break it down into a

series of tasks and we're going to start

entering it into a GAN chart. So we got

this concrete slab. We can see it's a

100 mil thick concrete slab. There's a

series of ground beams. Review the

drawings and we look that you can see

with the ground beams. There's no

construction joints between the beams

which we can assume we can pour the

whole thing at once. So I'm using a

simple Gant chart software for this. So

first thing we have to do, we have to

identify the tasks. Let's do we'll break

it down into initial and concrete. So

we've got mobilization, bulk earth works

and materials. So these are three tasks

that have to be done before we can start

works. And then for concrete. So once

these are done, we can actually start

the concrete works. Got detailed

excavation. So this would be excavating

for all the ground beams. We'd have

formwork. So this is putting the

formwork around the edge of the slab.

We'd have steel fixing. Just call that

formwork

placement steel fixing concrete pour

curing. You could show this as a task or

a lag. We'll show it as a lag. So we'll

add this later. Concrete pour formwork

strip. They are all the tasks in our

schedule. Our work breakdown structure

is really simple. So we've got this set

of tasks under concrete and this set of

tasks under initial. After we've defined

all the work we need to do to complete

the project, what we have to do next is

to put them into sequence. Now

understand that this happens

iteratively. We go through, we find the

task, we put them in order, we realize

we miss some tasks, we go back, we do

it, understand happens iteratively, but

laying it out as a six-step process,

it's just an easy framework to think

through it. So next we're going to talk

about how to sequence the tasks. So

sequencing the task is capturing our

methodology. It's putting the work in

the order it needs to be done. What

needs to be done before a task and what

can be done after. This is referred to

as the network schedule. You don't have

any durations as the tasks and linkages.

We also want to introduce our leads and

our lags. So, for example, after we pour

concrete, how long does it need to take

to cure? These are our leads and lags.

And we've already spoken about the

different types of linkages. our

mandatory linkages, what has to be done

a certain way, and our discretionary

linkages, choices we're making about how

to sequence tasks. Now, my really strong

recommendation is when you do your first

cut of the schedule, just focus on

mandatory linkages. Big mistake I see

people make is they do both at the same

time and it gets really confusing. When

you do your first cut of the schedule,

keep it simple. Just do the mandatory

task linkages. Okay, so let's take from

our example road project, the work

breakdown structure we had in the last

section. Let's break this down into a

network schedule for the street lighting

activities in one zone of the project.

So we can start the street lighting

works, the pits, conc, and foundations

once the earth works are complete. So

we've got a milestone in our schedule

for earthworks completion. Because the

foundations have a 5-day curing time for

the concrete before we can start

standing the poles, we have a 5-day lag

before we can supply and install the

street lighting poles. We then can also

supply and install the distribution

boards. And once these are done, once

we've installed the poles, we've

installed the distribution boards, we

can start installing and terminating our

cabling. And the completion of this,

we've got our street lighting in zone A

complete. This that's the general

methodology of how they we're going to

do the job. We have to do the pits,

commutes, and foundations first. We have

to wait for the concrete to cure. Then

we do our poles, install our

distribution boards, and then we can

install our cabling. Okay. So, for our

concreting project, let's go through and

do the same thing. So, our initial tasks

are going to have no predecessor in

them. They're just going to be the start

points of our schedule. So, we have no

predecessor. We'll just give it a fixed

start date. So let's give it today's

date 12th of May 25. Same with our

earthworks and same with ordering our

materials. These are all going to start

on the same date. They're going to have

no

lag between them. What happens next? So

the first thing we need to do is we need

to do our detailed excavation. So for

that to be done, we need to mobilize the

site and we need to have done our

detailed excavation. Remember, we're

putting no durations in yet. So we're

going to go through and fix up these

durations in the next section. Then we

can place our formwork once we've done

the detailed excavation

and we can start the steel fixing at the

same time. So, so steel fixing formwork

start at the same time. Once our steel

fixing and formwork's done, we can place

our concrete. So, we need seven and

eight complete to the concrete pour and

we then can strip our formwork once

we've done that. Importantly, but when

we pour our concrete, we have to wait

for it to cure. So, we have to wait. We

have to introduce a lag. So, we got four

strip and we're going to introduce a

5day lag to allow for the concrete

curing. I think I've done that wrong.

Ah, sorry. It's that wrong task. So, I

make that concrete pour with a 5-day

lag. And that 5-day lag, you can see

here that is the concrete curing time.

Once that's done, the tasks are good.

Okay. So, we know the tasks, we know the

order. The next thing we need to know is

the duration of each task. We have to

estimate from start to finish how long

each task will take. Now this is going

to be a function of the activity itself,

the nature of it and the resources we

apply to. Remember at the start we spoke

about the difference between a

productionbased task which is purely

driven by resources and their

productivity and a programbased task

which has some sort of fixed set

duration. We also need to consider

whether we're self-performing a task or

whether we're subcontracting a task. So

that's going to impact how we go through

the process and estimate the durations.

We also need to consider the calendar.

So the calendar is the days available to

work. Are we working a 24-hour shift?

We're doing night shift. Are we working

Monday to Saturday or only working

Monday to Friday? Are there a ton of

public holidays coming up? So on and so

forth. So we need to consider available

working days. Okay. So when we're

estimating the duration of an activity

and it's a productionbased task, it

depends on a quantum of work. So say we

have 1,200 m of trenching to do. We then

need to know a productivity per So

for example, 40 m per shift which is

going to be driven by the resourcing we

allocate to the task and the task

itself. So whether we're going to have

100,000 or one crew that's going to give

us the total number of shift that task

going to take. So if we have 1200 m of

trenching, 40 m per shift, we're going

to take 30 shifts to finish the task.

Now, if we're self-performing a task, so

using our own labor plan materials, we

need to do a bottom up estimate to

determine how long the task will take or

we can use benchmark information from

other projects. The key is we're using

our own labor plan and resources. So, we

need to come up with the productivity

rates. Now, on the other hand, we might

be subcontracting out a task, which

means engaging an external contractor to

complete it for us. Subcontractors will

have agreed upon programs in their

contracts which we can use activity

durations in the agreed upon programs to

estimate. Then we can independently

check and verify this using a bottomup

estimate or a parametric estimate. But

when we're subcontracting a task, we'll

need to take the subcontractor's program

of works and integrate it into our own.

Now when we did that calculation of 1200

m of trenching, 40 m per shift gives us

30 shifts. That's not the actual

duration of the task. That's the number

of shifts it will take. The schedule

calendar is going to help us determine

the start and finish date of the task.

Are we working 6 days a week? Are we

working 5 days a week? Public holidays,

night shift, all these sorts of things

captured by our schedule calendar. Okay,

going back to our street lighting

example. Say we have civil self-perform

work. So, we're managing work ourselves,

an electrical subcontractor doing the

light poles, installing the distribution

boards, and doing the cabling. Let's

work out how we work out how long this

task will take. Okay, so for our civil

selfperform works, because we're

self-performing the works, we need to do

a bottomup estimate. So we're looking at

the working hours for the day. Say it's

a 10-hour day, and we're allowing for 3

hours of non-productive time. We've got

pre-start, we've got lunch breaks, we've

got setup, packup, these sorts of

things. So we get really 7 hours a day

when we're working. AU know a crew from

past project data can install 20 m of

condute per hour. This equates because

we've got seven productive hours per

shift. This equates to 140 mters per

shift. For our pit installation, a crew

can do half a pit per hour. So, it takes

them 2 hours to install a pit. And for

our foundations, again, they can do half

a foundation per hour. Takes them 2

hours through a foundation. So, we can

do 3 and 1/2 foundations per shift and

three and a half pits per shift. Now, we

also know the total volumes of work. So,

based on these total volumes of work, we

can come up with a total number of

shifts. So we've got 25 shifts for the

condute installation based on 140 m per

shift, 40 shifts for the foundations and

10 shifts for the pit. So this is just

based on total quantity of pits and

foundations. And this gives us a total

number of shifts for all these tasks. So

we need 75 shifts of work to complete

the civil works in zone 8. Okay, let's

go back to our example. Schedule the

concrete foundation. So I'm not going to

do quantity takeoffs and work this out,

but this is how you'd have to do it.

You'd have to say detail excavation

there's 100 m cubed of soil to move. We

can move 20 m cubed per shift. So it'll

take five ship. That's the type of

calculation you have to do. You do these

calculations and then you enter the

durations into the schedule. And since

we've already put in the linkages, it'll

fix the task. So formwork, we say say

there's like 100 m squared of of

formwork and then we're going to put

four guys on it and it'll take three

shifts to do the edgeboards. Steel

fixing, there's 20 tons of steel. It's

going to be two guys on it. It's going

to take um four shits. So, as we put in

these numbers, you can start to see that

our schedule's actually coming to life.

So, we got the concrete paw, which

concrete paw will take one day, and then

the former trip will take 2 days. Based

on this, we've actually created our

schedule model. So, we know the work's

going to start on the 13th of May, and

it's going to finish on the 4th of June.

So once we've got our tasks, our

sequence, our durations, we put all this

together. We get our schedule model, our

Gant chart. These are our activities

displayed against time represented by a

bar chart. They show the activities, the

plan start and end dates, the activity

durations, and the start and end dates

of your overall project. So you can use

the traditional way of doing it by hand.

But the reality is in 2025, you're not

going to be doing that. you're going to

be using some sort of software tool to

create your schedule model. It's really

a couple of different tools we've got at

our disposal. I'll categorize these

based on what typically project

engineers or construction people would

use. Then you've got specialist software

that planners and project scheduling

professionals tend to use. So for

project engineers a lot we'd use Excel

to do something like this. This might

just be listing out your tasks and

shading them to represent the bar chart

to the GAN chart. And we use this a lot

for things like a 3we look ahead or

short range programs. Slightly more

concept like a six week look ahead or a

mid-range program. You might use

something like Microsoft Project. I use

Smart Sheet because I just find it way

easier to use the Microsoft Project. As

a project scheduling professional

though, you're probably going to be use

something like Primma Vera P6 which

would have your master project schedule

might have thousands of lines on it for

a big project or the same with inate as

another proper project scheduling tool.

Okay. So once we've developed the model,

once we've put that information into

project or a similar tool, we've got our

GAN chart. The next thing we need to do

is we need to optimize and analyze it.

Need to look at the critical path. We

need to work out if it's violating any

constraints. So the key question we need

to ask here is the schedule going to

meet the objectives of the project does

it fulfill our requirements. So we need

to ask questions like are we going to

meet the finish date? Are there any

interim milestones we need to consider?

What is the critical path? Which

activities have float? Can we optimize

resources? Are there ways to minimize

and reduce risk? And overall we kind of

come to the conclusion is the schedule

correct for our project? When we do this

analysis, we're really going to be

looking at the critical path and asking

the question, is the critical path

correct? Because at the end of the day,

that is what is determining the duration

of the project. That is what has to make

sense and be correct. You can be wrong

about some activities that have more

float. Ultimately, it's not going to

have much of an impact on the contract

you sign with your client. The critical

part's wrong. If you have incorrectly

calculated how long the project will

take, it can have big consequences.

That's why when you're doing this

analysis, you always want to first look

at the critical path and ask yourself,

does it make sense? Is it correct? Are

the activity durations correct? So often

when you look at a critical path, the

project, there's something the schedule

model is telling you, but you just know

that the information it's giving you,

the result it's giving you is wrong. It

just doesn't make sense that in reality,

this would be the critical part. The

biggest issue tends to be that resource

estimates are either conservative or too

aggressive. That's what tends to be

wrong. When you look at the critical

path, you see it and you realize like

this isn't actually what would delay the

project. We'd add more crews to this

task. So then when we're coming to the

question of how do we optimize the

schedule, there's really two principal

things we can do. We can come up with a

smarter way to do things or we can spend

more money and have risk. When we're

talking about coming up with a smarter

way to do things, we should do this for

all activities. We should always be

questioning ourselves and asking, is

there a better way to perform the works?

The other hand, if we're talking about

introducing risk and spending more

money, we should only be applying that

to critical path or near critical path

task. Remember, the critical path is a

calculation on a year-long project. If a

task has 10 days float, less than 10

days float, for all intents and

purposes, it is on the critical path.

your schedule isn't going to be accurate

to the day where so you can confidently

say that this isn't on the critical

path. If it has less than 10 days float

and it's like a year-long project again

it depends on the overall duration

proportionate to the level of float.

Critical path near critical path in my

opinion the exact same thing. So as we

spoke about when we were defining these

scheduling terms for these critical path

or near critical path tasks, we can

crash them. We can add resources to them

that's going to increase our cost or we

can fasttrack them. We can overlap them

which introduces risk. Okay. So the

important final step in developing a

schedule is to get our stakeholders to

review it. This is going to really tie

into when we talk about implementing

this schedule, but we don't want to just

build a schedule in isolation. And we

want people to give us feedback. We want

them to tell us what's wrong, what's

right, review it, pick up errors we've

made. Basically, get the whole team on

board to get everyone to say, "Yes, this

is the plan. We're going to follow to

deliver the project." The other way to

think of a stakeholder review is just

getting their buy into the plan. You

want people to say, "This is my plan.

Yes, we can achieve it. Yes, we are

happy with those dates. We're happy to

meet them." A schedule is completely

useless if nobody follows it. You need

to ensure the plan is realistic, people

understand it, and that people own it.

They've given it their ticket of

approval, they've given their feedback

into it, and they say they're willing to

help achieve it. So, up next, my

favorite topic in project scheduling,

and the one everybody ignores, schedule

implementation. Schedule implementation,

put simply, is the process of turning

our plans into action. We've spent

schedule development building a

schedule, creating it. Next thing we

need to do is we need to turn that into

a series of tasks that we perform to

complete the project. Time and time

again in my career, I've seen people put

all this effort into building fancy

schedules. They've spent hours working

on them. They workshop them. They've

done all this stuff. And then when it

comes to actually delivering the

project, as soon as it starts to get a

little bit chaotic, they throw the

schedule out. They put it in the drawer.

They never look at it again. And then

the project becomes a disaster. All that

time they spent building the schedule,

thinking through everything suddenly

becomes wasted. The core message is that

planning without action is a form of

procrastination. It's a complete waste

of time. So if you're not even going to

bother following the schedule, why did

you spend all the time building it to

begin with? So when we really dig deep

and think about it, the only value a

schedule has is when we follow it. Sure,

it helps us to assess feasibility and

cost, but the real value in a schedule

is to help us deliver the project. It's

pointless to develop a schedule if we're

never going to implement it. So schedule

implementation is all about putting the

plan into action. It's about planning,

coordinating, and delivering the works

in accordance with the original plan.

It's the process of executing the plan

laid out in the master schedule. So

we're going to take the highle project

schedule we developed the master

schedule to implement it. We're going to

break it down into clear detailed

actions. We're going to take the

schedule and turn it into a list of

tasks we need to complete a to-do list.

The goal is to make the schedule usable

on site and turn it into a real world

setup of actions. A to-do list that we

simply follow to put the plan into

action. Step one in this process is to

understand the schedule. Now remember on

most projects say we're in the

construction team or the delivery team

we probably didn't deliver or develop

the schedule. Sure if we were lucky

enough to work on tender and then move

into construction we would have but a

lot of the times we'll be thrown into a

project and the first thing we need to

actually do is to understand the

schedule. So this will be reading

analyzing and interpreting the schedule.

When we do this we want to be hyper

critical. We want to understand

everything in detail and we also want to

pick up all the mistakes and gaps. We'll

typically get something like this. A

whole lot of tasks with start and finish

dates red to represent the critical

path. When we're onboarding ourselves

onto a project, we need to understand

the drawings. Need to understand

actually what we're building. Then the

next step will be to look at how the

drawings are mapped to the schedule,

what we're building and how it relates

to the plan. What's the methodology?

What's the proposed resourcing? And we

do that by analyzing the schedule. So

the reason I said originally is that we

want to be hyperritical when we do this

is because schedules are always wrong.

There's always things missing. There's

always activity and linkages that are

wrong. There's constraints or

circumstances that have evolved that

weren't there when the schedule was

originally developed. There'll be detail

missing and have been changed. So when

we're going through the schedule, we

want to understand that this was the

plan, but it won't exactly match

reality. We need to be hyperritical and

to understand what is potentially

changing. Your job is to question

everything. Be hyperritical. Understand

the logic. Again, at the end of the day,

your job is to achieve the project

outcomes, the finish date in the

contract, the time the project needs to

be completed by, not to follow the

schedule. Your job isn't to blindly

follow the schedule. It's to understand

it, understand the logic, and pick up

any errors in it. The next step is that

we want to decompose the schedule. We

first understand it, then we decompose

it. We want to the master schedule

that's developed will generally be

relatively high level. It'll have a

start and finish date for trenching, an

access date, and a completion date based

on highle productivities. When we're

talking about implementing a schedule,

we need to break it down into specific

activities and tasks. These tasks will

be more detailed than what was in the

master schedule and we're breaking it

down into more detailed schedule levels.

We capture this in a short range

program. So a short-range program is a

highly detailed short-term schedule that

we use to plan and coordinate all the

minor activities that needed to

facilitate the works. We could use

something like like an Excel document, a

whiteboard, or even markups and staging

plans. We use some sort of time slice

method to do this. So we'll have a

window of focus might be 3 6 9 weeks

depending on the project and I'll talk

about how exactly to determine this time

slice you need to choose and then we

take the t the task and the master

schedule and we need to break them down

into extensive detail into every minor

thing that needs to happen to ensure

that finish date for the task is

achieved. Let me give you a quick

example of what I'm talking about. Say

in the master schedule we have basement

excavation. That's a task with a start

and finish date that probably won't

capture any more information than that.

We know the start date of the excavation

and we know a planned finish date that

the planner developed probably based on

quantities and assumed productivity

rates. The 3we look ahead 6 week look

ahead depending on the time slice we

choose needs to capture every single

activity that has to happen to ensure

the basement excavation is completed by

the state. So this means floating the

machine to site, getting the surveyor to

mark out all the depths of the

excavation, setting up barricaded and

temporary fencing around the excavation,

excavating to the first design RL, then

setting up shoring. So every task that

has to happen will be captured in our

3WE or short range program. Now when

you're doing this, you're going to add a

significant amount of detail. The only

way you're going to know exactly what

this detail is is if you have a really

solid understanding of the construction

methodology or more likely you have

access to people who understand what's

involved in the works. You need to

understand the methodology in detail.

List turn the tasks into subtasks that

will all have their own dependencies and

linkages. Now you might not capture this

in a formal Gant chart or schedule might

just be an Excel list. You need to

understand the overall task is going to

be broken down into 20 or 30 subtasks

and all these tasks relate to each other

as well. Now, let me give you a really

simple threeear heads for some street

lighting, civil work. So, we've got

trenching and pit install for a certain

range of the road. And then there's

tasks allocated to this. For example,

they need an excavation permit. They

need service proving to identify

ingground services. And there's a

planned start and finish date. We're

also going to have quality assurance and

testing. So, testing the conduites,

checking they're all installed

correctly. We have another crew doing

that. We have a crew doing the road the

road crossing at John Street. Again,

they need an excavation permit and

there's a planned start and finish date.

And we're also going to be installing

light poles on the bridge where they

need a lifting permit. So, we've mapped

out the task, the permits we need, who's

doing it, whether they need traffic

management or a road closure, and the

plan start and finish date. Now in our

master schedule there might only be one

line item in the schedule which says

street lighting civil works in zone 2.

Now through look ahead has broken this

all down into detail. Now the obvious

question when we're doing this is how do

we work out what all of our subtasks

are? Well that comes down to pull

planning. So pull planning is a tool

where we ask ourselves before any task

that's coming up, what is everything

that needs to be in place to facilitate

this task and it helps us to transform

our schedule into a to-do list. So let

me give you an example. If we're talking

about the master project schedule

showing a certain concrete structure, so

a planned concrete p, let's think about

everything that needs to be in place to

facilitate this concrete p. We need the

excavation complete. We need the survey

set out. We need any service

penetrations within the slab installed.

We need the materials to do the work.

So, we need temporary materials like

formwork and consumables. We'll need the

steel reinforcement. We'll need the

concrete supply booked in. We'll need a

subcontractor to complete the works or

our own internal labor if we're

self-erforming the task. We need safety

documentation and we'll need quality

documentation. That is a list of things

we need to get ready to complete the

concrete pour on the fixed date. None of

this will be in the master schedule. The

master schedule will just show the

concrete pore. Now, so before I

mentioned a 3we look ahead is an example

of a short range program, but I also

made the comment that the time slice you

choose for your short-range programs

depends a lot on the task. Now, all

these different activities, ordering the

materials, getting the subcontractor on

boarded, all these things take time. So,

this leads to the point of how long

should your short range program or your

detailed to-do list be? And it really

depends on how long this stuff takes to

get ready. Depending on the type of

project, it might be really quick. If

it's a more complicated project where

you've got longer lead times for

materials, you might have to be looking

3 or 4 months ahead to ensure things

stay on track. So, this is the idea of

activity lead times. So activity lead

times are basically just the time it

takes to organize everything before we

do the work. We need to consider for

example the concrete the materials we

need for the concrete foundation. We'll

need steel reinforcement. So we need to

allow for time to get it fabricated. We

need to allow for time for the Rio

supplier to get shop drawings and steel

reinforcement. We need to get those

reviewed and approved. we need to

actually award a contract to them to

supply the materials, which means we

need multiple quotes and to go through

some form of procurement process. Okay,

so let's imagine we have a concrete pour

on the 28th of June. For this concrete

pour, amongst the 20 other things we're

going to need ready, we also need the

steel reinforcement on site, which means

if there's a 3we lead time for the steel

reinforcement, we need to award the

contract and place the order by the 7th

of June. If we need to allow four weeks

to get quotes, to negotiate rates, to

get internals approvals, to sign off the

contract, we need our quotes back by the

7th of May. So, 1 month before that. If

we need 4 weeks to review drawings, do

our quantity takeoffs, prepare our

tender packages. That means we need IFC

drawings that tell us what still

reinforcement we need on the 7th. So,

that's just one example of one chain,

which is to procure it. So you can begin

to see how far ahead you need to be

planning to ensure a concrete pour on

the 28th of June isn't delayed. Now

depending on the project, these dates

will change, but the example of the

concrete pour, you need to be thinking

about a June concrete pour as far back

in April. Now I've worked on solar farms

where we've been ordering transformers

that have a 70we lead time. So the core

message I'm trying to give you here, you

need to be really planning far ahead to

be allowing enough time for all this

stuff to happen. Again, the core

message, think about what needs to be in

place for the activity to happen and how

far in advance you need to be getting

that stuff ready. So the core process

I've spoken about here is to decompose

the master schedule into a series of

subtasks. You do this by identifying all

of the tasks that need to be completed

for the activity in the master project

schedule to be completed. And to do this

effectively, to make sure the master

schedule isn't delayed, you need to

understand how long this stuff takes to

get ready by understanding activity lead

times. So at the end of the day,

schedule implementation is where

scheduling meets time management. So

much of scheduling implementation is

just being organized, preventing

roadblocks before they occur. Thinking

through what has to be in place for this

to happen. Constantly asking yourself

the question, have I identified

everything? Is it ready? Is it going to

be ready on time? Effectively, what

you're doing in this step is you're

taking your schedule, you're

transforming it into a to-do list. This

might be done in Microsoft Planner, but

I've always found with schedule

implementation, you don't really want a

complicated GAN chart. You just want an

Excel document, a to-do list, a

whiteboard, something really simple that

the team can see and everyone can be

working back from. Okay, so we've taken

the plan and we've worked out how to put

it into action. Next question comes up

is how do we know we're sticking to the

plan? So that's why this next section

we're going to talk about monitoring and

controlling the schedule. How do you

ensure you're staying on track? Now,

there's a lot of different ways people

express the monitoring control process.

I like to think it of asking a question.

How do we ensure we are following the

plan? Schedule development. We built a

plan. Schedule implementation. We took

that plan. We turned it into a to-do

list. We started working through all the

actions to put the plan into action.

Monitoring and controlling is then the

process of checking that what we're

doing matches the original plan. And if

it doesn't, updating the schedule and

addressing variances. Now, when we built

the schedule, there were assumptions.

There were guesses. There were unknown

and unknowable things. And that's just

the reality of construction projects.

Every single construction project is

different. Every project is unique. When

we're planning the projects, there are

things we cannot foresee. There's

changes that will happen. There's

unknown and unknowable things that will

happen. So, by monitoring, controlling

the schedule, progress tracking, we need

to keep the plan relevant and useful.

It'll help with managing our

stakeholders and it helps us to identify

issues and deviances early. So

fundamentally monitoring and controlling

the schedule means tracking progress

comparing how much work we're doing

versus what our baseline plan is

understanding deviations from this plan.

So understanding delays and then when

there are are delays applying treatments

to them effectively monitoring

controlling the schedule helps us to

ensure the plan is still useful and

relevant. It helps to ensure it still

remains a useful planning and

coordination tool. It helps us to then

plan activities, book resources, and

make informed decisions about cost,

time, and scope. And if the information

in the schedule's wrong, if it's not

updated, then it can't be a useful tool

that helps us do this. Now, let me work

through an overly simple example, but

it's here to illustrate the point of why

you want to keep the schedule relevant

and useful. Say cable installation

begins after the conduit are complete.

The condute installation is currently at

10% complete, but it should be at 90%

complete. Looking at our schedule, our

cable install is planned to start next

week, but cable procurement has been

delayed and everyone's stressed because

the cable's not going to be here in time

to start installing it. We've got an

option to pay for an expedited delivery.

The question is, should we do it? Well,

looking at these numbers, obviously not

because you can see the condute install

is only at 10% complete, even if it was

meant to be at 90% complete. If we're

updating our progress, tracking our

numbers, we can clearly see the cable

installation activity that's planned to

start next week isn't going to happen

because the conduit installation is so

far behind. The question, should we pay

for an expedited delivery? Obviously

not. Okay. So schedule helps us to make

informed decisions around our progress

and planning and coordinating the works,

but it also helps us to manage our

stakeholders. The schedule's used to

inform our stakeholders of progress

becomes the source of truth they can

look at to see where everything's up to.

Often it's also a contractual

requirement to maintain a schedule

written into the contract we have with

our client that we'll need to provide

them fortnightly or monthly progress

updates. The schedule is how we capture

realistic information. How far we're

through different tasks like procurement

or what percentage we're complete we're

on piling. Now the final reason we

should monitor and control our schedule

and keep it relevant is it gives us a

way to look into the future. It's a lead

indicator helps us to know if

something's going to go wrong before it

goes wrong. This is the opposite to a

lag indicator where something goes wrong

and retrospectively we can look at it.

So, a lead indicator is a way of seeing

into the future and preventing mistakes

before they happen. As an example, say

we know our piling is 10% complete at

the end of week one and our schedule has

a 4-week program for piling. It's a

critical path activity. So, any delays

to the piling will delay project

completion. What should we do? Well,

clearly we're going to delay project

completion because we're 10% complete

and we should be around 25% complete. We

could look at options to do weekend

work. We could look at options to do

night shift. We could look at options to

bring in another piling rig. The only

reason we know that is because we

understand the schedule. We know it's a

critical path task. We know it's 10%

complete at the end of week one rather

than 25% complete because we've tracked

progress and we've maintained our

schedule. Okay. So, the first part of

scheduling, monitoring, and controlling

is progress tracking. Progress tracking

is basically just determining the

percentage complete of each task in our

schedule. And it's a really simple

process. We first need to understand the

activity we're tracking. We need to set

up a progress tracker. And then we need

to monitor the activity and record the

actual quantities of work complete.

Okay. So first when I say we need to

understand the activity we're tracking,

we really want to understand whether

it's a production driven task or a

milestone driven task. Production driven

task means the activity can be

represented by a baseline quantity. The

progress for the task is the quantity of

work complete. For example, if we know

we need to do 10 km of trenching and

we've done 500 m of trenching, we've

done 5% of the work. For examples

completed verse the total numbers of

piles. A milestone-driven task on the

other hand is an activity that is a

group of different sub activities where

there's no consistent metric we can use

to track them. Classic example of this

would be procurement. You're not going

to track the number of words of a scope

of works that someone's written. It's

just a series of different tasks grouped

together. So you might have writing a

scope of works, issuing the tender,

getting quotes, contract award. You

track these by giving fair

representations of the work to each of

the sub activities and tracking whether

that sub activity is completed. Okay. So

if we want to set up a progress tracker

for a production driven task, we want to

determine the activity to be tracked. We

want to determine the total quantity of

that work from the design. So for

example, we've got we're tracking

trenching. We've got 10 km of trenching.

Then we want to determine the start and

finish date for the activity to give us

a daily quantity or weekly quantity we

need to be completing. Okay, let's do an

example for street lighting civil works.

We want to track the percentage complete

of the street lighting civil works in an

area. However, we run into the challenge

where we've got three different tasks

for tracking. We've got pit

installation, condute installation, and

foundations. The metrical we want to

track is linear meters of condute

installed because that's the biggest

task. We could say for example we could

have tracked the overall task by the

number of pits or the number of

foundations but in this sense made the

most sense to track by linear meters of

conduit which means we have to represent

pit installation as equivalent to 20 m

of conduit. This would be done based on

say if a pit takes 4 hours to install

and 20 m of condute also takes 4 hours.

We could just baseline it like this.

Again we're saying a foundation is the

equivalent of 60 m of condute. Okay. So

let's come up with a total quantity of

work we need to track in zone A for the

pits condutes and foundation. So condute

install we've got 3500 lineal meters

pits we're saying we've got 35 pits was

the which is the equivalent to 1,50 m of

condute and we've got 140 foundations

which is the equivalent to 2,800 m of

condute using that equivalence we came

up with in the previous section. Okay,

the next thing we need to do is we need

to come up with our daily targets. How

much work do we have to do per shift per

day? Or you could do this weekly or

monthly depending on the project. For

example, pits, conduits, and foundations

in zone A. We've got a design quantity

of 7,350 m with 75 shifts which come we

come up with a daily target of 98 m per

day. We can do this for all the

activities in our schedule. We come up

with a planned daily target. Then all we

do to track progress is we set up an

Excel template similar to this where

we've got for the activity we've got our

planned target each day, our planned

total, so our cumulative total, our

actual t what we actually got each day,

our cumulative actual, and then the

quantity remaining. So for example, on

the 1st of October, we plan to do 100 m.

Our cumulative total is 100 meters

because we've only done one day of work,

but we actually got 98 mters. The next

day, we planned to do 100 meters. Our

planned total is now 200 m because we

should have done 2 days of work. Our

actual quantity was 121 m. So, our

cumulative total is 219 m. So, you can

see that each day we track how much work

we did versus how much we planned, which

gives us the cumulative total and also a

quantity remaining. Okay, so if we want

to track a milestone-driven task, now

remember this is an activity which is a

set of sub activities with no consistent

quantity or metric we can track, we need

to determine the milestones that break

down the task. We need to set up some

sort of credit system and then we need

to monitor against this credit system.

Again, this isn't going to be as

objective and scientific as a

productionbased task, but it's still a

useful way of tracking activities that

can't be represented as a single

quantity of work. So for example, if

we're talking about procurement, we

might have the following milestones to

represent a task. The tender package is

ready and prepared by a team. The tender

has been issued to the market. We've

received quotes back. We've awarded a

contract and then they've mobilized the

site. So the activity of procuring a

subcontractor is broken down into five

different tasks. We then apply a

percentage to each of these tasks that

would in best match the reality of how

much effort or time that task would plan

to take as a representation of the

overall task. For example, the tender

package being ready, we represent as 10%

complete. The tender issued and sent out

to subcontractors, we represent as 20%

complete. The quotes received back from

subcontractors, we say we're 50%

complete on that task. The contract has

then been awarded, signed, and

negotiated. We say we're 75% complete.

The subcontractor on site, mobilized,

ready to begin works is the 100%

complete milestone. Basically, when

we're setting up a credit system, we

just want to come up with some

realistic, logical waiting of tasks that

represent the real level of effort or

duration. It takes one week to prepare a

tender, two weeks to get the quotes. The

activity of getting the quotes should be

worth two times the preparation of the

tender. It's really simple. It's just

how long that task we're planning for it

to take, how much effort does it take,

and just waiting the sub activities

appropriately. Then simply based on what

step we're up to in the overall process,

we can make a pretty accurate estimate

of the overall task completion. Again,

it's more subjective, less scientific

than a productionbased task, but it's

the best way we have to do it. The

better the metric we have, the better or

more accurately we've broken down the

tasks, the better the actual information

in our project schedule is going to be.

Just to summarize, where are we up to

terms of tracking progress? We've

understood the task. We understand if

it's production driven or milestone

driven. We've set up a progress tracker,

a way of capturing the raw work

performance data. And we're monitoring

our task every day. We're we're

recording how much work is getting done.

We're comparing this to our planned

targets. So what we've tracked so far is

our raw work performance data simply how

much work we're getting done. We can

then calculate a series of metrics with

this that help us to better understand

how we're tracking. So the first one is

percentage complete which is simply the

work we've completed divided by the

total quantity of work we need to do. We

can also calculate our production which

is the quantity we've completed divided

by the time elapsed which allows us to

calculate a daily or weekly production

what we're actually hitting. We can

calculate our schedule variance. So

schedule variance is the difference

between how much work we've done minus

how much work we plan to do. If we get a

positive schedule variance it means

we're ahead of schedule. We get a

negative schedule variance it means

we're behind schedule. Similarly, we can

calculate our schedule performance

index. So, schedule performance index is

the ratio of earned value, how much work

we've actually done divided by planned

value, how much work we plan to get

done. We can also calculate our

estimated completion date. So, estimated

completion date is elapse time. So, how

far we in are the task currently plus

the ratio of the work remaining divided

by our actual production rate. So

basically, we've done we're 5 days into

the task. We've got 100 m left to do and

we're doing 20 m a day. Then we're going

to need another 5 days to finish. That

gives us our estimated completion date.

Let's work through an example. Say we're

installing inverters on a solar farm.

We've got 100 inverters to install. Our

plan is to hit four per day, which gives

us an estimated duration of 25 days. As

an example, we're at day 10 and so far

we've installed 25 inverters. So at day

10 of the task, let's calculate all our

key metrics. So percentage complete.

Well, we've done 25 inverters. We've got

100. So we're 25% complete. Our actual

production, we've done 25 inverters over

10 days. So our actual production is 2

and a half inverters per day. Our

schedule variance, well, we've done 25.

We should have done 40 which after 10

days at four per day that's our plan

value if we'd planned to do four per

day. So we're 15 inverters behind

schedule. Our schedule performance index

is the ratio of what we done versus

where we should be. So we're at 625

which means we're doing 62.5% of the

work we should have been doing. And our

estimated completion date is day 10

where we're up to now. our elapse time

plus the ratio of the remaining work we

have to do by our actual production

rate. So we've got 75 inverters left and

we're doing two and a half per day. It's

going to give us 30 which means our

forecast completion date is day 40. As

you can see by calculating these metrics

we've given context to our raw data. The

next thing we need to understand is that

this information is only useful if we

act on it. So, it's great we've

calculated these metrics, but what are

we actually going to do about them? So,

this leads us to the idea of a

treatment. The only value information

has if we act on it. If not, it's a

waste of time. Same with planning

without action, it's just a form of

procrastination. So, what do we do if

the works are delayed? What do we do if

we calculate our metrics and we see that

we're behind schedule when we need to

apply a treatment? Treatments is all

about understanding what can we do about

the delay and choosing the optimal

solution to the problem. So when we're

choosing a treatment, we need to

understand first. So what type of

activity is being delayed? We need to

then identify the root cause of delay

and explore options we have and

correctly implement them. Okay. So

there's fundamentally two types of

activities that can be delayed. a

critical path activity which is an

activity that will delay project

completion and importantly we also want

to talk about near critical path

activity. So these would be activities

that have less than 10 days float or

whatever a reasonable reference point is

depending on the type of project you

have. It's short project it'll be plus

or minus one or two days of float. It's

a really really long project it might be

activities that have within 30 or 40

days of float. Idea here is your

critical path is a calculation. And so

it's never going to be 100% accurate.

The other type of activity that can be

delayed is a non-critical path task.

These are activities that have a

significant amount of float that we can

delay without impacting the project

finish date. Then we need to understand

the specific root cause of the delay. Is

it a resource constraints? Can we not

get enough people or machines to do the

task? Is it planning or scheduling

issues? Are we have we poorly planned?

Is our initial plan wrong? Do we have

project management issues? is we're not

managing or coordinating the works

properly. So we have technical

challenges. There's complex design or

construction methodologies or design

constraints that we need to address. Are

there external factors or stakeholder

approvers holding us up? Really need to

dig deep to understand what actually is

holding the activity back. What is

changed from when we prepared our

baseline schedule. So, we've understood

whether it's a critical or non-critical

task that's being delayed, and we

understand the root cause of the delay.

What can we then do about this delay?

Well, there's fundamentally two things

we can do about a delay. We can optimize

and improve, which is improving the

systems and performance, how we're

organizing the works, coming up with

better design solutions, all these sorts

of things. Or we can do both. Or we can

add cost and risk to make sure it's done

faster. This means crashing where we add

additional resources. we go from two

crews to three crews or we fast track

tasks. So originally we might have

planned to finish one task and then

start the next one. Maybe we can start

the following task with a 50% overlap.

Now for optimizing and improving the

task, we should do this for all

activities. We should constantly be

asking how do we do a better, faster,

cheaper with a better design. We should

always be doing that. That would apply

to both critical and non-critical task.

But if we're talking about crashing or

fasttracking activity, adding cost and

risk, we should only do that with

critical path or near critical path

task. But at the end of the day, going

to spend more money and add additional

risk. And the only reason we would

benefit from doing that is if it's a

critical path task. If we can delay an

activity and it doesn't impact the

finish date, then we shouldn't be

spending money or adding risk to do it

faster. Should only be doing that for

critical tasks. The fundamental reason

most schedules fail is because they're

disconnected from the way projects are

actually delivered. Here are 10 traps to

avoid so your schedules reflect reality,

and to get ahead of 90% of project

schedulers. I'm going to break these 10

traps into four sections: planning

mistakes, logic mistakes, communication

issues, and monitoring and adaption

issues. Planning mistakes are mistakes

you make while you're setting up the

initial schedule. And the first one is

being precisely wrong rather than

roughly correct. It's trying to build a

highly detailed schedule in week one

when you don't have any information

about how the job will be built. It

wastes tons of time on task that will

change and it creates a false sense of

precision that just is not based in

reality. So when you're first creating

your schedule, start high level and then

progressively add detail as you get

better information. Start high level.

Get the job duration and overall

methodology roughly correct and then add

detail when it becomes available.

Mistake number two is blindly copying

other projects. Every project is

different. Every project is unique. Yes,

templates can be recycled, but other

projects should only be relied on with

caution. I was working on a solar farm

and I remember looking at the schedule

and trying to understand why specific

activity was being rushed. so

aggressively and why it was coming up as

holding up the entire schedule. And it

was because we'd copied the template

from another project that had a specific

requirement in it for our development

approval. We needed to put up the

external fencing and landscaping, which

wasn't applicable on the project we're

working on. So, we could see that the

landscaping was holding up the entire

construction of the panel system. It

made no sense until we realized that the

planner had simply copied a template

from another project. So yes, you can

recycle templates, you can use other

projects, but you need to fundamentally

understand how the project's going to be

built and the project specifics and

constraints because if you're just

copying other projects, they might have

unique requirements that aren't

reflected in our project. The next

mistake which always confuses and over

complicates things is adding

discretionary linkages too early in the

planning process. This is when we're

creating our first cut of the schedule

during the planning phase and we add in

a ton of non-contractual or

preference-based linkages that don't

match the hard logic of how the project

has to be delivered. It extends the

duration artificially. It adds confusion

and it'll make optimizing the schedule

much more challenging. So when you're

first building your schedule, focus on

the hard physical dependencies, the

actual construction methodology, what

you have to do to build the job. Then

add in things like resourcing or other

issues you want to capture in the

schedule, preferences on how to build

it, how to optimize for cost. Add this

in as a later optimizing stage of

building the schedule. And the final

planning mistake is not properly linking

procurement and design. People focus way

too much on construction. They get into

the details, but to build anything, you

need drawings and you need materials and

subcontractors. So failing to properly

capture the durations of these tasks,

the dependencies of these tasks will

lead to a schedule that is a very

detailed construction phase, but

everything that happens before it being

completely wrong. Okay, so those are the

mistakes people make during the planning

phase. What about logic and data issues?

These are issues with how the schedule

is fundamentally structured and set up

to track progress during construction.

So the biggest logic mistake I see is

people ignoring the logic and the

methodology of the project. The schedule

has to reflect reality. It has to

reflect how the project is actually

going to be built. If for whatever

reason an activity can't start before

your client's not giving you access,

that has to be in the schedule. That is

the thing that's driving the start date

to that task. The schedule has to

reflect reality. So many times you look

at a schedule and it just doesn't

actually reflect the way the work is

being done. So you always have to be

asking yourself the question, is this

what's actually holding up the task? Is

this what the task is actually dependent

on? Again, it's all about being critical

of the schedule and ensuring that the

plan reflects reality. The next mistake

I see people make is similar to the

earlier one I had, which was about being

precisely wrong rather than roughly

correct, which is obsessing too much

over the numbers rather than what they

mean. People get way too fixated on

percentages, complete, dates, floats,

the critical part without really

understanding what they represent and

the sequence of the overall project and

how they all fit together. It's being

again too precise rather than roughly

correct. It gives you a false sense of

control. For example, a task might be

marked as 90% complete, but that final

10% complete of the task might be some

sort of defect that has a 6-month lead

time on the materials we need to fix it.

If you looked at the schedule and you

didn't understand how that 90% complete

was made up of and that we were actually

looking at a 6-month delay to rectifying

a defect, we need to have closed out

before practical completion, then you're

completely missing the point.

Fundamentally, you still need to have a

firm grasp of how the job's actually

being built, the methodology, how the

data is being captured, and what it

actually means. You have to understand

the methodology. The next mistakes I

want to talk about are communication

issues. These are mistakes that happen

when planners and the construction teams

are out of sync. The big one I see here

is a disconnection between planners and

construction. This happens when the

schedules are created in isolation

without input from the people managing

and delivering the project. The sequence

doesn't match the real world site

conditions and the team therefore don't

look at the schedule. They don't use it

as a planning tool and they don't see it

as their plan. So they don't have

ownership over the outcomes. Fix to this

is really simple. If you're the planner,

you need to involve the people doing the

work. They understand it better than you

and you want them to have ownership over

it. need to get them involved in the

planning process. You need to work out a

way to make it their schedule. The next

mistake I see is people focus on

schedule development and schedule

tracking, monitoring, and controlling,

but they ignore the fundamental step of

implementation. If you create a schedule

and don't implement it, as I've said

before, it's a waste of time. You need

to work out a way to take the plan that

exists in paper and turn it into a to-do

list. need to work out how to bridge the

gap between scheduling as a project

management tool and time management and

to-do list. You need to work out a way

that people can take the schedule, turn

it into a set of actions, and then

follow up on these actions. This is

where scheduling and time management and

organization are highly interrelated.

And the final category of mistakes I see

people making all the time is monitoring

and adaptation. You need to adjust the

plan when conditions change. A big

mistake I see people making here is they

treat the schedule as a Bible rather

than a guide. Again, they follow the

schedule blindly even when the

conditions on site change. Becomes a

tool that people use to blame when

things go wrong rather than seeing it as

a guide and understanding it might be

incorrect. There might be issues with

it, but you need to take ownership of

it. Understand what mistakes are in the

schedule. Understand the way the job

actually has to be built because

fundamentally you're there to meet the

finished dates not to follow the

schedule. And finally, people fail to

update and maintain and reforcast the

schedule. They treat the schedule. They

develop it as a set and forget strategy.

They build the schedule. They save it on

their desktop. They never look at it

again. and then they go and make all the

mistakes that they identified in the

schedule as issues that were going to

come up on the project. Again, you need

to constantly be referring to

maintaining and updating the schedule so

it remains a useful tool to plan and

coordinate the project.

Whether you like it or not, making money

in construction is more than just

building stuff. It's more than just

building stuff on time and budget. Yes,

obviously that plays a huge part, but to

make money in construction, you need to

build something and then get paid for

it. That's where contracts come in.

Unless you are a commercial person, most

people I know in the construction

industry hate contracts. Construction

contracts contain hundreds of pages with

multiple attachments. They all reference

different parts of the documents, and we

can all agree they're not written to be

userfriendly. But as I'm going to show

you in this course, contracts are

actually unbelievably simple. You just

need a framework to understand them, and

to learn how to use them to your

advantage. In this course, I'm going to

show you everything you need to know and

understand about construction contracts

and procurement so you can boost your

margins, boost your cash flow, and

reduce your risk. We're going to be

covering why contracts matter and how

they're used. What actually is a

contract, the structure and contents of

a contract, and then we'll jump into

contract management, and go through the

four domains of construction contract

management. We're going to talk about

both upstream contract management,

downstream contract management across

the formation and administration phases.

So that's the four domains of contract

management. We've got tendering, which

is upstream contract formation. We've

got procurement, which is downstream

contract formation. Then we've got both

head contract administration and

subcontract administration. Each of

these domains, we'll talk about the

tools and techniques you can use to

boost your margins, reduce your risk,

and increase your cash flow.

So, let's start with the big important

question. Why do contracts matter in

construction? So, I want to answer this

question by first setting the scene. So

imagine we're building a new road road

construction project and I first want to

understand what's involved in the

process. Well, we need to start with

feasibility and planning. We have to

decide whether the road is worthwhile to

build. We'll need a concept design.

We'll need some cost estimates. We then

go on to our design development and

design approvals. We need detailed

drawings and specifications that tell us

exactly what to build. They have to

comply with the feasibility approvals,

our budget constraints and also our

development approvals. We then need to

start with the bulk earthworks. We'll

need to move soil, move a huge amount of

cubic meters of dirt to make way for the

road formation. We can then install

underground utilities, electricity,

lighting. Maybe we'll have to relocate

some services like gas or

telecommunications.

We'll then need to actually construct

the road formation, the ashevelt paving,

put in any sort of landscaping and

roadside furnitureures. On top of that,

we'll need a team of people planning,

coordinating all these things, managing

the impact to the community, managing

all the separate traffic diversions. Now

when we map out all these steps from the

initial conception and feasibility to

the end opening of the road, all the

different construction activities, all

the different approvals, design

processes, all the different expert

expertise that are needed, we can very

quickly establish that no single company

or public government department could

complete all of these works in house.

It's just not feasible considering how

many different sorts of expertise and

skills needed to construct a road. There

needs to be a way for separate companies

to come together and all work towards

this same objective of building a road.

Now this comes the idea of an agreement.

For any two companies to collaborate and

work together the need they need to have

some sort of agreement. One party needs

to agree to do something. the other

party needs to agree to compensate for

them. For example, say the project owner

who's done the early stage design and

feasibility studies for the road decides

that they do in fact want to build this

road. First thing they're going to do is

they're going to go to a general

contractor, a head contractor, and

engage them to do this. They want a

single person they can pay to deliver

this project. So, the project owner will

say, "I'll pay you $30 million." And the

contractor is saying, "I'll build this

bridge for you." They're making an

agreement. One person's offering a

service, the other person's offering to

pay them for it. A contract, therefore,

is just a legal tool used to formalize

this agreement. So, fundamentally,

that's why contracts matter in

construction because we need all these

different parties to work together. We

need them to form agreements and the

contract is the legal tool that

formalizes this agreement. When we say

they formalize it, it means it's legally

binding, which fundamentally means the

courts will enforce it. The contract

defines who is responsible for what.

This means what and how they're going to

get paid, when will the work get done,

what risks are they responsible for, how

does changes to the scope to the project

get managed, what happens if arguments

or disputes arise, and any other

relevant terms and conditions. The

contract is the legal mechanism. the way

we formalized this agreement. Now, the

attitude of a lot of people in the

construction industry is that contracts

are paperwork and once you sign the

contract, it pretty much sits in a

folder and never gets referenced for the

entirety of the job. So, we've

established why contracts need to exist.

But then there's this other prevailing

belief that I see time and time again in

the construction industry is that people

think contracts just get signed, they

sit in a folder, then nothing ever

happens with them. So now I want to talk

about specifically for contractors why

effective contract management isn't just

a formal process that is used to capture

an agreement. It's actually a tool at

your disposal that you can use to boost

your profit margins, reduce your risk,

and improve your cash flow. So I want to

give you one really simple example from

my own career why I know contracts don't

just sit in folders. So I was working as

a contractor on a major electrical

construction project and the procurement

of the package from our client was

rushed. They really pushed us to sign

the contract to get onto the site to

start working because they had deadlines

that they had to meet. We agreed to a

whole lot of things with our client

verbally or in meetings and we had the

shared understanding of how the scope

was going to work. things like we'd

priced over a bill of quantities and

then the client agreed that the bill of

quantities was a source of truth over

the drawings and if there was a change

in the quantities there'd be a change

the contract price. None of this stuff

was it was documented to to an extent in

the scope but it wasn't clearly spelled

out in the scope. What happened about a

month into the project? The client

changed their project manager. And so

all these issues we were having with the

quantities being wrong, not matching the

drawings, we thought we were entitled

for additional money for because it

wasn't written in the contract. The new

project manager disputed everything. So

it's an example where we thought we were

relying on a relationship, but we soon

realized that if it wasn't documented in

the contract, pretty much everything was

at our own risk. So using the principle

of inversion, let's ask ourselves a

question. What happens if you don't

manage your contract? Well, you do work,

you don't need to, and you don't get

paid for it. So you're incurring costs

and not getting a corresponding increase

in revenue. A delay happens, but you

don't notify your client in time and you

wear the cost of this delay and

potentially incur liquidated damages at

the tail end of the contract because

you're late in finishing. your

subcontractor underperforms and you

can't have any way to recover the cost

of their poor performance. Your client

stops paying you paying you and you have

no idea what to do. So these are all

situations that can happen if you don't

manage the contract effectively. So

there's two sides of construction

management. There's the side that most

construction people intuitively focus on

and are in the part they like, the part

they're good at, which is doing a good

job delivering the work on time and on

budget to the standards in the

specifications. Building the correct

thing and building it under budget and

ahead of schedule. We all know we need

to do this. Then there comes the

contract side of things, which is doing

the work, but also getting paid for it.

We need to manage the works, but we also

need to manage the contract to have a

successful project outcome. So, I have

some stats to back up the claim on

making the contracts matter. There's a

couple of big studies that have showed

that improving contract management

drastically improves your project

performance. McKenzie in 2017 found that

poor contract management is responsible

for a loss of 5 to 15% in project value.

Considering the average margins people

operate on are like 10 to 15%. That's a

huge amount of money. The World Commerce

and Contracting Association found that

ineffective contract management leads to

an average 11 revenue leakage of 9.2%

per project. Again, very similar

statistic, very similar result. You can

basically wipe out your profit margin by

not managing a contract properly. And a

KPMG construction survey found that only

31% of contractors say they consistently

deliver projects on budget. Contract

controls are a key reason why. One of

the key reasons I listed was not having

effective contract management. Okay. So

when I talk about why contract

management matters, I always break it

down into these three buckets. We've got

profit, which is getting a higher

revenue than your cost base. We've got

risk that is preventing the preventing

bad things from happening. And then

we've got cash flow getting paid before

you incur cost. Contract management

helps you to do all of these things. So

increasing your profit. Contract

management helps you make claims and

then get paid for variations and scrup

change. So if you do more work, you get

paid for more work. It avoids doing

unapproved or unnecessary work. So not

incurring costs that you shouldn't have.

helps you to justify any extension of

times and recover any delay related

cost. So if you're delayed in doing the

work, you'll get a corresponding

increase in your contract ma contract

value if you manage the contract

effectively and it h helps you to

capture any back charges, day works and

entitlements to your subcontractors. So

if your subcontractors have

underperformed it helps you avoid paying

them additional money or incurring

additional costs. Contract management

also helps you to lower risk. So to

lower the uncertainty that matters to

the project does this by clarifying who

is responsible for what and when. It

helps to protect against liability creep

and unfair instructions from your

client. Helps you to avoid liquidated

damages. So risks associated with

finishing a project late. Helps you to

effectively transfer risks you're

responsible to in head contract to your

subcontractors. And it helps you to

comply with legislation. Result is fewer

surprises, stronger protection and more

control of your obligations. And

finally, it helps you to improve your

cash position. As contractors know, cash

isn't always an issue on construction

projects. So contract management

actually helps you to improve your cash

flow. helps you to negotiate favorable

contract terms, favorable payment terms

in contract formation. Helps you to

ensure that you make your payment claims

on time and you get paid for the work

you've done. Helps you to use notice

procedures to trigger payment claim

variations and delays. And it helps you

to track and follow up on unpaid

invoices using only contract mechanisms.

The result is to get money in your bank

before you incur costs. So, I know we've

already briefly touched on what a

contract is, but in this section, I want

to dive a little deeper into

specifically what is a contract. We know

it's a legally enforcable agreement, but

let's break that down. Let's look at the

specific characteristics that have to be

in place for a contract to exist. So a

contract in terms of legal speak terms

of what the courts refer to it as it's a

legally binding agreement between two

parties and it creates enforcable rights

and obligations. So the terms and

conditions in a contract what we're

signing up to do and what we're signing

up to receive become enforcable by the

courts. Contracts are governed by common

law principles. This means judgments by

the courts around how contracts will be

enforced and interpreted are governed by

historic cases. And then based on this,

the courts can either award damages or

enforce penalties if you go to court.

Okay. So the legal foundations of what a

contract are means to be legally

enforcable. A contract has to meet

certain criteria. There needs to be an

offer. There needs to be acceptance.

There needs to be consideration. So

something of value moving between

parties. There needs to be an intention

to create legal relations. There needs

to be a capacity to contract. And there

needs to be certainty of the terms. So

I'll break down what all these mean so

you understand exactly what's involved

for a contract to be in place between

two parties. Okay. So the first

foundation of a contract is the offer.

One party must make a clear proposal to

enter into a contract. So for in

construction, this would typically

happen during a tender submission where

a client provides a scope of works and a

contractor provides a quote and

methodology to deliver this work. Offer

must be definite and intended to be

accepted accepted. For example,

contractor say we will construct the

payment works for $1.2 million as per

the attached scope of works drawing. So

that's an offer that is the first basis

of a contract. The next part is

acceptance. So the offer creates is the

first step. Then that offer must be

accepted by the client. So the other

party agrees to the terms of the offer

without change. So the client comes back

and says no, we want your price to

increase reduce by $300,000. Then

obviously that is a counter offer and

needs to be accepted by the other party.

They just can't automatically

unilaterally deduct the price. must be

clear, unconditional, and communicated.

And if the response includes changes, it

becomes a counter offer, not acceptance

of the offer. For example, if the with

the payment example, the client then

says, "We accept your tender for the

payment works in full." Now, for a

contract to exist, there must be

consideration, which means something of

value must move between the two parties.

So, in construction, this is work in

exchange for payment. Without

consideration, the contract is not

enforcable except in deeds, but they're

separate. So, the contractor is offered

to build the pavement for $1.2 million.

The client is then agreeing to pay them

$1.2 million. So, there's mutual

consideration in that example. There's

services from the contractor to the

client, and there's the payment from the

client to the contractor. Now, for a

contract to exist, there also needs to

be intention to create legal relations.

Both parties must clearly intend to

enter into a legal legal binding

agreement in commercial and business

negotiations. This is presumed by

default. For example, if someone sent

you a scope of works with a draft form

of contract drawing specifications and

you're saying you're willing to do it

for $1.2 million, there's clear

intention to create a legal arrangement.

If you offer to mow your brother's lawn

and for $20, then there's no intention

to create a contract. Just dealing

between friends. So intention to create

legal relations is another fundamental

thing that has to exist for a contract

to exist. There must also be capacity to

contract. So both parties must have the

legal capacity to enter into a contract.

This means they're of legal age and

sound mind and have the authority to

sign, which will be the biggest one you

see in construction companies. For

example, a junior graduate engineer on a

project isn't going to be able to sign

off on a $20 million project and they

would clearly not have the capacity to

contract that. So even if they did sign

it, it probably wouldn't count for

anything because clearly that person

would not have the authority. So it

would not be enforceable. There must

also be certainty of terms. So the

contract must be clear enough for a

court to interpret and enforce. Vague or

ambiguous clauses can make a contract

uninforceable or open to dispute. Good

contracts will clearly define scope,

time, payments, and obligations. And if

things are not defined clearly, the

courts may not enforce them. Next, I

want to move on to talking about some

core concepts of construction contract

management. So, I want to start by

talking about the two key roles in any

construction contract. We've got the

buyer and we've got the seller. The

buyer is also referred to as the

principal. They're the one acquiring the

goods and services. They're paying for

something to be done. So, for example,

of a road construction project, the

buyer is the state government, the

project developer. They are the ones

that want a road to be built, and

they're the ones who are going to be

paying for it. Seller is also referred

to as the contractor. They're the ones

providing the goods and services, and

they're the ones receiving the payment.

So in the example, the road project,

they're the general contractor who's

going to get paid $30 million to build

the bridge. So they're going to be the

ones organizing all the labor, plant,

materials, subcontractors to do that,

and they'll complete the works and

receive payment from the buyer. So

breaking down these roles and some of

the other roles that we typically see in

construction contracts. So the principal

is the client and the owner. They're the

party who commissions the work, pays for

it, they set the project objectives,

they provide access to the works, and

they review any claims to the

contractor. The contractor referred to

as the head contractor or general

contractor specifically is the one

managing the overall project, and they

deliver the work as per the contractor.

They manage the program, typically the

cost, subcontractors, and their

obligations.

Some instances you have a superintendent

or a contract administrator. So this is

an agent employed by the principal to

manage the contract, but they're meant

to be impartial and assess any claims

from the contractor. You then also have

subcontractors. So these are specialist

contractors engaged by the contractor to

complete specific portions of the

project scope. For example, on the road

project, the general contractor may

engage an electrical subcontractor to

complete the street lighting. Then the

last party that we have on construction

projects is the architect or engineer.

They're the professional services

provider who prepared the drawings and

specifications and the detailed design.

Depending on the contract model, they

may be working for the contractor or

they may be working for the principal.

So this leads into the contract model

which is the structure that governs the

relationship between all of these

different parties. You might have a

design and construct contract, a

construct only contract and ECI or early

contractor involvement APC. There's tons

of different models that are suited to

different projects. And in the early

stage feasibility stage, the principal

needs to decide on the best structure

for all these parties to work together

depending on the specifics of the

project. We're going to go through all

of these models, but to start with,

here's an example of a design and

construct contract so you can understand

what I'm referring to when I'm talking

about the contract model. You have a

project owner, the one who's deciding

what to build and financing it. They're

paying a general contractor to deliver

the project or a head contractor to

deliver the project. Head contractor is

providing them the service, a building,

whatever they're doing. Under a design

and construct model, the head contractor

engages the designer for the detailed

design and engineering and also engages

all of the subcontractors. So the

project owner has no commercial

relationship with subcontractors or the

designer. They engage directly the head

contractor. The head contractor then

engages the architect, the engineer and

the subcontractors. In the same way that

the project owner is the buyer and the

contractor is the seller, in the head

contract arrangement, in the subcontract

arrangements

the head contractor becomes the buyer,

the subcontractor and the designer

become the seller. So they're the ones

providing the services and the head

contractor will pay them for it. When we

talk about construction contracts and

the relationships between all these

different parties, an important concept

to understand is the flowown effect. So

the flow down effect is basically how

requirements move from the principal to

the head contractor to subcontractors.

The principal originally specifies what

they want. They want a bridge that meets

these certain requirements. They want it

built within 6 months. They have 20-day

payment terms, all these different

things. They pass these requirements on

to the head contractor. Head contractor

will typically pass these on to

subcontractors. For example, the design

drawings might say an 150 mil thick

concrete slab in accordance with blah

blah blah blah blah. There's a 24-month

defect liability period. What good

contractors do is they take the

requirements from the head contractor

and they pass these on to their

subcontractors. They transfer

responsibility and risk through this

process. Now, there's two core stages of

contract management. There's the

formation stage, the process through

which a contract is created between two

parties. And there's the administration

stage. The administration stage is the

process of monitoring and facilitating

the smooth performance of the works. We

form a contract. We agree to terms and

conditions. Then we deliver the works in

accordance with these terms and

conditions. Now, we can break this

process down into four steps. We've got

upstream and downstream contract

management. So if we're the head

contractor, our upstream contractor is

with principal. Our downstream contract

is with our subcontractors. And then

there's two stages to this process.

There's contract formation where we

negotiate and sign a contract. There's

contract administration. So forming the

contract with our client. Upstream

contract formation we refer to as

tendering or quoting. Tendering, quoting

or bidding, whatever the specific term

you use. Then there's procurement which

is downstream contract formation which

is finding subcontractors and suppliers

to deliver the works on our behalf. Then

once we sign a contract we move into

contract administration. We've got

upstream contract formation which is

head contract administration managing

the contract with our client. And we

also have subcontractor administration

managing the contract with our

subcontractors. Again so upstream

contract formation or tendering is where

we negotiate and sign a contract with

our client. This means we need to review

the project requirements, submit a quote

and conditions of offer that align with

the project, negotiate and sign a

contract. The goal here is to win a

project at a price and terms that we can

then ensure we deliver profitably.

We always want to be focusing on the

terms and conditions of the contract,

not just the price we sign up to. Then

we've got downstream contract formation

or procurement where we need to identify

the packages we need to procure from the

market, prepare and issue RFQ documents,

review and negotiate contracts with our

suppliers. The goal here is to find the

best possible suppliers and

subcontractors at the best possible

price. We want to align scope, schedule,

and risk responsibilities and transfer

these obligations to our subcontractors

so we're not caught between the

requirements in the head contracts and

the requirements in the subcontracts.

Then we've got our upstream and

downstream contract administration. So

upstream, the focus is getting paid for

the work we do and fulfilling our

contract obligation. So complying with

all the rules the contract specifies to

follow. Downstream contract

administration is about providing access

on time to our subcontractors so they

can complete the works. If we're free

issuing materials, getting them the

materials on time, managing them

closely. At the end of the day, we're

accountable for the work we do. The

worst thing we can do is let and forget

and maintaining an alignment with the

head contract. We want to get paid for

the work we've done. We want to ensure

safety, quality, and performance

subcontractors and we want to manage

risk. So now we understand the core

concepts around contract management. We

understand all the different parties,

the relationship between these parties

defined in the contract model and also

the different stages of the four stages

of contract management. Let's now talk

about the structure and contents of a

construction contract.

>> So head to the section by giving you a

framework of how to think about

contracts because the vast majority of

people drastically over complicate them.

You need to think about a contract as a

rule book. They tell you what to do and

when. They tell you what work you need

to do, exactly what work you need to do,

how to get paid for the work you've

completed, what to do when things

change, what you have to do to finish

and sign off the contract, and so on and

so forth. They're basically just rule

books for the game you're playing. You

can think of them as like the rules of a

game of chess. If you think about

contracts like that, they're going to

become way simpler. So, let me give you

some examples of how you can think of

contracts as rule books. Say, for

example, you're the contractor managing

a project and the materials you plan to

order are going to arrive late. Does

that matter? Is that important? Well, if

you look at what the contract says, the

contract says, so these are clauses from

a real contract progress. The contractor

shall ensure that WU the work under the

contract reaches practical completion by

the date for practical completion. So

what that tells you is you need to

finish the work by the date for the

contract. If the contractor does not

achieve practical completion by this

date, they will be they will have to pay

liquidated damages. So you will get a

fine for not completing the project on

time. What does that mean? If your

materials are going to come late and

they're going to delay completion of

project, it means you're going to get

penalized for doing it. So you have to

come up with some sort of solution to

this problem. It is a problem that does

in fact matter. Let me give you another

example. Say you're managing a

subcontractor and they have a whole lot

of defects and issues with the work

they've completed and you keep telling

them you have to come back to site and

fix your defects. You have to come to

back to site fix your defects but

they're ignoring you and they're not

doing it. What can you do about this?

will refer to the contract the section

where it says defected work and it says

if the contractor has fa has failed to

come back to site and fix their defects

and you've provided them written notice

given the set period of time you've got

to allow them to come back and fix their

defects if they haven't come back and

fix their defects referring to this

clause in the contract you are allowed

to take out money from their security or

money you owe them to go and rectify the

defective work so the contract is given

giving you a specific process to follow

in this exact situation. That's what I

mean when I talk about contracts as rule

books. You think about contract

management as a game. The contract is

the rules for how to play. Your

subcontractor is failing to fix their

defects. There's a process in the

contract you can follow to rectify this.

Okay. So now we understand this

framework of how to think about

contracts. There just a set of rules.

Let's talk about the structure of a

contract. So contracts typically broken

down into three sections. We've got the

general conditions of contracts. So

these are standard terms used across

many projects. In Australia we have the

AS4000 series. But in Europe, the UK,

America, there's the FID and NEC

contracts. They cover general rights and

responsibilities such as payment time

variations. The extracts I had in the

last two slides, they were from general

conditions of contracts. We've then got

special conditions. For example, project

specific specific amendments to the

general conditions. So these general

conditions might be adjusted and these

override or modify the standard rules

and often contain bigger risks. Then

we've got this attachments and

supporting documentations. For example,

to the general condition of contract,

you might attach a scope of works,

technical specifications, drawings, a

bill of quantities and so on. Now I'm

going to touch on some core concepts

around the contract and the specific

terms and conditions you need to

understand. First one which is always

the most important one is the scope of

works which defines the work you need to

do. Scope is what you're contracted to

complete. It typically contains

deliverables. So, what you're required

to build, boundaries, where the work

stops, where your interfaces are, any

exclusions, what's specifically not

included in your scope of works, and any

interfaces or dependencies you'll have

on other contractors or the clients.

Scope is always an issue on construction

projects, and it's always the biggest

source of disputes. Why is this? Well,

because construction projects often

technically complicated and difficult to

understand. There's a lot of different

tasks involved. There's a lot of

different steps and the scope is open to

misinterpretation. There's always

misalignments and misinterpretations.

Fundamentally, what drives the cost of

the project. The cost is the work you

need to complete. There's always going

to be disputes around scope because if

you do less work, you save money. The

principal has contracted work and

they've got you to do it. They don't

have to pay extra for the for another

contractor to complete the work. So

scope is probably where the biggest

disputes around cost are going to be and

there's always documents that conflict

each other. The drawings might say one

thing, the specifications might say

another and the bill of quantities might

suggest something else. So you need to

understand the order of precedence, what

order these documents need to be read

and understood in. So what are the tools

we use in contract management to manage

scope? There might be things like scope

checklist. We use a work breakdown

structure. We might have scope briefings

with subcontractors.

Fundamentally though, what we want to do

is if we're the head contractor, we want

to take the requirements in head

contractor and make our subcontractors

responsible for these same portions of

the work. So, it's always back to back

with our subcontractors.

This is fundamentally going to help us

avoid scope creep and undocumented

changes. So, basically where we do

additional work and don't get paid for

it. The next fundamental concept is time

when we need to have completed the work

by. So these are things like the key key

dates like the date we meant to start

the work any specific milestones we need

to meet when we need to complete the

work the defect liability period whether

there's any sectional completions but

also we might have specific

responsibilities to maintain a program

we might have to issue an updated

program every 2 weeks or every month. In

addition to this contracts typically

have liquidated damages. So, liquidated

damages are a penalty that's enforced if

we're late in completing the works. They

might be $1,000 a day, there might be

$10,000 a day, they might be a million

dollars a day depending on the size of

the project. But basically, as there's

the scope defines what we need to do,

time defines when we need to do it, and

because time matters so much in

construction, we'll get penalized if

we're late. The construction program is

how we communicate the progress of the

project to our client and to our

subcontractors. It will show the

critical path series of activities that

if delayed delay project completion

float and any access states to the site.

So we need access to site on this date

to complete our work. This is the

critical path. This is the series of

tasks that if delayed will delay our

finish date and any activities that

aren't on the critical path will be will

have some float associated with them.

The contract program is the basis of any

claims we can make. If our if our client

is late in giving us access to the site,

we can claim for delays. If a client

disrupts a non-critical path activity

but changes the way we're working but

doesn't impact our finish date, we can

prove and justify claiming costs for

disruption. core concept around time and

a topic most people love but it's a term

people throw around without fully

understanding what it means are

extension of time claims. Extension of

time claims is when we adjust the finish

state in the contract. To do this we

need to maintain a construction program.

So we need to have a program that shows

a sequence of tasks the order they need

to be completed in and what date we need

access from our client. To claim an

extension of time, we need to just

demonstrate that a critical path

activity has been delayed. For example,

if we're doing a constructs

project and the date in our program that

we need the IFC or the issue for

construction design is the 15th of

February. If that date elapses and we

don't have the IFC design, we can claim

a critical path activity has been

delayed. So, we need to adjust the

finish date in the contract. When we're

claiming, we can claim just time, which

is adjusting the completion date of the

contract, or we can also claim cost. For

example, because the finish date in the

contract is pushed out, we're going to

need our project manager and sidesheds

on site for another month, which is

going to cost an extra $20,000 or

whatever it is. So, that's why you can

see that time is such an important

concept of any project because it has

such an impact on both risk through

liquidated damages, but also cost. The

next core concept in contracts is

payment. How and when do we receive

payment for the works completed or how

and when do we have to pay our

subcontractors the works they've

completed. Payment when it's defined in

the contract will include the payment

mechanism whether it's lumpsum schedule

of rates or cost reimbursible. The

pricing schedule so how our clients or

how our subcontractors will bill us. the

claim cycle whether it's monthly or we

get paid based on milestones any

security we have to give so whether we

have to give whether client will hold

retention or they'll hold a bank

guarantee again when I spoke about why

contract management matters so much it's

because cash is key in construction

construction operates on thin margins

and if you get delayed in getting paid

you can very quickly be cash negative on

a project managing a contract is how we

manage our cash cycle okay so what are

different payment mechanisms in the

contract. We've got fixed cost. This is

where there's a fixed fee paid to the

contractor for the delivery of a fixed

scope of works. We've got schedule of

rates. So, this is where there's a fixed

amount paid per unit of work complete.

For example, contractor might get paid

$128 per linear meter of subsurface

drap. If they do a,000 mters, they'll

get paid 128,000. They do 2,000, they'll

get paid whatever double that is. I

can't do the maths that fast in my head.

Cost reimbursible is where there's

payment to the contractor for the actual

works completed plus an agreed upon

margin. So in this situation, the

contract has to has to provide evidence

of the actual costs incurred or finally

less common on subcontracts but common

on bigger projects now is a target cost

contract where the project costs are

agreed between the client and the

contractor and then they share any

overruns between the parties. Now as a

contractor you need to be able to

effectively make payment claims. That's

the process through which the principal

pays the contractor. So, how does this

process happen? Well, each month or on a

regular cycle throughout the project,

the contractor will submit a payment

claim to the client. They'll provide

evidence of the work they've completed

and what items in the payment schedule

they're claiming against. What happens

then is that the principal will then

review this payment claim. Maybe the

contractor is claiming to say they've

done 1,000 m of drainage, but the

principal thinks they've only done 950

m. They will negotiate this and agree on

the value of the of the of the claim,

then issue an invoice or a payment

certificate. Once project completion,

once the contractor has completed the

work, they'll submit a final payment

claim, which will start the defects

liability period. And at the completion

of the defects liability period, the

principal will return the contractor's

security and they'll finish the

contract. Okay. So, how are payment

claims typically structured? Well, you

typically structure your payment claim

in an Excel workbook and each month the

contractor makes a payment claim to the

principal. For example, for street

lighting civil works, we've got here

there's a rate in the contract for each

of the different types of trenches which

probably correspond to different widths

and depths. a rate for light pole

foundations, a rate for pit

installations, a rate for distribution

board foundations. There's a quantity

and a rate against each of these. And

each month, the contractor submits a

claim to the principal that says, "I've

done 193 m of trench type A at unit rate

$1,200 per meter or sorry, $400 per

meter. This equates to a claim of

$200,000 or whatever it is." The

principal then assesses this. They then

say, "Nope, you've only done 200 m. We

value this claim at X and negotiate

this." They agree on a claim value and

that becomes the claim. The contractor

submits the principle. Okay. Partly tied

into payment and I mentioned it briefly

when I spoke about retention and bait

guarantees. But we also need to

understand security. Security is

fundamental to any construction contract

and it's basically financial guarantees

that one party gives the other.

Typically the contractor gives it to the

principal and it can come in the form of

retention where the client holds a

portion of every payment claim bank

guarantee where the contractor gives a

sheet of paper to the principal saying

there's a million dollars in this bank

account and if I fail to complete the

works you can take this to the bank and

take the money or the third form of

security which isn't written into the

contract but works the same is value of

the work completed by the contractor

that they have not been paid for. So the

contract specifies the form of security

the the principal will hold, the amount

of security, the timing when it will be

returned, a practical completion and at

the end of the defect liability period

and the process the principal can use to

draw down the security. So if they going

to take money off the contractor from

their security, what is the process they

need to follow? So the principal can

access this security and this is what

most contracts say. Whenever the

contractor is in default and failing to

complete the work under the contract.

This means any additional costs incurred

by the principal can be recovered from

the security. For example, the

contractor is failing to rectify their

defects. The principal's given them

notice asked them to come back and fix

their defects and they're refusing. The

principal can then access this security.

They can take this money and use it to

pay another contractor to come back and

fix their defect. If the contractor has

left the site dangerous, maybe they left

a huge open excavation in the road,

they're not coming back to fix it, the

principal can access the security to get

them to fix it. Or basically whenever

there's a reason, the principal can take

work off the contractor and engage

another contractor to rectify any

shortfall. Insurance and risk are

another core concept in any construction

contract and it's this idea of who

covers what when things go wrong. So

insurance as you know the same as you

get home or car insurance. Construction

contracts also nominate requirements for

contractors to hold insurance. So

insurance provides compensation for a

specified loss and is a riskmanagement

tool. It's mandated in construction

contracts to protect the principal or

third party if a risk plays out and the

contractor is unable to cover the cost.

The types needed depend on the work

being completed by the contractor. The

contract nominates the type of

insuranceances the contractor needs to

hold and the level of cover whether it's

$20 million or whatever. Okay. So the

main types of insuranceances you see in

construction contracts a contractor's

all risk insurance which covers loss or

damage to the works for the project

duration and is taken out by the head

contractor. Got public liability

insurance which covers damage to people

and property outside of the work and is

required for all parties involved in a

construction contract. We've got workers

compensation insurance which covers the

costs associated with injuries and

rehabilitation to construction workers.

is generally mandated by law. And then

we've got professional indemnity

insurance, which is when you're

providing any sort of professional

service or technical expertise, which

covers any breach in duty. So if you're

a civil engineer designing a foundation,

you design a foundation the wrong depth,

you're covered by professional indemnity

insurance. Now, depending on the project

specifics, other types of insuranceances

may be required. For example, if you're

buying expensive plant overseas and

you're shipping it, the contract may say

that you need maritime transit

insurance. Now the next topic, the one

everyone loves variations. How do we

manage change of the contract sum? When

we were talking about payment mechanism

and we spoke about fixed fee contracts,

we said contractor is paid fixed fee for

completing a scope of works in

accordance with the contract. Variations

are how we manage changed scope, time,

quality, project requirements and how

the corresponding fixed fee is adjusted.

So basically the principal changes the

requirements then the fixed fee needs to

be adjusted to reflect this and that is

managed through variations. There's two

core types of variations. There's

variations instructed or requested by

the principles and there's variations

claimed by the contractor. So a

variation proposed is when the principal

acknowledges before the fact that

there's been a change. For example,

they're building a building and the

principal says, "Oh no, I actually want

this new architectural feature outside

the building was never in the scope to

begin with." The process for a variation

proposed is that the principal proposes

the additional scope to the contractor.

The key here again is that it's agreed

before the proposal. Everyone agrees

there's a change to the project scope.

The contractor will then review this

requirement and then advises the

feasibility of it and the cost or

schedule impacts to the project. For

example, they say to add this new

architectural fe feature, it's going to

take us a month longer to finish the

project and it's going to cost $100,000.

The principal will then review and

assess this and they'll negotiate it to

determine whether they agree to this

cost impact or whether they actually

want to proceed with the change. They

then decide whether to proceed with it

as either an approved variation or they

decline it. They decline it. There's no

change to project code. They approve it.

Then there's adjustment by the time and

cost agreed to in the variation. Now on

the other hand, we've got variations

claimed. So these are everyone's least

favorite topic. It's where all the

arguments occur on projects and it's

where the contractor believes something

has changed and they present this to the

principal and say hey you've delayed us

by accessing site by one month because

of this we need an extra month to finish

the project and you need to pay for our

indirect cost for another month which is

going to be $100,000. They become aware

of the grounds for a claim. So the key

here which is different to a variation

proposed is with a variation proposed

everybody agrees there's been a change

the scope with a variation claimed there

is no implied agreement that there's

been a change. So which means the

principal will argue one that the change

exists in the first place and then two

the cost impact of the change. So in

this situation the contractor becomes

aware of the grounds for a claim. Hey,

you've delayed us accessing the site.

They'll present this justification.

They'll sub submit a notice of the claim

and details of the claim. Now, contracts

have in them time bars. A time bar just

means that once you become aware of a

change, you might only have 48 hours

within which you have to notify your

client. If you're late in notifying them

of the change, you may get bu you may

not actually be entitled to claim for

the change. So you have to submit any

notices within a time bar. The claim is

then assessed by the principal

superintendent. You might have extra

time to prepare your cost estimate. How

they assess the claim will be the cause.

So who has actually caused it? Obviously

if the contractor is late in ordering

materials, they can't build the

principal for that. There's no grounds

for a claim. But if the principal or

they're both at fault, then there will

be grounds for a claim. They will assess

the impact of the claim. So they will

have agreed the claim exists. Then they

assess the cost and time impact. They

negotiate it. They review the impact of

the schedule. Has a critical path

activity been delayed? And then they

determine what compensation or change

the contract there is. Now once we talk

about variations in claims, it only

makes sense to then talk about disputes

because all disputes start with

arguments over variations in scope. In

the contract are specific mechanisms for

how to resolve disputes. What happens

when things go wrong? What happens when

the principal and the contractor aren't

getting along? Typically, what causes

disputes are payment issues, delays to

payment, arguing over payment claims,

variation, disagreements, and EOT

disagreements. The contract will have

specific resolution mechanisms within

it. So the contract might specify that

first you have to have a site meeting

then it has to get escal escalated to

senior representatives from the company

then you have to go to mediation and

then if none of that can be resolved you

go to arbitration in courts in Australia

because payment is such a big issue and

in most countries where contractors use

it as a bullying tactic for

subcontractors is very strict laws

around payment in the security of

payment act to manage disputes

effectively you need really good

records, site diaries, records,

drawings, exactly what's happened and

why it's happened. And at all costs, you

should avoid escalation. It's always

better to manage things as a project

team at the site level rather than going

to senior management. And finally, last

but not least, we've got termination.

How the contract can be ended. The

contract within it will specify when and

how the contract can be terminated. So

for cause when there's a serious breach

by one party for another for example if

the principal has stopped paying the

contractor or the contractor has walked

off site and is not doing the work. You

can some contracts will have it so the

principal can terminate the contract for

convenience or there can be mutual

termination. Both parties agree not to

do the work. The procedure around

termination will pretty much be there'll

be some sort of notice period. The

contractor will have to make the site

safe and demobilization and there'll

need to be financial settlements. So the

contractor will need to get paid for the

work they've completed. And there's also

risk protection. So termination clauses

when the principal can terminate the

contract or if the subcontractor or

contractor goes insolvent, how to manage

the insolveny process. Next, let's talk

about the different types of

construction contracts. In the previous

section, we spoke about all the

different parties involved in delivering

a project. The project model or the

contract type specifies how all these

different parties are going to work

together and the project owner needs to

choose the optimal contract model to

best suit the type of project and their

objectives.

>> So, talking about the contract model,

we're really talking about answering a

couple of quick key questions. Things

like who does what? Who's responsible

for the design? Who's responsible for

the construction? How is payment

structured? Is it going to be cost

reimbursible or is it going to be a lump

sum? Who bears the different risks for

the project delivery? The cost risk, the

time risk, risk for design errors and

then also how is the project model going

to be used. So all these questions need

to be answered to come up with the

optimal contract model. So the first

most common construction model we see is

the constru model. So the constructor

model is where the client completes the

design themselves. So the project owner

directly engages the engineer or

architect to complete the detailed

design. All the contractor is doing is

getting given this IFC set of drawings

and building to the drawings. It is also

referred to as traditional procurement.

The contractor quotes off the design to

build the design. The contractor builds

the design and any issues with the

design become a variation to the

contract. If there's an error or an

omission in the design, the contractor

will get paid for the rework associated

with that. Payment is fixed and lump

sum. The contractor bears all the risk

for the construction cost but does not

bear any of the design risk. So these

are used in traditional projects and you

need to have a client or a project owner

who knows what they're doing. They need

to be able to manage the design

themselves, pick up constructibility

issues, pick up value engineering

opportunities. So it's typically done on

more traditional building projects.

Design and construct is where the

contractor is engaged for both the

detailed design and the construction of

the project. So the client prepares an

initial concept design and

specification. The contractor quotes to

complete the detailed design and

construction. So they based off this

concept design and the specifications.

They'll need to take the design to IFC

and then build in accordance with this

design. The client selects their

preferred contractor which is going to

be a combination of their price to

deliver the works but also the technical

solution they're proposing. So when the

contractor is tendering for the works

typically they'll complete a 15% or

tender design revision which the client

will review and they'll make the

decision based off both the design and

the construction solution. The

contractor then manages the architect

and the engineer to take the design to

IFC and then they construct this IFC

design. Again payment is fixed lump sum.

The contractor is bearing all the risk.

The contractor in this contract model is

also bearing the design risk. So any

issues with the detailed design IFC

drawings, any emissions, any lost

opportunities, the contractor is bearing

that risk. The only exception to this

would be when the the principal is

requesting a change to the initial

specifications or concept design. This

model is best used when you want a

single point of accountability in the

contractor. However, the project owner

does not have the expertise to manage

the design themselves. So they want the

contractor to identify the value

engineering opportunities and factor

this into their pricing. Now so

construct only design and construct

they're both lumpsum contracts. The

contractor is paid a fixed fee for

delivering the work. A cost plus

contract is a cost reimburseable

contractor where the contractor is paid

for the actual cost of doing the work

plus a fee. So the client chooses a

contractor based on their experience or

capability. The design is done by the

client. It's given to the contractor and

they deliver the project as per the

client's directions. The contractor is

paid the actual cost of the works plus a

fixed fee or percentage markup. might be

7%, might be 15% depending on the

contract type. In this situation, the

client is bearing all the financial risk

and because of this the contractor has

less of an incentive to be efficient and

cost effective. These types of cost plus

contracts are used when for time

critical work or what scope is hard to

define or messy. So, for example, if

you're doing a brownfield upgrade to

rail infrastructure where it's not clear

what's already installed, what has to be

replaced, this would be an example of a

cost plus contract. A target cost

contract is similar to a cost plus.

However, the contractor and the client

agree to a budget for the project and

they share underruns and overruns. So in

this situation, the contractor isn't

bearing all of the cost risk like a a

construct only or a design and construct

contract, but they're agreeing to a

maximum cost and then they're going to

share any overruns or underrun. So the

contractor is incentive incentivized to

be more efficient with their spending.

Then the contractor delivers the

project. The payment for the contractor

will be the actual cost of doing the

work plus their markup plus their pain

or gain share. This is used on complex

high-risk projects where you can't find

it. Typically, a project owner would

want to get engage a contractor under a

construct only contract, but a lot of

contractors might not accept that. There

might be huge risks or there might be

situations where the clo the contractor

will almost certainly be able to claim

for variations or additional scope.

Using a target cost contract, you don't

have that same adversarial relationship

when change happens with construct only

and designing construct contracts. Now

the final contract model we'll talk

about is a construction management

agreement. This is where the client

hires the constru the contractor to

manage the project on their behalf. So

the contractor is engaged almost as a

professional service provider in the

same way as a design engineer or an

architect's engaged. So the client would

select the contractor based on their

experience and their capability to

manage the project. The contractor would

manage the trades, the engineers, the

architects, the third parties, they

basically managed the project on behalf

of the client as opposed to doing it

under a fixed fee. So the co in terms of

how payments worked, the the contractor

would quote to deliver the construction

management services. So they paid a

fixed fee for the services they provide,

but the sub subcontractors are all

engaged directly by the project owner.

The project owner is paying the actual

cost of delivering the project. In this

situation, the client is bearing all of

the financial risk, all of the errors

with any issues with the design, any

issues with construction works on site.

The client is bearing all of those. The

contractor is purely acting as a

coordinator. These construction

management projects are typically used

for fasttracked or complex projects, but

they're also used for mega projects. Say

there's some $40 billion oil and gas

facility upgrade where the project is

just too big of a financial risk for a

contractor to take on as a design and

constructor as an APC. It's very typical

that the project owner still needs the

expertise of a competent contractor. So

they'll engage them under a construction

management agreement and they'll help to

manage large subcontractors. So that was

a really brief simple overview of some

of the typical contract models we see.

Now we're going to talk move on to

talking about contract management. So so

far we've spoken about the different

types of contracts, what contracts are,

the different parties involved in a

contract. Now it's time to talk about

how to actually manage contracts to

boost your profit, reduce your risk, and

optimize your cash flow. So had we

introduced the idea of contracts, we use

the analogy of the rules of a game.

Contracts aren't just a legal legal

document. It's a rule book for how the

project should be delivered. Tells you

what to do in different situations. But

knowing the rules isn't enough. You need

to be able to play the game, which is

where contract management comes in.

Contracts are the rules. Contract

management is how you play the game.

It's about understanding your

obligations, managing risk, securing

your entitlements, and navigating

challenges that come up throughout the

project. All by playing by the rules,

but knowing how to play to win. So, what

is the goal of effective contract

management? Well, the first one is to

get paid for the work you do, but also

to get what you paid for with your

subcontractors and suppliers. It's about

minimizing disputes as they come up,

handling delays, claims, and risks to

ensure you get your entitlements and

you're getting your obligations, but

also ensuring that you're not exposed to

unnecessary liabilities. So, there's two

stages to contract management. There's

contract formation and contract

administration. Contract formation is

the stage when we set up and negotiate

the agreement. We set up an agreement

with our client that ensures we've got

reasonable terms and conditions and the

opportunity to make money on the project

and we negotiate agreements with our

subcontractors to ensure we're getting

the best value for money from the

market. Contract administration is then

executing the project, ensuring we're

fulfilling our obligations but also

receiving our entitlement. So contract

administration we can break down into

two key sets of tasks. We've got

business as usual activities. So this

covers the sets of activities that are

undertaken when everything is going as

planned. This means the project scope is

unfolding as expected. We're not dealing

with any major changes and both parties

are complying with their rights and

obligations. Then the second set of

contract administration tasks, we've got

change and issue management. This is the

management of exceptional circumstances

and issues as they they arise. These

processes arise as a result result from

changing circumstances, changes to the

scopes, changes to the conditions or

poor performance by one of the parties.

So we can break down formation

administration into the downstream and

upstream contracts. The upstream

contract being the contract with our

client, the downstream contracts being

the contracts with our supply chain, our

subcontractors and suppliers. we've

already spoken about but these are the

four different groups of tasks we'll go

through during contract manager.

Tendering is us quoting and negotiating

contract and signing a contract with our

client. That's upstream contract

formation. Then once we sign that

contract, the head contract, we've got

head contract administration.

Downstream dealing with our

subcontractors, we've got procurement,

which is finding and signing agreements

with our supply chain. Then once these

agreements are executed, we've got

subcontractor administration. So making

sure we get what we paid for. We're

going to cover each of these in a lot

more detail, but these different domains

all have tools, techniques, and

processes we follow. Tendering, head

contract formation, it's about

understanding the client's contract,

preparing your bid, and negotiating the

terms so you can secure a project that

you make money on. procurement. It's

about finding the best value for money

subcontractors in the market. So,

engaging subcontractors, suppliers that

match our terms, our conditions, and

take on our head contract risks. Head

contract administration, it's about

managing your obligations with the

client, getting your entitlements, and

getting extra time and money if the

scope changes. Subcontract

administration. It's about managing your

subcontractors so that they perform and

you don't incur additional costs. As

we're going to cover in each of the next

four sections, the tools and techniques

we're going to be learning with

tendering, it's contract reviews, how to

identify risks, and how to identify

qualifications with your bids.

procurement. It's about establishing and

writing a good scope of works, taking

your head contract obligations and

passing them on to your subcontracts,

and negotiating and signing subcontract

agreements. Head contract

administration, it's about maintaining a

program, maintaining a variation

register, submitting variations, getting

variations approved, and keeping good

records in a site diary. subcontract

administration. It's about maintaining a

program for your subcontractors,

coordinating their works, managing any

variations in claims from them, and

again, documenting and keeping strong

records. So, the first of the four

domains of contract management we're

going to dive into is tendering, head

contract formation. How do we secure the

best possible contract with our client?

How do we secure a pro a contract at our

price with our terms and conditions

where we can guarantee we make money

during execution? So, head contract

formation or tendering, it's about

signing a contract that gives us the

best possible chance of making money.

This is going to be a function of the

price and the terms and conditions. The

price is what we quote to do the work,

what we're going to get paid to deliver

the project, but also the terms and

conditions, who's responsible for what,

how we get paid, the payment mechanisms,

whether we're responsible for liquidated

damages, what type of security we have

to get. We want to basically negotiate

and sign a contract that gives us the

best possible chance to generate profit.

And that's a function of the price and

terms and conditions but also how we

strategize and identify opportunities

for profit during execution. Okay. So

why is this challenging? Well, first one

is that the construction industry is

largely commoditized which means clients

are going to three to six contractors to

deliver a project. Everyone's trying to

give the lowest possible price and the

client is going to choose the cheapest

price most likely. Top of that, the

client is going to be passing on to us

obligations to do the work. There'll be

design obligations. There'll be

technical obligations. There'll be

commercial obligations. And with these

obligations comes a large amount of risk

if we don't perform. It's going to be a

complicated scope. There's going to be

lots of different ways, lots of

different ways to get caught out.

There's a lot of different things we

could potentially miss. There'll be

complex technical requirements. There'll

be requirements to deal with

stakeholders. There'll be requirements

to get certain approvals to do the work.

All of these things make the scope of

what we have to do complicated and

increased. And when you factor in the

fact that it's a quantitized industry

and the client's going to be going for

the cheapest price, basically we're

going to be caught in a situation where

it's a race to the bottom on a

complicated scope and it's increasingly

likely that we're going to miss things.

And on top of that, clients always want

you to sign up to unfair terms and

conditions. They're always going to be

pushing their most aggressive, most

unfair contract onto you with heavy

liquidated damages, long payment terms,

and it's our job to basically work

against the forces of the industry and

to negotiate the best possible agreement

at the best possible price. Okay. So,

the first step in the head contract for

contract formation process is actually

going to be receiving the tender

documentation. A client contacts us,

they want us to quote on a project for

them. This is going to they're going to

send us a package of documentation that

includes the drawings, the

specifications, the scope of works,

contract conditions, schedule, all these

things. And this might come from an

email or it might come from some sort of

tender portal like a connects or Felix.

First question in contract formation is

really going to be, is this a project we

want to do? Should we tender for this

project? How much competition is there?

Is this competition going to drive the

price down and force us to take on

unfair risks? Do we have a ton of other

work going on and we don't have the

capacity to manage it carefully? So the

first part of contract formation, it's

always going to be asking the question,

should we tender for this project? The

second part of this process is then

reviewing the documentation. We want to

perform a highle review of all the

documents they've been provided. The

scope of works, is the scope clear?

What's included? What's excluded? the

program. Can we meet the time frames?

Are they very aggressive? Are there

major liquidated damages on multiple

severable portions? And what are the

contract terms like? Are they major

risks? Are they the liquidated damages?

Do they want huge amounts of security?

Do they want to be able to draw down on

security without notifying us? When

we're doing this, we want to the key

tools we want to create is an RFI or a

big clarification register. So any

questions or issues we have, we want to

quickly ask them so we can get time

frames and responses back in time to

support our tender. We also want to

start preparing a qualification register

or also known as a departures register.

So we want to start listing out all the

parts of the contract, the scope of

work, tender documentation where we are

not going to comply with. The next part

of this process is preparing the

estimate. So we need to build up our

cost to complete the project. This is

going to be based on the scope,

quantities, production rates, and any

market pricing we've got for from our

supply chain. There's going to be

provisional items. There's going to be

items that are excluded. And there's

going to be areas of uncertainty and

risk that we need to factor in. There's

also going to be ways we transfer risk

to our subcontracted. So, if we're

getting we have major subcontracts

during the tenoring phase, we want to

basically get our subcontracts in a

position where we can sign them as soon

as we execute the head contract. So the

tools we're going to use to do this will

be our qualification and assumption

register. This is a really important

document because this is going to be the

basis of our letter of offer. Any

exclusions we're making, any assumptions

that we want to document and clarify

with our submission. It's going to be

our estimate. So our bottom up direct

cost estimate of how much we how much

we're estimating it's going to cost us

to deliver the project and also our

subcontractor to procurement. I can't

stress this enough. If there are major

subcontracts that we're procuring that

we're going to rely on to deliver the

project, we want those in a position

where we can sign them as soon as the

head contract is executed. We have a

subcontractor that that makes up 40% of

the contract value. We rely on them.

They've got activities on the critical

path. Then basically we want if we're

signing up to a separable portion or

completion date in the contract with

heavy liquidated damages, we want to

also and we're relying on a

subcontractor to deliver that. We

basically want to be signing a

subcontract with that same risk

transfer, the same completion date, the

same liquidated damages associated with

it. Now, once we've prepared our

estimate, we want to create our

assumptions and qualifications, our

departures from the scope of works.

What's included in our offer and what's

excluded? This is not going to match the

scope of works and requirements the

client have sent us. We will always have

departures and we need to clearly

document what these are. What are we not

offering to do? Does the client want us

to supply all the permanent materials,

but our pricing is based on them free

issuing them to us? All of these have to

be captured in our departures register.

Any key assumptions we've got, are we

going to be able to work 7 days a week

to meet their program? It has to be made

crystal clear to them when we do this.

Anything unusual or unclear, any key

assumptions we've had to make has to go

into our qualification register. Now in

line with this so when we've prepared

our estimate based on their

documentation we may or may not have

reviewed the contract so far but if we

haven't we need to review the contract

terms. We need to do a detailed review

of the contract and come up with any

terms and conditions that we want to

negotiate or departure. These might be

things like payment terms. So they've

got 45 days from end of month payment

terms and we're going to have cash flow

issues. We'd want 20-day payment terms.

If they want 10% security, we might only

feel comfortable giving 5% security. Do

they have heavy liquidated damages? And

because we've developed a program, we've

checked and we've shown we can't meet

these dates. All of these have to go

into our contract departures register.

We have to look at all the terms and

conditions, we have to nominate the

terms and conditions we aren't happy

with. We want to come up with a proposed

rewriting of that term. Now once we're

ready to submit our bid, we've got our

estimate, we've checked it, it's

correct, we've gone through the scope of

works, the documentation they provided,

we've prepared our qualification

register, we've reviewed the contract,

and we've come up with our contract

departures. We want to submit our letter

of offer. This is our price and our

terms to do the work. It's so important.

I can't keep stressing this. Your price

is one thing. It's the thing your

client's going to focus on, but your

terms and conditions are the opportunity

for you to win the bid. Include your

qualifications, your assumptions, any

requested changes to the contract, and

in your letter of offer, clearly

document what your price to do the work

is, but what your terms and conditions

are as well. Terms and conditions being

your qualifications, the tenant

documentation,

and your contract departures. The next

step is to negotiate and sign the

contract. Basically, what will happen

now is that you've submitted your letter

of offer. Your client will come back to

say they like your price. They're

unhappy with these qualifications. They

want you to repric. You'll go back and

forward. Go on for ages, but basically,

you want to get to a position where

you've agreed on both the price, the

schedule, the scope, and the contract

terms and conditions. To do this, you

really want to do detailed contract

review. If you didn't do one at the

tender stage, be incredibly happy to

what you're signing up to. Critical

thing here is that you want to ensure

that your qualifications, your letter of

offer make it into the scope of works in

the contract. See it happen an

unbelievable amount of times where

people submit certain exclusions to

scope, but they never follow up and

never make sure they make it into the

scope of works. So they'll price to do

one thing, but the contract they sign

says they're going to do another. So you

need to ensure your qualifications, what

you're negotiating goes into the scope

of works in the contract. The reality is

throughout this entire process, and I

say it all the time, is when you're

negotiating a contract, everyone

obsesses over the price and they never

pay attention to the terms and

conditions. The reality is everyone is

going to be focused on your price.

Everyone wants the cheapest contractor,

but terms in terms of your ability to

make money on a project. Your terms

matter just as much, if not more, than

your price. And in a commoditized

industry where there's so much downwards

pressure on your price, everyone's going

to be driving your price down. They'll

want discounts. They'll always want to

go with the cheapest contractor. If you

can understand the terms and conditions

and qualifications to scope and how they

impact your price, you can negotiate

down your price without actually

reducing your profit margins. So that's

your opportunity to focus on negotiating

the terms while reducing your price to

ensure you are in their eyes the

cheapest contractor, but you're still

maintaining your terms and conditions so

you can make money on the project. Next

up, once we've signed the head contract,

we need to talk about procurement

subcontractor formation. How do we find

the best possible subcontractors at the

best possible price? How do we find the

subcontractors we need to deliver the

project while also ensuring we get value

for money? Okay, so subcontract

formation is the process of procurement.

It's the process of engaging

subcontractors and suppliers to deliver

portions of the project work. It's

basically how we transfer our

obligations, our responsibilities under

the head contract to our subcontractors

at the best possible price. We need to

find the subcontractors that we need to

deliver the works. We also want to make

sure we're getting value for money and

the best possible pricing from the

market. So, what makes procurement so

hard? And it is something that most

projects stuff up to a certain degree.

Well, the first one again complicated

scopes. Construction projects are messy

and complicated. There's multiple

trades. There's multiple different

staging. The methodology impacts the

scope. Different vendors impact the pro

the products they choose will impact the

scope. There's all these moving parts.

And ultimately, nine times out of 10,

most construction projects are messy and

complicated because they're technically

complicated scopes. Other thing that

makes procurement hard is that

subcontractors, the suppliers we go to

just know more about the specific scope

than you do. If you're going to a

concreting contractor for a portion of

the works, they'll know a lot more about

concrete construction than you ever

will. You're buying inverters for a

solar farm, you're going to the

technical experts on the subject. So

they have this there's this knowledge

gap between you and them and they have

opportunities to take advantage of you

because they just understand the scope

better. The next one is confusing

documentation. By the time you've put

together a subcontract agreement, you've

attached the scope of works, the

drawings, the program, there's just

every chance that there's mistakes,

inconsistencies, and confusions in the

documentation. and there's differing

interpretations of the scope between you

and the subcontractors which can

potentially lead to variations and

disputes down the track. The last one is

that procurement always happens fast.

Construction projects always done

incredibly fast. There's a rapid

transition from the design going to IFC

to needing to get all our procurement

done and signing up our subcontractors

to starting on site. And often

procurement is the portion of the

project that everyone rushes through to

basically go from an IFC design to

starting on site as fast as possible.

Okay. So how does the procurement

process work? Well, step number one is

we need to define the packages. We need

to break the job into clear packages of

works. For example, for a building we

might have earthworks, concrete, the

building, the structural steel, the

electrical. There'll be all these

defined packages of work. we need to

complete. These packages are captured in

our work breakdown structure and then

within each package there'll be a set of

documents that define the work we're

going to be procuring. The drawings,

specifications, the project

requirements, the tools we use to break

the project down and create all our

different packages are the work

breakdown structure and scope of works

documents. Okay, so once the job is

broken down and we've got our work

breakdown structure and all the

different packages we need to procure

from the market, we need to create our

tender packages, our detailed sets of

drawings and specifications and scope of

works documents that define exactly what

we want to procure from the market. The

litmus test I always use is to put

myself in the subcontractor's position.

There needs to be enough information in

the tender package that if you were the

estimator, you could price it. So, for

example, if you're procuring concrete

construction works, what do they need?

They need the structural engineering

drawings. They need any concrete

specifications. They need the date that

they're going to work on site. They need

the sequence of the build, what sequence

they're getting access to the slabs. Are

they doing the detailed excavation? Are

they doing the piling? Are they doing

the piling breakback? All these things

need to be captured in the tender

package we send them. We then send this

package of information to three to six

subcontractors per tender package. We

want to get multiple quotes. So we're

we're leveraging market competition.

When I spoke about head contract for

formation, spoke about how construction

was a commoditized industry. For head

contractor formation, that's a negative

for us. For procurement, that's an

that's our advantage. It's our

opportunity to get multiple quotes for a

package and to get the best value for

money from the market. Then we want to

provide them a tender submission date, a

date we need their response by. And then

we want to we want to leers with the

subcontractors to make sure they

understand the information what we've

sent them and what exactly what we're

asking for. Now once we get our quotes

back from our subcontractors, the next

step is we want to review and adjust the

quotes as needed. When I spoke about

head contractor formation, I spoke about

departures and exclusions. When we get

quotes back from subcontractors, we need

to identify these same departures. If

we're getting quotes for concrete

construction and one subcontractor has

excluded concrete pumping, but another

has included, we would need to adjust

their quotes and level them. So, we're

comparing apples to apples. We use a

quote comparison matrix or a tender

clarification register to do this. But

basically, for the three to six quotes

we get, we want to make sure that

they're all pricing the same thing. We

can either adjust the quotes ourselves

or we can send them back to the

subcontractors and ask them to adjust

them. Now, once we've got our 3 to six

quotes, we've leveled them, we're

comparing apples to apples, we want to

select our preferred subcontractor. This

isn't going to be just based on price.

We're so reliant on our subcontractors

to deliver the project that the small

savings we'd get by going to the

cheapest subcontractor if we know that

they don't have the cap capability to

deliver it can quickly wipe out the

entire project. So, we want to choose a

subcontractor based on the value they

offer, the capability, whether they can

meet the program, what risks they're

happy to take on, and also the price.

Ultimately, at the end of the day, we

want to maximize the value to money

ratio. We need a subcontractor who can

perform the work safely to program

taking on certain risks. And we also

want to make sure we're getting the best

value for money. So, we're also going to

negotiate on their price. In the same

way we negotiated our head contract, now

we need to negotiate our sub

subcontracts. We need to make sure

they're taking on all the scope we want

them to. They're taking on the terms and

conditions and we've negotiated their

price. Tools we're going to use to do

this are the subcontract agreement. So,

the actual form of contract that they

sign and any internal approvals we need

from our own management to sign off on

the agreement. Once both parties are

happy, we've agreed on the price, the

scope, the program, and terms and

conditions of the contract, we can sign

the contract. Tools we're going to use

to do this will be the actual contract

form and the agreement checklist. We

want to make sure that all of the

obligations we're under for the head

contractor relevant to their scope of

works they're signing up to. For

example, if it's a subcontract on the

critical path and they impact our

completion date and we have liquidated

damages, we should have liquidated

damages in our subcontract.

Once we do that, we can start the

process of onboarding the subcontractor

and getting ready to deliver the

project. Okay, so that's the procurement

process from start to finish. It's

pretty simple. It's basically the

opposite of the head contract formation

process. We're on the other side of the

fence. Some tips for procurement is to

document everything and make sure what

you're agreeing to makes its way into

the contract to ensure your subcontract

mirrors your head contract risk. So,

making sure any obligations you're under

for the head contract, for that relevant

subcontract, whether it's captured in

the drawings, whether it's captured in

the contract terms and conditions,

you're passing on to your

subcontractors.

The key here is if you want to go

properly back to back, you should be

starting the procurement process during

your tenuring phase. So, you should have

backtoback contracts for key packages of

work. That means as soon as you sign the

head contract, you're signing up your

subcontracts. So you're not getting

caught between, you're not exposed to

some risk that you can't transfer to

your subcontractors.

Do this by protecting your cost and

responsibility by clearly documenting

what you're responsible for,

transferring to your subcontractors, and

starting this process as early as

possible. So once we've signed

contracts, we've formed them, the next

step is to administer them. We need to

execute the project in line with our

obligations and our entitlements. First

off, we're going to talk about head

contract administration. How do you

manage the contract with your client to

ensure you make money on the project?

Head contract administration is the

ongoing administration of the contract

with your client. It's about ensuring

that you deliver what's required and you

get paid what you're entitled to. This

means if your client delays you, if the

scope changes, you get paid for these

changes. So what makes head contract

administration so hard? Well, first off

is the high administrative load. As soon

as the project starts getting delivered,

you need to start safety documents,

quality documents, managing the

schedule, dealing with subcontractors

that all the administration tasks in the

head contract can slowly start to slip.

You stop taking paying attention to

records. you stop maintaining the

program, it's very easy to stop doing

these key tasks. Second one is the risk

and responsibility transfer. You would

pro you probably signed up to a whole

lot of risks, completion dates with

liquidated damages, all these things and

you're basically now accountable for

everything. The scope, program, and

conditions are probably going to be

changing continuously. You'll be

requested to price additional work.

Things the client access dates the

client will have given you won't have

been fulfilled and there'll also be

strict procedures you have to follow in

the contract. If you miss a notice

period or a deadline, you might get time

barred and lose your entitlements. Okay.

So to begin with the business as usual

head contract administration task. What

are the regular ongoing tasks you need

to do day in day out to keep the project

moving? First one will be your payment

claims. So these are regular monthly

invoicing of the client for the work

you've completed and you'll probably

need to provide a lot of substantiation

to these. Next will be project

reporting. You might have to give a

monthly report. You might have to give

weekly schedule updates. You might have

to give records of how many inclement

weather days you've been delayed.

whatever the contract says you need to

report on and to maintain and submit an

upto-ate construction program

as you work through the project. You'll

also have regular meetings with your

clients which for these you should

record meeting minutes and document any

correspondence formally with action

items and agreed upon solutions. Again,

when disputes start to come up, meeting

minutes are unbelievably important.

You'll need compliance records. For

example, safe work method statements,

insuranceances, quality assurance

documents, subcontractor onboarding

forms. All of these compliance records

will have to be documented may have to

be submitted to the client. And also any

requests for information. So questions

to your clients about issues with the

design, changes, access dates, all of

these RFIs and any communication about

change will have to be documented. Okay,

so that's the business as usual task.

What about when things change? How do

you deal with changes and issues? Well,

the first one will be extension of time

claims for delays. If your client's late

and giving you site access, you'll need

to claim for more time so you can adjust

your completion date. You'll have to put

in variation claims, both claims to the

client when you think something's

changed and requests from the client to

do additional work. and also any back

charges and credits. When there's

quality issues, when there's scope

overlaps, the client may try to take

work off you or may try to reduce your

contract value. So, these are some of

the ways the contract can change and

what you'll have to continually be

working through on the project. So, when

things change, you always have to

consider notice requirements. What sort

of time frames do you have to give your

client? You might have to give them

notice within 48 hours. You might have 5

days to do it. And then after that

provide substantiation and valuation of

the change. So you might need records,

photos, an impact to the program,

correspondence. That's why records

matter so much when you're talking about

head contract administration and

documentation. You always need to be

able to prove what you're saying because

basically construction budgets tight.

Anytime you're trying to claim for more

money or time, client is incentivized to

push back as hard as they can. So what

documentation should you be maintaining?

You should always have a variation

register. You should always have a delay

or event notification template. So some

simple template you can send to your

client to say because of XY Z we've been

delayed as per the original baseline

program. RFI registers and claims and

correspondence folder. So tracking all

the correspondence about certain claims

if they're approved, if they're not.

Basically, what you're trying to do

through the head contract administration

process is to secure your entitlements,

reduce disputes, and protect your

margins. If you don't manage this

properly, you risk not getting paid for

what you're owed. You lose the ability

to claim for time or cost. If you don't

meet your notice periods, and you absorb

risks that should sit with your client.

Okay, so we've spoken about how to

manage and administer head contracts.

Let's talk about how to administer the

subcontracts. How do you ensure you're

getting what you're paying for? Most

contractors at best leave money on the

table and at worst go broke because they

don't manage their contracts properly.

So, in this video, I'm going to show you

10 contract management mistakes

contractors make that can very easily

send them broke. These mistakes going to

be broken down into contract formation

mistakes, mistakes before you sign the

contract and contract administration

mistakes, mistakes during execution of

the project. Okay, so the goal of

contract formation is to sign a contract

with terms and conditions and a price

that gives you the best possible chance

of making money. Subcontract

administration is about managing your

subcontractors and suppliers to ensure

they deliver on time, to the

specifications, and within the budget

while protecting your own commercial

position with your client. It's about

getting what you paid for, covering

yourself. At the end of the day,

depending on the type of project, your

subcontract costs might make up 70 to

80% of the total project value, which at

the end of the day means you're relying

on your subcontractors to deliver the

project. You need to be managing them

properly. So, the goal of subcontract

administration is to ensure

subcontractors deliver their scope at

the agreed cost, on time, and without

exposure to risk. This means avoiding

scope gaps or delays, preventing back

charges or disputes, ensuring your head

contract obligations have been passed on

and you're managing those, and

maintaining cash flow in commercial

control. So, why is subcontract

administration so difficult? Well, at

the end of the day, yes, your

subcontractors are on site. Yes, you've

signed a contract with them, but you're

still accountable for the work they

perform. they go insolvent, they go

broke, if they decide to get into some

huge dispute and they walk off the job,

your client doesn't care. Still your

obligation to manage the work. The other

reason it's hard is again I spoke about

the knowledge gap between general

contractor and subcontractor. Your

subcontractors know more about the work

and they often will come up with their

own strategies to maximize their own

profit. And if scope isn't crystal

clear, it becomes a battle of

assumptions and they're always going to

know the work better than you. They're

always going to have their own

strategies to make money from

variations. Subcontractors have their

own priorities. They might have 10 jobs

on at once. They might have another job

that's going bad that's taking all of

their management attention. They'll have

their own priorities, their own separate

business with their different interest,

which at times because construction once

you sign a contract is by definition a

zero sum game. Every dollar you pay them

is a dollar you don't get. There is

going to be they are going to have

different priorities to you. And again,

comes down to personalities,

relationships. you are going to be

working very closely with these people

and sometimes you're going to be working

with difficult people, people who are

adversarial, all these sorts of things.

So subcontract administration can be

incredibly hard. Okay. So what are the

business as usual subcontract

administration activities? Well,

there'll be you'll need to onboard your

subcontractors. You need to get their

insuranceances, their safe work method

statements, organize their site

inductions. You'll have regular

coordination meetings with them where

you go through the program, the access

to site dates, how they're going with

their works, when they're planned to be

finished. You'll have they'll submit

their own payment claims to you for

review and approval. You'll assess the

works and approve them. They'll be

submitting variations to you. So,

they'll claim certain scopes have

changed, certain things have changed,

and you'll need to monitor their

performance of the work. Are they on

time? Are they doing the work correctly?

Is their quality correct? All these

sorts of things. Okay, so what are the

core business asusual tools you're going

to be using? They be things like

onboarding checklists, your payment

claim assessment templates,

subcontractor variation logs, site

diaries records, and your construction

program. Can't stress this enough. The

program is one of the most important

contract management tools, both with

managing the head contracts and managing

all of your subcontracts. Okay, so those

are the business as usual tasks. What

about change and issue management? What

happens when things change from what was

agreed on during contract formation?

Well, you might have subcontractors who

are underperforming. They might not be

resourcing the project properly. They

might miss their own start dates. They

might have they might poorly manage the

work. They might be late in ordering

materials. All these sorts of issues can

come up. There might be dis there might

be disputes over scope. They might be

claiming things or variation when you

don't think they are. They might have

defects. They might have rework. and

they might not be fixing it properly or

they might be saying it's not their

responsibility to fix or you could have

safety or compliance issues. They could

be continually performing the works

poorly. All these sorts of issues happen

on every single project. Okay. So, how

do you manage these sorts of subcontract

issues? Well, the first one is going to

be notices and back charge. If your

subcontract subcontractor is not

rectifying their defects within a set

period of time, you should be sending

them notices. If you have had to do work

for them, you should be back charging

them for it and setting it off against

your payment claims. They're submitting

you you variations. You should, if

you've set up your contracts correctly,

you should always have head contract

entitlements for variations if you've

set up your subcontracts properly. A lot

of the time there will be variations

which you can't claim from your head

contracts will have which will have to

come out of your contingency. But again,

you should be negotiating these

variations with the subcontracts. You

should be asking for detailed

breakdowns, how they've priced it. You

should be fact-checking their pricing

because they're always going to try and

inflate their cost if they are

underperforming. And you have to be very

careful with this because there's a lot

of legal regulations around this, but

you should withhold payment if they if

you are entitled to according to the

contract. You should always be very fair

about how you do this, but it is a

negotiation tactic you can use. And you

should have clear records. You should

have photos, meeting minutes,

correspondence trails, everything to

back up what you're doing. Again, in

line with the contract and in line with

what's fair and reasonable. You

shouldn't be bullying your contractors

and taking advantage of them, but you

shouldn't let them take advantage of you

either. Okay. So, what are the tools we

commonly use? We use delay notices and

templates. We use non-conformance

registers. We might be sending our

subcontractors NCRs. We might have back

charge registers, variation registers,

and also as always communication logs.

Most contractors at best leave money on

the table and at worst go broke because

they don't manage their contracts

properly. So in this video, I'm going to

show you 10 contract management mistakes

contractors make that can very easily

send them broke. These mistakes going to

be broken down into contract formation

mistakes, mistakes before you sign the

contract, and contract administration

mistakes, mistakes during execution of

the project. So, the goal of contract

formation is to sign a contract with

terms and conditions and a price that

gives you the best possible chance of

making money. First big mistake

contractors make is they focus on price

over terms and conditions. If contractor

A submits a quote for $100,000 and

contractor B submits a quote for

$200,000, which contractor is cheaper?

Well, the obvious answer is contractor

A. The reality is you don't actually

know the answer to that question until

you understand the terms, conditions,

and clarifications that surround that

offer. The reality is everybody in the

construction industry focuses on price.

But the reality is contractor A might

have submitted a quote, excluded 90% of

the scope, not signed up to liquidated

damages, want faster payment terms, and

have all these other qualifications when

contractor B has agreed to do everything

in the specifications. The takeaway is

because everybody in the industry

focuses on price, terms, conditions, and

scope your opportunity. You can be

willing to negotiate on price because

the construction industry is a

commoditized industry. People choose the

cheapest contractors. But if you can

clarify your terms, conditions, and

scope. So you can pull down your price

but still structure your terms and

conditions so you have the opportunity

to make money. It will increase the

chances of securing profitable

contracts. Mistake number two is

trusting relationships over writing. On

my last project, we had a fantastic

relationship with the client project

manager where he'd worked on the

pre-contract stage and then was there at

the start of project execution. We'd

agreed on everything. We started

delivering the work and then the clients

swapped project managers. They brought

in a new project manager who read the

contract to the letter and a whole lot

of things we thought we weren't

responsible for were not clearly

documented in the contract and he used

that to their advantage. So even though

we previously agreed on certain things,

they swap project managers and then the

new project manager led the read the

contract to the letter of the law. This

is a classic contract management

mistake. assuming a good relationship

with your client will protect you and

90% of the time it probably will. It's

the 10% of the time where you're caught

out that can lead to real disaster. So,

have a good relationship, but also

insist everything is in writing and

everything is documented crystal clear.

Mistake number three is not agreeing to

a program. I'm shocked how many

contractors sign up to a contract with

heavy liquidated damages without a clear

construction program showing them what

dates they're relying on to meet their

completion date in the contract.

Basically, people agree to build

something by a certain date without any

understanding of what has to be in place

to meet that date. If you do this,

you're signing up to delays that you'll

wear the cost of without any control

over them. Key takeaway is a

construction program that clearly

defines the access dates, what dates

you're relying on from the client. It

gives you the opportunity to claim

delays if you're delayed. So, the

construction program is one of the key

contract management documents. Mistake

number four is signing up to harsh

payment terms. Contractors pay wages

weekly. They may have to pay suppliers

upfront, but then they sign contracts

where they get paid 30 days or 40 5 days

from end of month. Basically, from the

day you start the work, you might be 2

months behind on payment. So, basically,

you're financing the project. Cash flow

is a bigger source of insolvency in the

construction industry than the

profitability of projects. Don't just

accept the payment terms in the

contract. Negotiate them and push back

on them. push for 20-day payment terms,

cash retention over bank guarantees,

interest on late payments, mobilization,

and early costs that you can claim in

the payment schedule. Anything you can

to ensure that you're getting paid

before you're incurring costs. Mistake

number five is not getting backto back

risk transfer with your supply chain. If

you're relying on your subcontractors to

deliver the project for you and you're

not getting backtoback risk transfer,

you're basically signing a contract to

guarantee the performance of your

subcontractors without any guarantees

from them. If prices change or scope

shifts, basically your core between and

you're going to wear these additional

costs. The key takeaway is before you

sign a contract with your client. Set up

your subcontracts, agree to the scope,

the terms and conditions, the program,

everything you're responsible from the

head contract. Ensure your

subcontractors can achieve that. And the

day you sign the head contract, be ready

to sign up your subcontractors. Okay.

So, avoiding these five mistakes should

get you to the point where you've signed

a contract, your best possible chance of

making money. Next, what can you do

during project execution to ensure your

project is profitable? The first mistake

during contract administration to avoid

is never do additional work unless you

have a written variation. Multiple times

in my career, I've had clients ask for

additional work, instruct us to do it,

and then when they get the bill for it,

to dispute the original instruction.

They might think it's all well and good

to tell you to do something, but then

they're shocked when the bills come in

and they'll clarify that, oh no, they

didn't mean that or no, they didn't

actually want you to do that work. And

they'll try and get out of paying you

for the additional work. If you don't

have it in writing, it becomes a he

said, she said situation. So before you

do any additional work, make sure you

submit a variation, you agree on the

price, because once you've done the

work, you lose all of your negotiating

power. The next mistake is not getting

paid early and often. As soon as you

start doing work, put in a payment

claim. Try to get paid early and often.

Even do a test payment claim so the

process is ironed out. There's no

issues. So when you start spending huge

amounts of money, you've already got a

structure for how to get paid and you've

already worked through the process with

your client. The next mistake, and I'm

guilty of having done this multiple

times, is not dealing with change as

specific issues, but bundling a whole

lot of variations together into one big

messy claim that gets disputed. I was

working on a major electrical job and

there were about 10 changes to the

lighting server works. We bundled this

together into one big variation claim

and it was a mess. The client suddenly

got confused by all the changes.

Everyone was confused on what was

happening, how it was valued, what the

original change was, how the change

impacted the price. When you're dealing

with variations, it's much better to

have a lot of small changes where

everyone agrees on the change and the

valuation of the change than to try to

bundle 10 variations together into one

big claim. The key takeaway is submit

small clear variations with specific

details on what changed, why it changed,

what's the cost impact, and any

supporting documentation. It will be so

much easier to get these approved. The

next big mistake I see is not

maintaining a construction program. As I

was saying during contract formation,

the program is your tool for claiming

additional time and cost if the client

is late in giving you access. The only

way you can do this is if you maintain

an upto-date and relevant construction

program. Update the program weekly.

Track plan versus actual. Go through it

at your weekly meetings with the client.

They'll see you as more professional for

doing so. And it will also be incredibly

easy to justify any EOT or claims you

make. And the final one that most

general contractors are guilty for is

letting and forgetting your

subcontracts. We signed a contract with

our subcontractors. We send them the

drawings. We tell them what they to come

to site. And then we basically just

assume they're going to manage

themselves. And a lot of really good

subcontractors will. That's basically

all you have to do. It's the

subcontractors that underperform, make

mistakes, and don't manage the work

properly that you get caught out for. So

even if you trust your subcontractors,

you know they're going to do a really

good job, you still need to stay on top

of them. If you just assume they know

what they're going to do and they don't,

you're setting yourself up for failure.

Rework the ladders and cost blowout. So,

the key takeaway is micromanage your

subcontractors. Track everything. How

they're going with their quality, where

they're up to in the program, what works

completed, what's not completed. Go and

physically check this for yourself.

Check on their safety, how they're

performing, and inspect everything. That

old saying, trust but verify.

Is it going to rain tomorrow? Does it

matter? Well, if you're planning on

spending all day inside watching

Netflix, then probably not. If you're

running a civil construction project

that's turning over a million dollars a

day, then a day of standown due to wet

weather is a huge issue. If you've only

budgeted for 10 inclement weather days

and you're 50% of the way through the

project and you've already had 15, then

it's a major issue. Uncertainty is

unavoidable on construction projects.

Everybody knows you need to plan

projects. Planning won't separate you as

a construction manager. But if you can

learn to manage and take accountability

for unpredictability and uncertainty,

then you're going to put yourself ahead

of 99% of construction project managers.

So, in this video, we're going to

outline everything you need to know

about construction project risk

management. We'll talk about why it

matters, what it is, the core concepts,

the different types of risks you'll face

on a construction project, how to manage

risk on a construction project from end

to end, how to deal with the specific

environmental, health, and safety and

cash risks, and finish off with a case

study where we explore applying these

concepts in practice.

So, let's start off with an allimportant

question. Why should you care about risk

management? Well, the first thing I want

to establish is that planning is the

baseline. 98% of project managers create

a plan for their project. Yet, only 48%

of construction projects finish under

budget and ahead of schedule. Why? Well,

a plan tells you what should happen

given our assumptions and our planning

is correct. But given such a small

percentage of projects achieve their

objectives, we can see there's a huge

difference between the way people plan

and the way projects are delivered in

practice. So why do plans fail? Well,

for a simple reason that construction is

unpredictable. We get weather conditions

we never could have planned for. We get

scorching hot days, heavy rains or

strong winds that cancel crane waves. We

get supply chain disruption. We get late

delivery from suppliers or key

subcontractors going broke. We get site

conditions that we couldn't have

prepared for. There might be unknown

utilities or poor geotechnical

conditions that screw up our earthworks

productivities and we get people issues.

We get labor shortages or disputes with

subcontractors.

Every plan we create relies on

assumptions around these core variables

that always end up being different to

what we planned for. On top of that,

because the construction industry is so

heavily commoditized, meaning the

cheapest price tends to win, the

subcontractor or contractor who makes

the most aggressive assumptions around

these unknowns tends to be the ones who

get the job. Meaning, the person who

underestimates the risk is often the one

doing the project. This leads to a set

of circumstances and an environment that

makes effective risk management

incredibly difficult. You can plan as

much as you want, but planning alone

won't protect you if your assumptions

are wrong and you have not prepared for

uncertainty. Excuses like we were late

because a key supplier failed just

aren't good enough. And the best

construction managers accept, prepare

for, and deal with uncertainty. They

take accountability and ownership of it

through effective risk management. And

the evidence supports this. A big study

by McKenzie found that effective risk

management is one of the key drivers of

successful project delivery. You can

think of it like this. Planning develops

a road map for how we're going to

deliver the project and risk management

protects this road map. It involves

several key actions, including

identifying possible risks, possible

sources of uncertainty that matter,

assessing their impact and likelihood,

developing response plans such as

avoiding, reducing, transferring, or

accepting, and monitoring and updating

this risk management plan continuously.

Fundamentally, effective risk management

is about resilience, not prediction. You

can't predict everything that's going to

go wrong, but you can be ready for it.

Study by the PMI found that effective

risk management can reduce the impact of

unpredictable delays by up to 20%. Risk

management protects your profit margins,

keeps your schedule realistic, reduces

costly disputes with subcontractors and

suppliers, and enhances safety and

compliance. Without it, we'll blow our

budgets, miss deadlines, suffer quality

issues, and damage the relationship we

have with our key clients. Planning

tells you what should happen. Risk

management prepares you for what might

happen.

So now we understand why risk management

matters and why you need to be able to

deal with uncertainty to be an effective

construction project management. Let's

get into the nuts and bolts of the topic

and start by talking about what is risk

management. So put simply risk

management. What is it? Well, it's the

process of how we take uncertainty and

turn it into manageable action. Risk

management is the structured approach of

identifying, assessing, treating and

monitoring uncertainty that may affect

our project goals. Project goals could

be anything like cost, time, quality,

scope, safety, reputation with the

client. So risk management is the way we

address the sources of uncertainty and

how they impact these goals. It allows

us to turn uncertainty into manageable

action.

Okay. Intrinsic to this definition of

risk is this term uncertainty.

So it's important to distinguish between

what's a risk and what's uncertainty.

So all risks are uncertainty, but not

all uncertainty a risk. What do I mean

by this? There's uncertainty in

everything and everywhere and what we

do. Who will win the lotto tomorrow?

What is the weather going to be like in

Greenland? and what will our production

rate for trenching be? These are all

sources of uncertainty. The difference

is that what our production rate for

trenching is a risk for the project. A

risk is a source of uncertainty that

matters. So any risk has to have two

components. It needs to be uncertain and

it needs to matter. Meaning needs to

impact the project goals. So risks are

specific uncertain events or conditions

that could impact the problem project

objectives. Importantly as well is that

if something has happened, it's not a

risk. If we know our production rate is

lower than what we plan for, it's not a

risk because it's not uncertainty. It's

a known it's a known issue we need to

deal with.

Okay. So next up, we've got this idea of

a threat verse an opportunity. So it's

important to understand that risks are

not always bad. How much is it going to

rain tomorrow is a risk. It's a source

of uncertainty that it matter matters

and it will impact the project

objectives but it could be both a threat

meaning it has a negative impact on the

objectives or it could be an

opportunity. If we have a contract

signed where we're allowed to claim

additional cost and time for any

inclement weather then it would be an

opportunity. we're going to get paid

extra to deliver the same project scope

because we're delayed by poor weather.

If however, we've got a fixed budget for

inclement weather. And if we go over

that, we have to wear the cost of that,

then by definition, it's a threat

because it's going to negatively impact

our project objectives.

Okay? So, the goal of risk management

isn't just to deal with the negative

consequences. It's also to increase the

chance of our opportunities happening.

So on one side, we're trying to

eliminate or reduce the impact of our

threats, but we also want to increase

the chances of our opportunities

happening.

Okay, the next thing I want to talk

about is basically defining some of

these key terms around risk. So we've

got a cause, a risk event, and

consequence. A cause is a condition or

trigger that makes the risk possible.

For example, extended heavy rain could

be a cause of our inclement weather

risk. The risk event is the uncertain

event itself. For example, the concrete

pour being delayed because of the poor

weather. And the consequence is the

impact on project objectives if it

happens. So for example, if excess heavy

rain, the cause delays our concrete pour

the event, then the consequence would be

the project timeline extended by 3 days.

Clarifying and understanding his

definition definitions helps you

understand a bit more about risk

management. Okay, let's look at another

example. So, we've got a key

subcontractor is in financial stress due

to under bidding multiple projects.

That's the cause. The risk event is the

subcontractor going into default in the

middle of the project and not being able

to finish the work. The consequence is

then the immediate need to find a

replacement resulting in increased cost

because we were to quickly procure

someone from the market delayed because

there'll be a period of time where we

need to find the additional

subcontractor and potential legal

dispute. That's an another example of a

risk where we've got the cause. So the

subcontractor being in financial stress,

the consequence or the risk sorry the

risk event which is the subcontractor

going into default and then the

consequence which is the impact of the

additional costs and time to find

another subcontractor.

Looking at another one we've got design

changes. So the cause the client's

approval was pending with lastm minute

conditions and we didn't get it properly

signed off before we needed to start

work. The risk event is the approved

design may need some sort of redesign

due to clashes with the facade layout

and the mech and plumbing. Consequence

would be redesign work, additional

procurement, additional rework on site,

cost overruns and so on and so forth. So

that's another example where we've got

the cause was poorly coordinated design

where the client didn't sign off in

time. The risk event with was the

approved design may require some sort of

changes post IFC and then the

consequence would be additional cost due

to the rework. Okay. So now we

understand a risk event, a cause and a

consequence. Let's actually talk about

the risk management process. What is the

process that we follow to increase the

chances of our opportunities happening

and reduce the chances of our threats?

So it's a four-step process which starts

with identifying our risk. We need to

systematically find the threats and

opportunities to the project. And we can

do this using brainstorming. So group

brainstorming sessions, lessons learned

or expert impact. So the best source of

risks I've always found is people who've

delivered similar projects. They have a

good understanding of what can go wrong.

Once we've identified our risks, the

next thing is we need to assess our

risk. We need to analyze the likelihood

of them occurring and the impact if they

do occur. Basically this is going to

help us prioritize what risks actually

matter. Where should we be putting our

limited time and attention? Step three

is then we need to plan. So we need to

prepare for our responses. So basically

what are we going to do to address each

risk? So for our threats, the negative

risks, we can avoid them. We could

change the plan to remove the risk. We

can mitigate them. We could take steps

to reduce either the likelihood of the

risk occurring or the impact if it does

occur. We could transfer this risk to a

third party through a subcontract or

through insuranceances. And if they're

not significant or not a big impact, we

could just accept them and choose to do

nothing. For opportunities, we want to

exploit them. So take steps to ensure

that they happen, enhance them, increase

the chance that they're happening or the

impact if they do. share them, partner

with someone to increase the chances of

it them happening and accept them that

take advantage of it happens but not

take any steps to increase the

likelihood. Then step four is the

iterative nature of it where we as we go

through the project some risks will

eventuate some will be closed off. We

basically want to continually monitor,

review and update our risk register, add

new risks if they occur and update the

plan if things change.

Okay, next important concept is a risk

register. So the risk register is the

principal tool that we'll be using

throughout the project to track, monitor

and update our risk. This is the source

of truth for uncertainty for the

project. So a risk register is basically

a live log of the identified risks, the

causes and consequences, the assessment,

so both the the assessment of the

likelihood and the impact, the treatment

actions, what we've decided to do about

it, the owner, who on the project team's

responsible for the risk, and the status

and updates. And basically, it ensures

none of our risks are forgotten. We're

keeping track of them, and it's clear

who's responsible for what.

Okay, the final concept around risk

management are risk tolerances. Okay, so

a risk appetite is how much overall risk

the organization is willing to accept in

pursuit of their goals. It's going to

depend on a lot of different factors

such as the size of the project, the

dollar size, particularly if it's a huge

project and it goes bad, that's going to

have a much bigger impact on your

organization than if a small project

goes bad.

But also the risk tolerance. So how much

variation from the plan is acceptable

before action is needed. These help

decide which risk to treat and which to

accept. So for example, we could see

that a company that's willing to pursue

a solar farm engineer procure and

construct contract where they're taking

all the risk of changing material

prices, the installation costs, the

performance of the plant is a very

different risk profile to a small ash

ashfelting job. It's done on square

meter rates where they where the

organization is not even taking the

quantity risk. So you can see different

organizations have significantly

different risk appetites and tolerances.

Okay. To summarize, risk management is

about seeing uncertainty clearly,

understanding what could help or hurt

your project, and having a plan to

handle it so you stay in control,

protect profit, and deliver the project

successfully regardless of the uncertain

events and conditions that can impact

the outcomes.

So now we understand some of the core

concepts around construction project

risk management. Let's talk about the

different types of uncertainty. In this

section, I really want to broaden your

understanding of what a risk is and all

the different sources of uncertainty on

a project. So, let's explore the

different types of risks and how to

group them. Really want to give you a

framework for thinking about all the

different types and forms of risks that

exist on projects.

Okay, so the first groupings is event

versus non-event risk. So an event risk

is a discrete identifiable event that

might happen. For example, a

subcontractor going broke. These are

typically what we think of when we think

of a risk. A discrete identifiable

event. However, it's not the only source

of or type of risk on a project.

Non-event ris risk is variability from

our assumptions when no single trigger

triggers happen. And these are critical

to understand on construction projects

because they exist everywhere. Our, for

example, our actual concrete placement

productivity is lower than expected. Our

actual rainfall is much higher than what

we thought it would be or our production

rate for trenching is different to what

we planned. That these sources exist

everywhere and they describe all the

different assumptions we need to make.

Now we try to improve the accuracy of

our assumptions but at the end of the

day through our estimate through our

schedule there are assumptions built

into these and these sorts of non-event

risks exist everywhere

in the pinach these are called

variability risks.

So the key takeaway here is to

effectively manage our risk, we need to

consider what could happen. So a

specific event, but we also need to

consider what could be different to what

we assumed. A non-event risk.

Okay. So the next distinction I want to

make are between

known risks and unknown risks referred

to as black swan events. So a known risk

is a risk we could reasonably foresee

based on our past project experience.

the experts in our team. These are

things we can identify and then plan

for. If someone's working at heights, we

know that there's a potential that they

could fall. So that is a risk we need to

address.

A black swan event, also referred to as

an unknown or unknowable risk, are risks

that are unexpected, highly unlikely,

and beyond normal prediction. For

example, the classic that everyone talks

about now is CO 19 shutdowns where there

was this sudden huge pandemic. It was

unpreped. There was nothing like it

before. You can't plan for specific

black swan events. But, and this is the

important point is that you can develop

project resilience. For example, having

contingency funds set aside, having

flexible contracts, good communication

between our subcontractors, suppliers,

and stakeholders, and strong

relationships all help to this idea of

project resilience. But we're not

planning for a specific risk because

it's by definition, we can't know it's

going to occur. Rather, we have a

resilient and flexible approach that we

can adapt if some sort of uncertain

event or condition occurs.

Okay, next let's talk about some common

ways to group risks and the different

categories. So these are typically what

we think of when we think of different

categories of sources of risk. So first

up we've got technical risks. So

technical risks are things like

incomplete designs, design errors or

incorrect specifications that impact

more of the engineering side of the

construction. We've got project

management risks, so poor planning,

unrealistic schedules, scope creep.

We've got contractual or commercial

risks such as unclear terms, the

potential for claims and disputes. Got

financial risks. So these are budget

overruns, funding delays or cash flow

issues. Supply chain risk. So this is

where we get late materials. We get

subcontractors going broke or price

fluctuations between when we negotiated

contract when we signed it and when we

needed to order the materials. Got

construction risks such as productivity

shortfalls, equipment breakdowns, and

rework. Got external risks such as poor

weather, environmental conditions or

regulatory changes. Got stakeholder

risks such as client disagreements or

community objections. And then we've got

health, safety, and environmental risks

such as accidents,

pollution, or non-compliance fines.

We can also group our risks by

consequence. So we could have cost risk

which is a budget overrun, unexpected

reworks, claims from subcontractors. You

could have schedule risks, so delays,

waiting on approvals that delays the

schedule, productivity shortfalls. Could

have quality risks such as defects or

non-conerformances. We could have safety

risks such as injuries or lost time

incidents. We could have environmental

risks such as spills, erosions or

regulatory fines. We could have

reputation risk. So this is where the

client is dissatisfied or we get

negative publicity.

And then the final way we can categorize

our risks is by ranking them in terms of

their impact on the project. So the

impact on the project or the potential

impact on the project is going to be

combination of the likelihood, the

probability of the risk happening and

the impact if it does occur. This sort

of matrix you'll see everywhere on

construction projects and it's two it's

a ex two-dimensional matri matrix that

is where we classify a risks qu qu qu qu

qu qu qu qu qu qu qu qu qu qu qu qu qu

qu qu qu qu qu qu qu qu qu qu qu qu qu

qu qu qu qu qu qu qu qu qu qu

qualitatively based on their impact. So

whether they're negligible, minor,

moderate, significant or severe and the

likelihood of where they occur. So very

unlikely to very likely. We can see if

something's very likely to occur and

very severe if it severe if it does

occur. And that's where we need to be

putting our time and attention when if

something is negligible, if it does

occur, and very unlikely, then it's not

worth our time and effort.

So, now we've got a good understanding

of the different types and categories of

risks that exist on construction

projects. Let's dive deeper into how to

specifically manage risk on a project.

So, the risk management process is a

structured systematic method for dealing

with uncertainty on a project. It

ensures you spot risks early, understand

their importance, have a plan to deal

with the important risks, and then

monitor and update your risk register

continuously. So as the project

progresses and things change, you stay

on top of the uncertainty that matters.

So most international standards, project

management bodies break it down into

four main steps. Step one is to identify

risks. Step two is to assess the risks.

Step three is to plan our responses. And

then step four is to monitor and review

and iterate on the risk management

process.

Okay. So step one is to identify risk.

What it means basically it's to

systematically find and record all the

sources of uncertainty both threats and

the opportunities that can impact your

project. How do we do this? We

brainstorm with the project team. We use

checklists and reviews from last

projects and lessons learned. We talk to

our stakeholders. We review the contract

conditions, the design drawings, site

reports. We engage with experts who know

what they're doing and have worked on

this exact type of project. For example,

during planning, the team identifies

that the schedule concrete pores are

planned during the region's peak rainy

season. They also notice that the supply

contract depends on a single steel

supply. So, they've identified two main

risks for their project. heavy rain that

may delay the concrete works, which is a

threat. A sole steel supplier that may

cause delivery bottlenecks, again, a

threat. And if potentially an

opportunity where the weather is

unusually dry, pores could progress

faster than planned. Now, this is broken

down into event risk, but you could also

categorize this as a variability risk

where we've got a set assumption of how

much inclement weather we think there's

going to be and that assumption may be

lower or higher than what we predicted.

Step two is we then need to assess the

risk. What this means is we need to

analyze for each risk how likely is it

to happen and how big will the impact be

if it does occur. We can do this

qualitatively using categories like low,

medium, or high like the risk register,

the risk matrix I showed you in the last

section. Quantitatively, if we've got

good data, we could actually calculate

these numbers specifically. For example,

we could do look at how much it's rained

over the last 10 years, how variable

that is, how accurate our assumptions

can be, and then we rank our risk. So

basically, the high impact, the high

probability risks are the ones we focus

on. For example, the risk rain delays,

the likelihood's high and the impact is

medium to high. It could push our

schedule up 5 days. We prioritize this

as high. Our steel supply delay, the

likelihood is medium, the impact is

high. So then we rank the risk high. And

dry weather that speeds up the pores.

Let's say the likelihood's poor because

we've looked at 10 years of historic

weather data and it never rains less

than what they think it's going to rain.

The impact is medium. you only get minor

cost savings. So the priority is

therefore low. Okay. So then step three

is to plan our responses.

What this means is we decide what action

to take for each of our risks. So for

our threat, our options are to avoid the

threat, mitigate the threat, transfer it

to another party or just accept it. For

opportunities, we can exploit them,

enhance them, share them, or accept

them. How do we do this? Again, we use

brainstorming, looking at all the

different practical applications. We

assign an owner to each. Again, this is

critical because we have to treat risks

and risk responses in the same way that

we would treat any task in the project.

Someone needs to be responsible for it

happening. And then we update our plans,

budgets or contracts if required. So,

for example, rain delay, we've

categorized as a high risk. So, we're

choosing to mitigate it using faster

concrete curing concrete mix, installing

temporary weather shelters where it's

possible, and sequencing the pores to

allow flexibility. The owner of this

risk is the site manager. The steel

supply delay, we want to transfer and

mitigate this. We want to add in a

backup steel supply to the contract and

order the critical sections of steel

earlier. So, we're both mitigating the

risk and then transferring it to a

supplier. The owner will be the

procurement manager to ensure that's how

the supply contract with the with the

steel supply is written. Then for the

dry weather opportunity, we want to

enhance it basically by just having a

contingency crew available that if we

get particularly good weather, we can

bring in extra resources and we can

finish the works as quickly as possible.

The owner is going to be the project

scheduler.

Then step four, we've got our continuous

iterative process. basically just

monitoring and reviewing the risks and

keeping them up to date. What this means

is we kept keep track of the risks

throughout the project. We ask ourselves

our treatments working has a risk

changed and a new risks appearing that

we need to assess and identify and plan

responses to. Basically, how we do it is

we'd set a weekly or monthly catchup

meeting depending on the duration of the

project and how important the risks are.

And we just go through the risk

register. We go through every risk and

look at all the information in it and

ask ourselves if it's still relevant. We

also want to hold regular meetings to

brainstorm and identify any new risks

that are cropping up. So, for example,

our construction manager monitors the

weekly weather forecast and plans the

concrete pores around when it's likely

not to rain. The procurement manager

tracks the steel supply deliveries to

ensure the supplier is on track and if

there's delays the main steel supplier

they get their backup supply ready. So

it's basically just the process of

checking our response is working things

changing can we close off risks and so

on and so forth. Okay. So why does this

four-step approach work? Well, it

ensures we start early. The earlier we

identify the risks, the cheaper and

easier it is to manage them. It's a

consistent concept in construction

management that the earlier we address

an issue, it's generally much cheaper to

fix. We assign clear owners. We treat

risks like any other task in the project

and we assign someone to manage them. We

keep it live because this is an

iterative approach and we're going

through it and continually updating it.

We track it and manage it as the project

progresses and we also communicate

effectively. We share our risk updates

with our client and key stakeholders. So

we ensure there's no surprises and we

keep them on board and supportive of the

project. If something changes outside of

our control, least we can say we had a

plan and did our very best.

How do you manage risk on a construction

project? Working on a project, it's not

a question of if risks will eventuate.

It's a question of when they'll

eventuate and how prepared we are to

deal with the projects that implement

risk response strategies are 58% more

likely to finish on time and 43% more

likely to finish under budget. As a

construction project manager, if you can

master project risk management, it is an

undisputable fact that your projects

will be more successfully and ultimately

your career will be more successful.

That's why in this video, we're going to

look specifically at risks on

construction projects, how to manage

risk, the process to follow, how to use

risk management to become a better

construction manager. Risk is the

uncertainty that matters to the

projects. It's the things we don't know

about, the uncertainty in our plan, and

the uncertainty that can impact the

outcomes of the project. So when we say

risk matters, we're saying risk has an

impact on the objectives of the project.

What are these? So it could impact the

health and safety of anybody working on

the project, the impact to the

environment, could have an impact on our

cost, our budget, could have an impact

on the time it takes to complete

project. And could it also have an

impact on the perception of the project

from our stakeholders? When talking

about risk on construction projects, we

can group these impacts into two

separate categories. We've got our zero

harm goal and we've got our project

success goal. So, when we're talking

about zero harm, we're talking about

eliminating any harm to people or the

environment. Now, this is an ethical

responsibility. It's not about making

more money. It's not about making people

happy with delivering the project. It's

about keeping people safe and avoiding

any sort of environmental harm. So this

is an ethical responsibility that we

have as construction project managers.

The other side we've got our project

success factors. So we want to make sure

the project is a success financially and

also finishes on time. So when we're

talking about project risk management,

talking about the process of conducting

risk management, planning,

identification, analysis, response

planning, and control on a project. What

does this mean in practice? Well, it

means we're increasing the likelihood

positive events by exploiting

opportunities and decreasing the

likelihood of negative events by

eliminating the rates. Okay, so now

we've established what project risk

management is in the context of

construction projects. Let's go on to

talking about the different categories

of project risks. So when we're talking

about risk categories, we're talking

about the categories or the groupings of

uncertainty that impact objectives. On

construction projects, we've got the

following categories of risks. We've got

technical risks, construction risks,

health and safety risks, environmental

risks, commercial risks, and external

risks. Okay, so the first one are our

technical risks. What are these? These

are risks to do with the development of

the project technical solution. So

making sure that what we build can work

and operate correctly. So for example,

these would this might be something like

this designing the strength of a

building foundation to meet the

earthquake requirements or designing a

HVAC system to ensure it meets the

climate control objectives of the

building. Okay. Once we develop the

technical solution to the project,

construction is the process we go

through to create the design to deliver

the project in accordance with the

drawings and specifications. There's a

lot of uncertainty in this process. We

can have issues with coordinating

subcontractors. We can have delays in

materials or we can have poor

workmanship resulting in defects and

rework. So construction risks are

uncertainties in the construction

process that can impact the objectives

of the of the project. Throughout the

construction process, we have the risk

of harming workers or members of the

public while completing the construction

activities. Construction projects are

dangerous. We might have to work at

heights. We'll be completing crane

lifts. We could drop things. We could

strike inground services while

excavating. There's a lot of

uncertainties throughout the

construction process that can have a

significant impact on people's health

and safety. And in the same way that we

can have health and safety risks, we can

also have environmental risks. So we

could have an oil spill. We could have

polluted water running off into a

waterway. We could remove native

protected vegetation without the

appropriate approvals. So we could have

all sorts of environmental risks while

we're completing the construction

project. Now tied into all of these

other risks, we can also have commercial

risks. So these are risks arising from

our contractual rights and obligations.

So we could have a dispute with our

client. We could have a dispute with our

subcontractors.

Our client could be delayed in paying us

resulting in cash flow issues or we

could be late in finishing the project

and incur liquidated damages. In the

final category, we've got external risk.

So we could have risks arising from our

stakeholders or impacted third parties.

So we could be prevented in accessing

the work site because we have to go

through private property or we could

have a utility not giving us approval to

complete construction excavation near

their underground service. So we can

have our works impacted by the actions

of third parties. Okay. So we've

established

what project risk management is and how

it relates to construction projects and

we've also spoken about the different

categories of risks on construction

projects. Let's now talk about the risk

management process in construction.

Okay. So here we've got an overview of

the risk management process. The high

level the risk management process we

follow is we establish the context. We

understand what's important to the

project. We identify our risk and

opportunities. Then we analyze, evaluate

and treat them. And then throughout this

entire process we're continually

monitoring and controlling to ensure the

risk management process is working as

planned. Then we're also communicating

with our stakeholders, those impacted by

the project, so they're aware of the

uncertainty that matters to the project.

Okay, so first off, we need to establish

the context. Okay, so first off, we need

to establish the context. What do we

mean by saying establish the context?

Well, we want to tailor the depth and

complexity of the risk responses to the

specific characteristics of the project

we're working on. There's a cost

associated with the risk management

process. It takes people's time, takes

resources, that costs money. On top of

this, there's a law of diminishing

returns. The more effort we put in

doesn't won't necessarily result in

better outcomes. We want to tailor the

risk management process to the

specifics, project risk, the project

specifics. On top of that, we want to

understand our specific project risk

thresholds. If we're working on a $10

billion project, a $2,000 cost blowout

on a material order isn't a big deal. If

we're working on a $20,000

minor home renovation, then a $2,000

cost blowout is a pretty big deal.

That's why for any specific project

we're working on, we need to understand

our risk thresholds. What are considered

important risks? What are considered

unimportant risk? These are going to

come, we can group these into three

categories, safety, schedule and cost.

And for our specific project, depending

on the size, nature of the project, we

want to come up with a scale of low,

medium, and high for the specific

project risks. Okay, so we're talking

schedule. We could say for our project,

a delay of 0 to 5 days is considered

below risk. A delay of greater than 20

days is high risk. can do the same with

our cost to come up with different

categories of impacts. Okay. So once

we've established the context, we

understand the specific project

thresholds, the context with which we're

going to apply the risk management

process, the next thing we need to do is

we need to identify the risk. We need to

identify the sources of uncertainty that

matter to the project. It's critically

important when we're identifying risks

that we're identifying risks. We're not

identifying causes. We're not

identifying impacts. And we're not

identifying problems or issues. When we

define a risk, for any risk, we should

be able to express it in the following

sentence. As a result of a specific

cause, an uncertain event may occur

which would lead to an effect on

objectives. As an example of this, we've

got as a result of latent site

conditions, excess contaminated soil

disposal may occur, which would lead to

increased disposal costs. So, we've got

the cause, which is latent site

conditions. We've got the risk, which is

excess disposal of contaminated soil.

And we've got the impact, additional

disposal costs. So, how do we identify

these sources of uncertainty amount?

Well, there's three ways we can do this.

We can look at the past, so what has

happened on previous projects to give us

an indication of what risks may

eventuate in our project. We can look at

present. We can talk about what we're

currently exposed to. We can talk about

the future. What could go wrong? We

could use brainstorming. So using these

three broad buckets of past, present,

and future, some techniques we can use

that integrate these. So we can look at

lessons learned from previous projects.

We can talk to subject matter experts.

So people who've got experience

delivering the type of projects we're

working on. We can use checklists. So a

checklist would capture a supererset

possible risks we're exposed to on the

project. We can look at contract

analysis. So we can look at the specific

contract we've signed and look at what

risks we're exposed to in the contract.

We can look at other sources of

documents that might give us an

indication as to potential sources of

uncertainty. And we can use

brainstorming. the the output of the

identify risk process is going to be the

risk register. This is where we document

all of the different types of project

risks we're exposed to. So for example,

the excess contaminated soil, the design

solution failing to meet the client

requirements or additional scope that we

haven't budgeted for. We'll categorize

these risks. We'll describe these risks

and we'll talk about the effect. Then we

need to analyze these risks. So we've

identified all the sources of

uncertainty that matter. Now we need to

analyze them. We need to work out which

of these risks matter. Now there's two

ways we can do this. We can use a

qualitative risk assessment or we can

use a quantitative risk assessment. So a

qualitative risk assessment is a

subjective risk assessment where

likelihood and impact are categorized

using our risk threshold. So low, medium

or high. Quantitative risk assessment is

where we use verifiable data to assign a

specific numer numerical cost or delay

to each of the risks. Okay. To complete

a qualitative risk assessment, we go

through each risk in our risk register

and we give it a probability and an

impact. So a probability is a chance of

occurring. An impact is the result if it

does occur. This can be in terms of how

much it will cost if it eventuates, how

much it will delay us or what sort of

health and safety consequence we'll get.

Across these two dimensions, we'll

categorize these into our risk

thresholds and then give it a risk

rating. So the risk rating is the

product of the probability and the

impact. This means high probability,

high impact risks will be given the

greatest score with low probability and

low impact risks given a lower score.

Then each of our risks we can score

based on these two underlying

characteristics. How likely they are to

occur and what happens if they do occur.

So a risk that's almost certain to

happen and catastrophic if it does occur

would be an extreme risk. A risk that is

unlikely to occur and low impact if it

does occur would be a low risk. Now,

this is an important exercise to do

because it allows us to get a holistic

view of which are the most important

risks to the project. Where should we be

putting our time and attention? We're

going to summarize all of this

information in our risk register. So,

against each of the individual risks for

the project, we've given it an impact

level, a prob probability level, and

then we can give it an overall risk

rating. Okay. So we've spoken about how

to do a qualitative risk assessment

which ultimately comes down to some sort

of subjective judgment as to the impact

and likelihood of each of the risk. The

other way we can do this is with a

quantitative risk analysis. So we can

look at all the risks in our schedule

and we can assign a numerical value to

each of them using data to support us.

So we can do this at the micro level

where we look at an individual risk and

score that risk based on an underlying

calculation or we can look at a macro

level where we look at the overall

impact of risk on the project outcome.

So we do this in terms of schedule

calculation or a budget calculation. So

the benefits of a quantitative risk

analysis is it actually gives us a

specific probability of achieving each

of the specific project objectives. So

we can develop what's referred to as a

P50 schedule. So an anticipated finish

date based on a 50% likelihood.

It also allows us to identify realistic

project ts and give us exact values for

different project risks and to also help

us analyze the cost of risk responses

versus the benefits. Okay, so now we've

analyzed our risks. What do we have to

do next? We need to evaluate which are

the most significant and important risks

on the project and then we need to do

something about them. So the important

risks will choose to develop a treatment

in response to a risk. There's several

different things we can do. We can do

nothing. We can ignore it. It's small.

It's insignificant. We choose to do

nothing. We can treat the risk. So we

can come up with some sort of plan to

mitigate the risk. So this means

reducing its likelihood or reducing its

impact if it does occur. We can

undertake further analysis and

investigation. Maybe we decide we don't

have enough information to perform a

proper judgment or proper significance

analysis. If we've already got some

controls in place, we can simply

maintain the existing controls or in

certain circumstances, we can actually

reconsider the objectives of the

project. So we can change what we're

choosing to focus on and how we're

defining project success. So a risk

treatment is taking some form of action

in response to the risk to reduce the

threat or maximize the opportunity. This

is the essence of project risk

management. If we're not treating our

risk, if we're not doing anything about

them, none of what we've done so far

matters. Okay. So what treatments do we

have available for any risk or we can

avoid or exploit the risk? This means

eliminate the risk or make the

opportunity definitely happen. We can

transfer it or share it with another

party. So we can involve another person

or party in the risk. For example, if

we're exposed to inclement weather, we

could transfer this to our

subcontractor.

We can reduce or enhance the risk. So

reduce the threat or enhance the

opportunity or we can accept the risk.

We can just accept the risk as it is and

choose to do nothing about it. So what's

the optimal strategy? The optimal

strategy is going to depend on the

specific risk, its likelihood and

impact, its risk rating, its urgency, so

how quickly we need to do something

about it, its manageability, how what

can we actually do about it, and its

propquity, which is a fancy way of

saying how in control are we of the risk

and also the cost of the risk response.

Okay, there's a continual problem that

project managers have where they make

plans, they work out what to do, and

they never do it. And it's highlighted

by this age-old riddle. If there's five

frogs on a log, and one of them decides

to get off, how many are left on the

log? Well, the answer is five. One of

them decided to get off, but they didn't

get off. Project risk management is

worthless if we don't do anything about

it. If we don't implement the risk

response strategies we've come up with,

this goes for any project management

process where we develop a plan, we

decide what to do. If we don't actually

do it, then all the planning we've done

has no value. To get anything out of

this process, we need to implement our

risk responses. Best way to do this is

just to treat them as project task.

Define the scope of the task, the

duration, the budget, the completion

criteria, and give them an action on it.

allocate the responsibility of

implementing the risk response to an

individual on the project team and

follow up to make sure they do it. Okay,

let's talk about our contaminated soil

risk. So, we're responsible for dealing

with contaminated soil in our project,

but we don't know how much contaminated

soil there is. So, what do we decide to

do? We decide to manage the risk. We

want to transfer this responsibility to

a subcontractor.

The timeline for implementing this risk

response is the procurement phase. By

the time we sign a contract with our

subcontractor, we need to have agreed on

a way of transferring this risk to them

for the budget of $30,000. So, we've got

contingency funds of $30,000 set aside.

And the responsible person for ensuring

this happens is the Earthworks package

late. to the one preparing and managing

the procurement of the earthworks

contractor. To successfully implement

any project risk response, it's all

about having a controlled response. We

just need to treat the risk response

strategy as any other project task. This

means we need a clear plan of how it

will be implemented. We need a known

deadline for implementing it. We need to

reassess the plan if it's not being

followed to understand why. We need a

budget and a duration. We need a

responsible person. And then if we're

not successfully implementing the plan,

we need to go through a change

management process. The essence of risk

response implementation is just treating

it like any other project task.

Throughout this entire process, we want

to be man monitoring and controlling the

process to making sure everything's

being followed correctly. We're

following up and we're identifying any

new risks as they arise. Risk management

is an iterative process. We're going to

be cycling continually through this

process throughout the duration of the

project. There's lots of different ways

we can do this. We can do process

reviews. We can make sure we're

regularly iterating through the process.

We're following through meetings. We can

audit our policies and procedures. We

can deal with changes as they arise and

assess these in terms of their risk. We

can look at outcomes of the project and

identify certain trends like areas where

we're overspending the budget. We can

look at specific incidents and we can

also communicate and engage with our

stakeholders. The key is when we're

talking about monitoring, controlling

risk management is just to iterate

through the risk process. Iterate

through the entire risk management

process. You constantly want to be

cycling through identifying, analyzing,

evaluating, treating, and then assessing

how effectively these treatments are

working. Simplest way is to set a

regular meeting in your calendar,

whether it's weekly, fortnightly,

monthly, and identify and treat any

emerging risks and look at the current

status of our existing risks. In

summary, risk is the uncertainty that

matters to the project. Risk management

is the process we go through to

eliminate threats and exploit

opportunities. It's a series of steps we

follow both at the beginning of the

project and iteratively throughout the

project. And risk is a reality of

projects. It's not a question of if a

risk will eventuate, it's when and how

prepared we are to deal with it.

As construction project managers, we

have an ethical responsibility to ensure

the safety of everybody working on our

projects. Other project outcomes like

cost or time are an important part of

our jobs, but safety is different.

Making sure nobody gets hurt will always

be our number one priority. If we can't

do it safely, we don't do it. It's as

simple as that. That's why in this

video, I'm going to talk about how to

manage health, safety, and environmental

risks on construction projects. I'll

talk about what a health and safety risk

is, why they matter, and how to manage

them. I want to start with a simple

example. Looking at the picture on

screen, what hazards can you see? Even

in this picture, there's a surprising

amount of hazards. There's traffic. You

could have someone crash into the

construction site. They could be

underground services like gas or

electricity that we dig through. They

could be people working around the

excavator leading to people and planet

interactions. You could have dropped

objects from people working above. You

could have a structure collapse. You

could have machinery fail. You could

have tricks with all the objects on the

ground. Or you could have an oil spill

that goes down the drain. In any

construction project, there is a huge

amount of different hazards that we need

to be aware of and we need to manage.

With all these different hazards, as

construction managers, our role, our

responsibility is to make sure the

activity is safe enough to do that we

can be confident that nobody's going to

get hurt while doing it. That's where

the ethical responsibility of

construction management comes in. Okay.

So let's define health and safety risk

management. So health and safety risk

management is the process of managing

construction activities to eliminate or

minimize as far as reasonably possible

the risk of injuries or fatalities. So

an example of this would be working at

heights would be using scaffolding and a

harness so we can safely complete any

works at heights. Another example could

be temporary electrical equipment we

have set up around the construction

site. So, we could use routine

inspections by a qualified electrician

to ensure that there's going to be no

electrical faults and the equipment is

continually safe to use. And more

generally, we could have regular toolbox

talks with the workers to make sure

they're aware of the different risks on

site and they're constantly paying

attention to and focusing on safety.

Now, managing all of these separate

hazards, all these separate risks is the

fundamental ethical responsibility of a

construction manager. What I mean by

this is while managing cost, managing

schedule is fundamental to your job

role. And if your projects below their

budget, then you're not going to be able

to work as a construction manager for

long, it's still a part of your job

role. Health and safety is different.

Health and safety is an ethical

responsibility. you're morally obliged

to make sure that the people working on

the project are safe. The fundamental

principle behind health and safety risk

management is if the job can't be done

safely, then we don't do it. It's as

simple as that. The key thing we need to

understand though is how do we know if a

job can be done safely? What does that

mean? Well, it means that the hazards

have appropriate controls in place.

Again, we come back to this word

appropriate or sufficient. What does

this actually mean? Well, now I'm going

to explain a concept called the

engineering hierarchy of controls. We're

going to clearly define what we mean by

an appropriate control. What is a

sufficient level of control? So, we're

going to talk about all the different

controls that we can have in place going

from eliminating a hazard, substituting,

isolating to administrative controls to

simply PPE. We're going to talk about

them in terms of their effectiveness and

then what is a sufficient control to

have in place. So the first level of

control we can have is an elimination

control. An elimination control is the

it's the best. It means we're physically

removing the hazard. It means the hazard

no longer exists. We've removed the

hazard completely. And these sorts of

controls are best or easiest to put in

place during the planning and design

phase of the project where we have most

control over the sequencing and the

specific task we need to complete. An

example of this say we got some works at

height. We could say fitting off an

antenna on a structure. If there was a

way we could fit off the antenna at

ground level and then simply erect the

structure, then we we've eliminated the

need to work at height. The next type of

control we can have is a substitution

control. So this is where the hazard

still exists to some degree, but we've

substituted it with a safer option. For

example, excavating around services. We

could substitute mechanical excavation

with an excavator with vacuum excavation

with a non-destructive digging truck.

The next is an isolation control. So an

isolation control is where we physically

isolate people from the hazard. For

example, if we've got people that need

to walk along a road to get to a

construction site and there's a risk

that they get hit by a car, we could

physically isolate them from the hazard

by putting in place concrete barriers

that protect them. Then we have an

engineering control. So an engineering

control is where we put in place a

system to engineer out the risk. For

example, for working at heights, we

could put in scaffolding. So that would

be an engineered solution to minimize

the risk of somebody falling off an

exposed edge. Then we've got an

administrative control. So this is where

we put in place a rule or tell people

that they aren't allowed to do something

dangerous. For example, we put in place

cones along a road and we say people

aren't allowed to step across this line

to eliminate the risk of interacting or

getting hit by a car. And then we've got

PPE, so personal protective equipment,

which is the lowest level of control we

can have in our hierarchy of controls.

And it's simply wearing protective

equipment like helmets, gloves, high

viz, and glasses. And it's the least

effective form of control. Okay. So we

can clearly define what is a sufficient

level of control based on this hierarchy

of controls. any activity where we're

exposed to a hazard, we need to have as

a minimum an engineering control. We

can't have an administrative control and

a PPE to eliminate the hazard. So, we

can't say that example of people having

to walk along a road to get to the

construction site. It's not sufficient

to simply say you're not allowed to walk

within 2 m of the road. You have to put

in some sort of barricading to isolate

or engineer out the hazard. For example,

working at heights, if you have an

exposed edge, you can't simply tell

people you're not allowed to walk up to

the edge. You need to put in place some

sort of scaffolding that eliminates and

or engineers out the hazard. So, as a

bare minimum, what is safe enough? Well,

safe enough means we've put in as a

minimum an engineering control. So this

could be guards on a machine. It could

be ventilation in confined spaces. Or it

could be edge protection when working at

height. Simply putting in PPE or

administrative controls is not

sufficient. So saying you can't go next

to an exposed edge or wearing a helmet

will protect you from a dropped object.

It's simply insufficient and it's not

considered safe. Okay. So now I'm going

to talk about what tools we have

available to manage safety on a

construction site. Okay. So the first

tool we've got available is a safe work

method statement or a SWIMS. So a SWIMS

is a document used to identify and

control all of the hazards. So we walk

through a construction activity, look at

all the steps in the process and against

each of these steps we identify the

hazards and the control we're going to

put in place. Okay. So as an example,

we've got a safe work method statement.

So safe work method statement is a table

like the one on screen and it's going to

list out what are the tasks involved,

what are the hazards associated with the

task and then what are the control

measures we're putting in place and

importantly who is responsible for

putting in place the control measures.

So if you look at an example an activity

like roof tiling

the hazard is slipping or falling from

the roof the control measure will be

scaffolding.

Then we specifically document how the

control measure will be implemented. So

scaffolding guard rail and access to the

roof and then who is responsible for it

the roof tiling supervisor. Okay. So the

next tool we have available a safety in

design workshop. So safety in design is

a series of workshops held during the

planning and design phase of a project

where different team members throughout

the entire life cycle of the project. So

during construction, commissioning,

operations and maintenance all come

together and we run these workshops to

identify all of the potential hazards

across the different phases of the life

cycle. These comments are recorded in a

register called the safety and design

register. And these comments need to be

closed out during the design phase. So

all of these potential hazards need to

be addressed. Now safety and design is

so effective because of an underlying

principle. Principle is that the earlier

on you identify and control a hazard,

the more effective it is to implement

the control. So during the concept and

the design phase, if we identify hazard,

we can design out the hazard. We can

completely eliminate it. If we identify

during the procurement phase, we can

make some changes, but we've lost some

abilities to influence the design. If we

only identify the hazard during

construction, we're limited in what we

can do. So the earlier we identify

hazards, the more control, the more

options, the better options we have to

control them. Okay. So let's look at a

safety in design example. So we've got a

hazard that's been identified which is

working at heights which is roof access

for services during maintenance. There's

no existing controls in place. The phase

of the project is the operations phase.

And then we also put in the likelihood

and consequences

and the control method. So a control

method is to include safe maintenance

access points and facilities for

harnesses in the design. And then we've

got our control the level of risk after

the control is put in place. We do this

all the potential hazards identified

during the safety and design. Next

option we have available is competency

and training. So we can train the people

completing the task of the skills and

capabilities to complete them safely. So

there's two parts of this. There's

verifying competencies. For example, if

we're getting someone to do electrical

work, we need to check they're an

electrician. The other way we can do

this is we can actually train people and

equip them with the skills to complete

the task safely. For example, we can do

a site induction so the workers are

aware of the specific hazards to our

site. Now I've stressed the importance

of safety as an ethical responsibility.

I want to highlight another important

consideration that safety is a

legislative requirement. It's an ethical

responsibility, but it's also a legal

responsibility.

It's a criminal offense to have people

working in unsafe conditions. As a

construction manager, you can go to jail

if you don't properly manage and control

safety on projects. And ultimately, one

of the most important things with safety

is to develop a culture of awareness to

make sure safety is at the forefront of

everybody's mind, that we're regularly

discussing it in pre-arts, toolbox, and

site inspections, and people feel they

have the authority and capability to

stop work if they feel unsafe. Okay, so

what are the key takeaways? Well, safety

is an ethical responsibility. It's not a

bureaucratic activity. It's an ethical

responsibility we have to make sure the

people doing the work can go home

safely. We can't do something safely. We

don't do it at all.

What is safe enough? Well, safe enough

means that based on our hierarchy of

controls, we have as a minimum an

engineering control in place for any

hazards. And there's a variety of tools

we've discussed available to us

including safe work method statements,

safety and design toolbox talks to

ensure these controllers are in place

and we can fulfill our ethical

responsibilities.

In this video, we're going to go through

a case study of effective project risk

management. Often the best way to learn

is through examples. We're going to

cover everything we've spoken about so

far in this section. We're going to go

through and we're going to apply it to a

wind farm. Okay. So, the project we're

working on is the construction of a new

wind farm. It's in a coastal area with

high wind potential and the objective of

the project is to generate electricity

and connect to the local power grid.

Okay. So, let's recap our risk

management process and how we going to

control the uncertainty that matters on

our project. Need to establish the

context. We need to identify the risks

and the opportunities. We need to

analyze these risks. We need to evaluate

them and then we need to treat them.

Okay. So step one, we need to establish

the context. So the over so we've got an

overview of the project. The

construction of a wind farm in a remote

coastal area to generate renewable

energy. Goal of the project is the

timely installation and activation of

turbines to meet energy production

targets and capitalize on favorable

weather conditions. Stakeholders. We've

got we've got the project owner, the

contractor, logistics providers, local

authorities and environmental agencies

and the constraints. So we've got

challenges include complex logistical

issues, weather variability and

environmental compliance. Okay. So as

part of properly establishing a context,

we need to go through and determine the

impact and likelihood of different risks

and categorize them into low, medium and

high. Next step is we need to identify

our risk. So we can do this through

stakeholder engagement. So conduct

interviews with key project workers,

stakeholders such as the logistics

providers and the regulatory

authorities, host risk workshops and

then review our existing documentation

such as the EPC contract, the project

specifications, the grid connection

requirements and any specific

environmental approvals. Okay. So the

risks we've identified weather

interruptions, so high winds can cause

disruptions to things like crane lifts.

We've got supply chain delays, so delays

in having the turbines delivered.

Transportation challenges, so

difficulties in moving the oversized

turbines to site, technical failures, so

risk of malfunction and underperformance

of the turbines, and environmental

compliance, so challenges in adhering to

wildlife and environmental regulation.

Okay, so now we're going to analyze and

focus on one specific risk, the

transportation challenges. So delays or

issues to transporting the large

turbines to site challenge on any wind

farm because of how big the turbines

are. And it's such a challenge to an

extent that you have to upgrade roads

often to the likelihood this is high due

to the remote location and the

complexity of the route. The impact

could significantly disrupt the critical

path task like delivering the turbines

at site and we're rating the risk as

critical. So it's highly likely to

happen and it has a huge impact if it

does happen. Okay. So now we need to

evaluate the risk. So we assess each

risk based on the impact the schedule,

budget, stakeholder expectations and

safety. And we want to prioritize the

key most important risks. So these ones

we've identified are transportation

challenges, weather interruptions and

supply chain delays. These are our

critical risks that we need to focus on

and that we need to do something to

address. Okay, so for the transportation

challenges, what are we going to do

about? Okay, so we need to get root

planning and permanent approval. So we

create this as a project task and we

allocate that responsibility to someone.

We should engage specialist transport

providers. We want to engage a company

that has done this exact type of work

before and can coach us through the

entire process. We want to set up a

local staging area to make the trip as

easy as possible. We want to consider

weather when we're doing this. So all of

these possible risk response responses

are risk and opportunity treatments we

need to treat as project tasks. We need

to make them the responsibility of

somebody to implement. Once we've

decided to implement these specific risk

response strategies, we then need to

monitor how effectively we're managing

the project risk. So, we're going to use

real-time tracking. We're going to use

GPS and regular check-ins on each of our

deliveries to make sure that they're

progressing as planned. We're going to

have regular risk review meetings, so

once a week, once a month. We're going

to have a workshop to re-evaluate the

risks and we'll determine how effective

our response strategies are. and we're

going to maintain our contingency and

adjust it as we proceed through the

project. So in summary, we worked

through a simple case study of a wind

farm construction project to look at the

types of risks and what we could do

about it. As you can see, proactive

planning is a form of effective risk

management. If we put in the upfront

effort to think about everything can go

wrong, what is the uncertainty that

matters? What can we do about it? and

then treat the risk management as

project task as specific activities

allocated to someone. We put them into

place and we focus on what we can

control. We'll do a lot to deal with the

inherent uncertainty of any project.

Here's the complete guide to

construction quality and completions

management. We're going to talk about

everything from inspections and test

plans, punch list and close out. and

we're going to give you strategies that

are simple, effective, and you can apply

to any type of construction project.

Let's be honest, quality isn't the most

exciting part of a project. I've heard

people say they love estimating,

scheduling, but I'm yet to hear someone

who says they're obsessed with quality.

Quality is all about discipline. It's

about dotting your eyes and crossing

your tees. In an industry where profit

margins are typically around 7 to 10%,

considering that the average project

spends around 5 to 10% of the project

budget on defects and rework, it is an

essential part of construction project

management. Quality management is an

optional. It's the difference between

making money and losing money on a

project. So, in this video, we're going

to be covering why quality and

completions matters, why it's essential

to any type of project. What is quality

and completions? Construction quality

management system, inspections and test

plans, non-conformances,

punch lists and defects, and effective

completions management before finishing

off with talking about some of the

biggest mistakes people make in running

a quality management system.

So before we dive into talking about how

to manage quality, let's answer an

important question. Why should we care?

Why does quality matter? and more

specifically, how does it help

construction companies make money? Well,

the first point I want to make is

quality is your ticket to play. It's not

optional. It's mandated by law and it's

specified in contracts. As an example,

in most countries, you can't get a

certificate of occupancy for a building

unless certain checks and inspections

have been completed. That's quality. If

you don't show compliance building code,

you can't hand over your project. You

can't get paid. And this applies in all

industries, not just residential or

commercial construction. Try connecting

a solar fund to the grid and see how

much paperwork you have to fill out. On

top of that, it's almost always

specified in construction contracts. In

most construction contracts, there are

certain quality assurance requirements

that the contractor has to meet. If the

contractor is not meeting them, they're

in default of the contract. Your client

can effectively stop paying you or show

that you've breached the contract and

terminate the contract. Take for example

the Australian industry standard form of

contract AS-4100. It mandates that

contractors need to maintain and update

quality assurance system. Clients have

the right to audit the system and also

perform their own independent checks of

the work being completed. And if they

can prove the contractor is not

complying, they can backcharge them. And

it can even become a form of contract

default. If you can't prove that what

you're building complies with the

project requirements, clients can and

will stop paying you. On top of that,

more and more clients are expecting

contractors to hold certain licenses and

accreditations like ISO 901, the quality

assurance system. To get certified and

maintain the certification, your systems

must be documented, audited regularly,

and followed. So quality is your ticket

to plate. As a contractor working for

construction companies, you need to be

able to manage quality as a baseline for

your job to continue delivering

projects. The real question then

becomes, should you just do the bare

minimum or is there benefit in going

above and beyond? So next I want to give

you some reasons why you should maintain

not only the barebones quality assurance

system you need to meet the contract

requirements to continue getting and

delivering projects but why you should

go above and beyond and treat quality as

importantly as any other discipline in

the project. So reason number one is

your clients will notice. A clear

professional quality management system

will build your reputation fast. Studies

have found that one of the core things

clients look at and judge the reputation

of a contractor is how professional

their quality management system is and

how effectively they help them to close

out the project and hand it over.

Basically, if you make life easy for

your clients, they'll want you to come

back and do more projects for them. It's

an easy and simple way to differentiate

yourself as a contractor in a highly

commoditized industry. Reason number two

is commercial protection. So quality

assurance records are more than just

paperwork. They're evidence. I've seen

this time and time again on project.

Recently, we were installing specialist

electrical equipment. We had strong

quality assurance records. And when

certain bits of equipment started to

fail, we could very easily prove that we

had installed them correctly. It wasn't

an installation issue. It was a supply

issue and we could claim the warranty.

Detailed quality assurance records

become proof of who did what, when, and

where. And these will save you money in

the long run. The third big reason

quality can save you money is that it

prevents delays between trades. Through

your quality assurance system, you can

check the work has been completed

correctly and fully and will prevent

delays between subsequent trades. For

example, if you've got a civil team

installing pits and then an electrical

team coming in after, if the pits aren't

labeled, the electrical team don't know

where they go. They're going to get much

worse productivities. But if you've got

to check within the civil installation

that all the pits are labeled correctly,

they've all been checked, they're all

roped and mandled, you're not going to

get delays when the electricians come to

site. QA checkpoints allow you to have

fixed handovers between trades that

prevent you bringing electricians, other

trades to site and causing delays.

Reason number four, and the big one, is

just avoiding defects and rework. As

I've mentioned before, defects and

rework typically cost between 5 to 10%

of a project's value. I can't count the

number of times I've seen simple things

like pre- poor inspections save tens of

thousands of dollars. Just think QA as

mistake prevention. Reason number five

is closing out the project faster.

Projects always fail during completions

and close out. No matter how effectively

construction was managed, the schedule

was adhered to. It's so common to see

teams spend just as long finishing the

last 5% of the project as they did doing

95% of the work. Why does this happen?

Well, I call it kicking the can down the

road. Get all these little jobs piling

up, all these tiny little tasks that

were too hard to do during the main

construction. Maybe you needed special

materials. Maybe you needed labels to

get reprinted. Everyone gets demobed and

then suddenly you end up with this 5% of

the work that's the most challenging

tedious little tasks. They all pile up

and they end up taking months and months

more than anyone could have ever

expected. A proactive quality assurance

system where you're proactively

identifying and closing out defects as

you do the work will save you so much

time during the last 5% of the work. So

in summary, while most contractors treat

quality assurance as a box ticking

exercise, it can and will save you money

if you implement an effective quality

assurance system. Smart contractors use

quality to prevent mistakes, protect

their business, impress their clients,

and finish projects faster.

So next up, I want to talk about some

core principles of construction quality

and completion strategy. I want to

define the core terms you need to

understand. These concepts are just

going to help you understand the broad

picture of quality management

completions and how it relates to the

objectives of the project. The first one

I want to talk about are requirements.

So what is a requirement? It's just what

we're getting paid to deliver. What our

clients, what our stakeholders actually

want us to build. So there's two core

types of requirements. And understanding

these is going to help you understand

the overall terminology around a quality

management and quality assurance system.

So the first one are product

requirements. These are the physical

deliverables that the client wants us to

build. They want a threelane bridge with

guardrails, lighting, landscaping, so on

so forth. This is the finished

construction project. The deliverables.

Second type of requirements we have on

project are process requirements. So

these are non-product deliverables,

things we have to do, but they're not

part of the finished construction

project. For example, certain

requirements about how the work has to

be done. For example, we might only be

allowed to work during certain hours.

There might be quality assurance

requirements we have to meet. We might

have to provide evidence of how things

have been built. We might have to give

them concrete testing. We might have to

give them like certain electrical

testings and signoffs. There might be

completions requirements. So things we

have to hand over at the end of the job

to help the client with handing over to

their maintenance team. So we might have

to do a training session. We might have

to hand over spare parts. So we've got

the product requirements, what we're

physically building. Then we've got the

process requirements. So things outside

of the finished product, but we still

have to do them as part of our contract.

Okay. So where do requirements come

from? Well, basically requirements come

from contracts. We sign a contract to

deliver a project. Attached to this will

be supporting documentation that defines

what we have to deliver. So we can have

drawings and design documents attached

to that. We can have project

specifications,

contract clauses, code and statutory

obligations, standards, international

standards or we might have third party

or client standards. So why do

requirements matter in the context of

quality? Well, requirements define the

baseline against which we measure

quality. Effectively, we're being paid

to build something. What we're being

paid to build is defined by the

requirements. Therefore, the

requirements define the baseline against

which we measure quality. The purpose of

quality is to measure we've delivered

the project in accordance with the

requirements. Okay. This then helps us

to actually define what quality is. So,

what is quality management? It's the

system to verify and validate that the

constructed product meets the original

requirements. For example, the design

drawings show us that we have to build a

3 m by 2 m tall concrete footing using

32MPA concrete. The quality system is

then going to verify that we're using

32MPPA concrete, that we including test

results to show that it's measured

strength, that there's been a survey

check to correct check it's in the

correct position, that there's been a

pre-pour inspection. Then the quality of

strong documentations is the documented

proof that what we've built matches the

requirements. Now I'm going to introduce

you to another incredibly important

concept when talking about quality

incomp completions and this is systems

engineering. So systems engineering is a

model that illustrates how requirements

are defined and validated throughout the

life cycle of a project. So this is

comes from software engineering

commissioning a broad different range of

types of projects but the principle is

very similar. You start with a project

definition phase where you go from

requirements. You progressively

elaborate these through establishing the

requirements, defining them better,

producing a concept design, checking

this concept design meets the objectives

of the project, doing the detailed

design, getting to an IFC stage, then

constructing this design, and then we go

through a series of testing and

integration to always verify and

validate that these requirements have

been met. So you start on the left side

starts with general project goals. They

progressively turn into design

specifications. And on the right side of

the V, you can see that as we move from

something being built, we're testing and

commissioning to check these

requirements have been met. The systems

engineering model is the easiest way to

think about how design quality and

completions all relate. I'm going to

talk about this a little bit more, but

it's basically this understanding that a

requirement gets turned into a design,

gets constructed, then goes through a

series of testing. Basically, that we

prove that the original requirement has

been built in accordance with the

original requirements. Now, this relates

to the next important point, which is

the relationship between quality and

design. Design is the process where we

define the technical solution that meets

the requirements. Quality management is

then ensuring that what we have

constructed conforms to the design. Now

this is a very construction specific

definition of quality and design. For

example in software other types of

projects they speak about quality more

holistically but in other words when

we're talking about construction project

the design is telling us what we need to

build. Then quality is really ensuring

that what we have built complies with

the design. That's why design

development is a critical part of

overall project quality management and

is essential to a proper functioning

quality assurance system. Okay. So

building on this definition we come to

construction quality assurance. So our

definition of quality assurance and a

quality assurance system on construction

project in construction quality

assurance we focus on compliance with

the design documentation the drawings

and specifications. Well holistic

project quality management focuses on

this entire systems engineering v which

includes defining the original

requirements turning these into an IFC

set of drawings. When we talk about

construction quality management, we're

talking just about this. We're talking

about compliance with the design

documentation. So, while quality

theoretically covers the overall

process, when we're talking about

construction quality management and a

construction quality management system,

we're talking about inspections,

materials testing, conformance

checklists, and basically everything

that we do to verify that what we've

built matches the drawings. The

essential point here is we're not

checking the drawings are correct. Okay.

The next concept, this is a term you've

probably heard about and it's opening a

bit of account when we're speaking about

it, but commissioning. Commissioning

something that applies more to

mechanical, electrical, process systems,

but basically commissioning is this part

of the V. It's how we prove that what

we've built meets the original

requirements as opposed to just testing

something meets the design. So, for

example, we install an electrical cable.

As part of our construction quality

assurance checks, we'll check that the

cable's correct, that it's labeled, that

it hasn't been damaged during

installation, but we're not checking is

the cable the right size. Is it is it

measuring the correct voltage?

Commissioning system will actually check

that stuff. So, you're checking that the

load on the cable is correct, that the

actual because you're also validating

that the cable's been designed

correctly. Commissioning moves through a

series of stages where you test higher

level and higher level requirements to

effectively you're checking the overall

system functions correctly. Okay, what

is completions? Well, completions is us

wrapping up the project. If you

remember, we had two different types of

requirements. We had our product

requirements which were the physical

things we're building. That's what the

construction quality assurance system

checks checks that we're building things

correctly.

Completions is about ensuring all our

process requirements have been met. Have

we done completed all our quality

assurance? Have we packed it all

together? Have we done our owner

training? Have we got our spare parts?

Completions is really about how we

document, wrap up the project, and then

submit it back to our client. It's the

entire process of doing our final

quality assurance close out, getting our

asbuilt drawings, our operations manual,

training handovers, all our statutory

signoffs, and filling out all our client

documentation. If we talk about the

differences between quality and

completions, quality ensures that the

work is correct and compliant.

Completions ensures that everything is

delivered and documented so the project

can be closed off.

In this video, I want to give you the

ultimate guide to construction quality

management. If you're getting confused

by all the different terms like

inspection and test plan, inspection and

test check sheet, punch list, defect

list, category A defect, all these

different terminologies. Don't worry, in

this video, I'm going to spill out

exactly what a construction quality

management system does from start to end

to achieve the project objectives. By

the end of this video, you're going to

understand the role of all these

different components of a quality

management system and importantly, how

to set up and manage a construction

quality management system on your

project. Implementing formal quality

management systems has been proven by

studies time and time again to lead to

more successful project outcomes. So, if

you're wondering if there's something

you can do to improve your job

performance, accelerate your career, the

mastering construction quality

management is without a doubt should be

the top of that list. Everybody talks

about quality management. It's so

important. It does this, it does that,

it does whatever. However, people in my

experience, in my experience in

industry, tend to miss the point. That's

why I wanted to make this video and I

wanted to step through what are the

components of quality management system,

how do you use them, how do they relate

to project success and how do you set up

and manage one. So that's what I really

want to break down as simple as

possible. So in this video I'll go

through what is a quality assurance and

quality management system. The

difference between project quality

assurance and construction quality

assurance, the link between design and

quality. what commissioning is and how

it falls into the overall system, the

components of quality management system,

and then finally, the biggest mistake I

see people making time and time again

when they're managing construction

quality. To understand what a

construction quality assurance system

is, we really have to think about the

life cycle of a construction project. It

starts with a set of drawings and

specifications.

We build the project according to these

drawings and specifications. Then we

create a finished product. The role of

the quality assurance system on the

construction project is to ensure that

the finished product, what we built,

complies with the drawings and

specifications. So the construction

quality assurance system is what relates

the finished product to the original

drawings and specifications. It's the

processes we follow to ensure that what

we've built matches what we intended to.

There's a very important distinction

between project quality management and

construction quality management. So

project quality management is about

ensuring the project meets the original

requirement. So it's about the original

requirements and ensuring what we've

built matches it. Construction quality

insurance is about checking what we

built matches the drawings and

specifications. So these might sound

exactly the same to you. However, there

is an important difference. The

difference is the construction quality

assurance system assumes that the

drawings and specifications capture the

project requirements. So then it's about

ensuring that what we build complies

with the drawings and specification.

Construction quality assurance is a

subset of project quality assurance

because project quality assurance also

has to check that the drawings and

specifications cover all of the project

requirements. That checking that the

drawings and specifications capture the

project requirements isn't a part of

construction quality assurance.

Construction quality assurance is simply

checking and verifying that the drawing

and specifications match the finished

product. Now this process of

transferring the stakeholder

requirements into a set of drawings and

specifications is design development. So

design transfers all the different

stakeholder project requirements and

turns them into a set of issue for

construction drawings that the

construction team then take and then

build according to these plans. For

example, a stakeholder requirement might

be we want a 10-story building or we

want the building to have an external

facade that looks like this or the

building code requires us to have two

fire extinguishers on every floor. So

these are the stakeholder requirements

that get integrated into the drawings

and specifications. The assumption

behind construction quality assurance

system is that the design captures the

stakeholder requirements and somebody's

checked the design to ensure that what's

captured on the drawings meets the

original project requirements. And

therefore, the role of the construction

quality assurance is simply to check

that what we're building matches the

drawings and specifications. And I

understand if anyone's worked on

projects that involve both design and

construction, this is never true. design

always has mistakes. It always has

issues and errors. However, that's not

the purpose of the construction quality

assurance system. Purpose of the

construction quality assurance system is

simply to check that what we're building

matches the drawings and specifications.

Checking that the design correctly

captures all the stakeholder

requirements falls under design quality

management. So the design quality

process is there to ensure the design

fills stakeholder requirements. We can

break this down into three subprocesses.

First one is quality assurance during

the design phase. So while we're

preparing the drawings and

specifications, we're checking are they

correct? Do they meet all of the

requirements? Once our stakeholders

satisfied with them, we've checked them.

they get an issue for construction

drawing set which means as the

constructor we can then begin

constructing of the drawings. This moves

into the construction phase which is all

about identification of errors and

issues during the construction phase

through the RFI process where if we want

to change the drawings or we identify

any issues with the drawings, things

that don't work during construction, we

go through a formal change control

process. Now I call this an RFI, a

request for information. Other people

call them TQ technical queries. They all

mean the same thing. that checking with

the designers during the construction

phase if we want to make changes. The

final part of the design quality

assurance process is the commissioning

process. Now, if you've heard the term

commissioning, you might tend to think

of it as something different. However,

when you look fundamentally at what

commissioning is, it's checking that

what we've built functions as per the

original requirement. So, it's going a

step beyond checking that it functions

as per the design. It's about checking

that what we've built functions as per

the intended requirement. So

commissioning is also an important part

of the design quality management

process. So now I'm going to go into a

little bit more detail breaking down

these three subprocesses of design

quality management. And I know they

don't directly form part of the

construction quality management process.

However, understanding how we check that

the design meets stakeholder

requirements is an important part that

will feed into the construction quality

management process. The first one is

quality assurance during the design

development process, which is the

process we follow to ensure the drawings

and specifications are correct. When we

say correct, we really mean three

different things. First one is that they

capture and fulfill the stakeholder

quote. So they produced a technical

solution that fulfills the intended

stakeholder requirements. Second one is

they're free from errors that they're

actually correct. And the final part of

this is that they're constructible. So

within the realms of what's possible in

terms of the construction that we can

actually build what the drawing say to

do the design core process has to check

these three things. Then it's check

stakeholder requirements. they're free

from errors and that we can actually

build it. The tools that are used to

ensure this is done correctly would be

regular and independent checks of the

design and validation of the original

project requirements against the design.

Once we move into the construction

phase, the drawings get an issue for

construction stamp which means they're

ready to be built. We then go have a

design management process during the

construction phase. So this is the

process to ensure we manage changes to

the design during construction and this

will ensure the design remains correct.

So any times the drawings are changed it

needs to get approved by the design

team. Once the design team check that

the change is okay that it's technically

feasible that it still complies with the

project requirements. The change gets

approved and reissued to the

construction team and then they're able

to build this. So the tools we use to do

this would be RFI. So this is a request

before the fact to change the design.

NCRs where we have some sort of error or

issue during construction and when we're

not able to build what the drawing

specified. And then the final type would

be a direction from the design team to

change the design that's not prompted

through construction. So for whatever

reason the client has required

additional scope, they've required

something additional added to the

design, the designers will integrate

this into the drawings and issue a

design change notice. And so the final

part of our design quality management

system and it's not strictly a part of

design management. However, it's useful

to think of it as part of the same

process is where we take what's finally

been built and rather than checking this

just complies with the drawings, we

actually check it complies with the

requirements. So, this is the role of

the commissioning process where we're

checking that what's been built

functions as intended, not just as

what's been built. To understand

commissioning, we need to understand

systems engineering. So systems

engineering is where we're designing,

integrating, and managing complex

systems throughout their life cycle and

ultimately relating a system as it's

built back to how it functions. So we

can relate a project's initial

objectives and requirements to the

design, the development of the detailed

design, the construction, and then the

testing. So we start with an investment

decision or a decision to proceed with a

project based on the requirements it

fulfills. We then develop a concept

design that fulfills these requirements.

We then move into a detailed design

where we add detail, work out the finer

details, work out exactly what we need

to build. We then go build this and then

commissioning is the other side of this

V. We go from low levels of detail. We

test something at the unit level and

then we continually go through a process

of testing bigger and bigger portions of

the system to where ultimately checking

the entire system functions as

originally intended. So construction

quality assurance checks that what's

been built matches the drawings.

Commissioning is where we're checking

that what has been built functions in

accordance with the project

requirements. So this starts at a unit

or device level. We move up to a

subsystem and then we're checking and

verifying the overall system. So if we

think about this in terms of the solar

farm. So the original project

requirements, the investment decision to

build the solar farm was based on

building a 50 megawatt solar farm. The

design says we need to install 45,000

panels. Construction quality assurance

then checks that all of these 45,000

panels have been installed correctly.

Commissioning through the commissioning

process will then check that the solar

farm correctly exports 50 megawatt. So

if you understand construction quality

assurance is about checking all the 45

45,000 panels were installed correctly.

Commissioning will then energize the

system and slowly check that each set of

panels is exporting the anticipated

amount of power at a certain radiance.

Then was it bringing on more and more

power? Are we reaching the 50 megawatt

export threshold? Okay. So I've spent a

ton of time talking about design quality

management and commissioning. Purpose of

that was to clarify in your mind how we

go from the initial project requirements

throughout the design to construction to

commissioning to checking ultimately

that we've built something that match

the original requirements. Now also said

the design quality management and

commissioning aren't form of the

construction quality assurance process.

The goal of the construction quality

assurance process is to check and verify

that what we've built matches the

drawings and specifications. So now I'm

going to talk about what does a

construction quality assurance system

consist of? What are all the different

components of them and how do they work

together to achieve this goal of

ensuring that what we've built matches

the drawings and specifications. Okay,

so let's map out all the different

components of a construction quality

assurance system across the life cycle

of a project. So we've got the inputs to

the process. Then we've got we've broken

the project life cycle up into three

distinct phases. We've got the planning

phase, the executing phase, and the

completions phase. So the inputs to the

construction quality assurance system

will be the project requirements and the

design drawings. So that's what we're

ultimately checking that what we're

building is correct. We're checking this

against any project or design

specifications and design drawings.

These get input into our document

management system. Now people don't

often understand the importance of an

effective documentation management

system but it is the backbone of the

quality assurance system. The quality

assurance system will not work correctly

unless we have some way of tracking all

the different drawings specifications

and making sure they're correct and are

the correct revision. So that's the

documentation management system

critically important to any construction

quality assurance system. Then what we

do is we take all the drawing and

specifications that define the scope of

the construction work and we turn these

into a work breakdown structure. So we

take the overall project scope, we

decompose it into component pieces. We

create a breakdown of all the different

construction activities. The next thing

we need to do is for each of these

different construction activities, we

need to prepare an inspection and test

plan. So against the specific

construction activity, what checks are

we going to be doing? We also need to

write for each of the inspection and

test plans a series of short inspection

and test check sheets. So these are the

physical check sheets that people are

going to go out onto site and complete

to check the works to be done correctly.

Supporting this will be a series of

other documents like calibration records

for all our test equipment documenting

all the licenses and accreditation of

the workers and supplier quality

assurance systems for any major

materials we're procuring. So they all

support this process and we set up as

well during the planning phase. Once

we've prepared all our quality

management documentation, we move into

the execution phase. This is where we're

delivering the project works. This is

really simple what we have to do in the

execution phase. We just have to follow

the inspection and test plans. We just

have to follow the plan we set out for

each of the construction activities and

go through the steps in the ITP. There

will be changes during construction. So

that's why we have the RFI process where

we deal with changes to the design

drawings and they'll also feed in to the

ITP process. Once we complete all the

inspection and testing for a specific

construction activity, any deviations

from the standard, so any failed

inspections, any failed checks, we need

to document in our punch list. So a

punch list is all it is is a record of

all the defects on the project. We're

going out and doing an visual inspection

of a solar panel tracker and we notice

it's missing cable ties. We note that

down. That gets added to our punch list.

To close out the project, we simply go

through, send people out to fix every

defect and document that all the

deviations, the quality standards have

been correctly documented. We go through

and do a handover walk through with our

client. We show them what we've built.

We show them the records. We show them

all the test records and we get them to

sign over acceptance of the work to

agree that that we've built what we've

said we would in accordance with the

drawings. Additionally, any changes

during construction has to be documented

on the drawings and specifications and

captured in our asbuilt drawing set.

That is the construction quality

management system where we go from the

initial project requirements and we turn

these into a series of checklist against

each of these activities. We verify that

they have been built correctly. We

document any defects in our punch list.

We close out the punch list. We get

acceptance from our client. And that's

all we have to do. Okay, I know I ranted

a little bit going through that

structure, but to make things a bit

clearer, I'm going to go through each of

these individual components step by step

and what it contains. The first one is

project requirements. So, they're the

primary input to this process consists

of the drawings and specifications,

project specifications, and any relevant

standards that we also have to comply

with. These are all the documentation

that define what we need to build. Okay,

the backbone to the system, the

documentation management system. All of

these different drawings,

specifications, project requirements

need to be captured in some sort of

documentation management system, which

is a system simply to control and manage

all the different project documents and

to check that they're correct and the

correct revision. So, we could use

something like teambinder, a connects.

There's a lot of different softwares out

there, but they all operate with the

same intended purposes. They capture all

the different project documents and then

as documents change, we get issued a new

revision of the drawings. There's an

RFI, whatever. This all gets captured

and updated in our documentation

management system. So, we have a single

source of truth we can go to and extract

the correct drawing. So, we've uploaded

all our drawings and specifications into

our document management system. The

first thing we need to do when setting

up our quality assurance system is

develop a work breakdown structure.

Blows my mind how many people miss this

step. But what we need to do need to

take the scope of what we're building,

what we're delivering. We need to break

it down into component pieces. So we

need to break it solar farm down into

earthworks, mechanical installation,

electrical or procurement, however you

choose to do it. The idea is you break

the project down into individual

activities and then the individual

activities we've broken down the scope

into. We then perform inspections and

testing against each of these individual

activities. So all we want to do is

ensure the entire project scope is

covered and no testing activities are

missed. Once we've broken down the

project scope into component pieces,

each of the items of scope we identify,

we need to prepare an inspection and

test plan. So an inspection and test

plan identifies every step in the

construction activity. And against each

of these steps, we document what checks

we're going to do to ensure that

activity is completed correctly. We want

to pick up what could go wrong and what

we're doing to ensure that we either

prevent something going wrong or if it

goes wrong, identify it and correct it.

So the ITP, the structure of an ITP

would consist of a pre-work section

where we talk about procuring the

materials, checking the drawings are

correct, making sure everyone doing the

work is appropriately qualified, a

construction part where we go through

all the different steps of the

construction process, and against each

of these we might do an inspection and

test check sheet, and then a close outer

where at the end of the work, we do any

final testing, close out any defects and

NCRs, and complete any redline markups

to the drawings to document changes.

Once we've completed an ITP, we've

written how we're going to perform the

checks for each construction activity.

We need to submit this to our client to

get their approval. As part of our ITP,

we'll reference a subdocument referred

to as an inspection and test check

sheet. Now again, people call these a

whole lot of different things, but

basically what it is, it's a really

simple, short checklist we complete

during construction in the field to

check something's been built correctly.

So an ITP you wouldn't complete in the

field inspecting the work. That's what a

check sheet is for. So check sheets, one

page, very simple, should come at things

like a pre-pro inspection. So before

you're pouring concrete, you do a

pre-pro inspection checklist or if

you're testing an electrical cable, if

it's installed, you might have an

electrical cable test sheet. So it just

documents every step in the construction

process and at a predefined point, we'll

complete an ITC and check that

everything's done correctly. So our ITP

will reference multiple ITC's. Once

we've prepared all our ITPS and ITC's,

they've been submitted to our client.

Our clients reviewed them, accepted

them, proved them. We then go out,

complete the construction works, and

complete our inspection and test plans.

As we're doing our testing, as we're

doing our checks, we'll identify

failures to comply with the project

requirements. We'll identify issues. So,

we might be missing cables for an

electrical cable or we might be about to

do a concrete pour and notice that the

formwork hasn't been braced and

supported correctly. that's the case.

All these failures to comply with the

project requirements get documented in a

punch list. So a punch list is a record

of all defects and any minor outstanding

works that are categorized appropriately

and given a responsibility to close out.

We need to work our way through the

punch list, close all the defects to

prove that we've correctly completed the

construction works. through this

construction process, there will almost

certainly be changes to the design. So

that's where the RFI or request for

information process enters into the

construction quality management system.

So through construction, there's going

to be changes to design. We manage these

through the RFI process, which is

basically a formal change management

process that when we're changing the

design, we get this approved by our

clients. We get it checked and we get

direction and approval from the client

and the design team before proceeding

with any changes. Importantly, if an RFI

changes a drawing, it needs to go into

the documentation management system. It

needs to go get uploaded the

documentation system so that everyone is

working off the same set of drawings.

There's nothing worse than getting sent

an RFI response, not updating the

drawings in the documentation management

system and someone going out and doing

the work incorrectly because the design

change hasn't been passed on to them.

So, it's critically important that when

there's any changes to the design, these

are getting uprev.

All these changes to the design need to

be captured on a set of drawings

referred to as the red line markup. So

the construction team as they build the

project document any changes in red pen

on a set of drawings called the red line

markups and at the end of the job these

get resubmitted to the design team who

then create an asbuilt drawing set

capturing all of these changes. After

we've completed all our construction

works, finished all our ITPS, closed off

all of our defects, we can then complete

a handover walk with the client. So this

is a joint inspection we complete with

our client or we inspect the work. We

show you what we've done. We show them

our completed ITPs and ITPS. We give

them confidence that what we've built

matches the drawing and specifications.

Purpose of this walkthrough is it gives

them an opportunity to add to the punch

list. So the client might identify

something that they're unhappy with that

they want changed. This is their

opportunity to add to the punch list.

And if it is a reasonable request, so if

it is a failure to comply with the

project requirements, we'll need to go

and fix it. In a lot of circumstances,

what I found in my own experience doing

these sorts of walkthroughs is the

client basically picks up a whole lot of

things they're unhappy with about the

original design. So that's why I find

when you're doing these joint

inspections, it's incredibly valuable to

have a member of the design team that's

somebody like the design manager who you

can complete these inspections with and

they can comment on why the design was

done a certain way. often on these

walkthroughs, yes, they pick up some

construction defects, but a lot of the

time what they're identifying is

problems with the design and it's

endlessly frustrating that then you then

have to go and check all these things

with the design team and you become a

line of communication between the client

and the design team. So that's why I

think it's incredibly valuable to have a

member of the design team there. In

terms of the construction, if they do

add things to the punch list, then the

same with any failed inspection testing,

we simply have to close out these punch

list activities, provide evidence to the

client, so we can then show them that

what we've built complies with the

requirements. Okay. So what we just

discussed then we went through all the

individual components of this system and

how they function to ensure that the

initial project requirements and design

drawings get checked verified and that

what we've built, what we've finished

off creating matches these original

requirements. So what is the biggest

mistake I see people making when they're

setting up, managing, and using a

quality management system on

construction projects? Biggest mistake I

see people making is they fail to

integrate quality management with

contract management. Purpose of the

quality management system is to check

and verify what we've built meets the

original requirements. The original

requirements come from the contract.

That's how the client bases whether they

pay us, whether they don't pay us,

whether we get into disputes is

ultimately comes down to us providing

evidence that what we've built matches

the original project requirement. So

quality has significant contractual

implications both in terms of the

payment process. So whether we get paid

when we get paid and it should be

integrated into the payment milestones

and integrated into the contract. And

this is going to benefit the overall

project because it gives the client the

opportunity to ensure works have been

satisfactorily completed and gives the

contractor an opportunity to justify

getting paid and showing that they've

done the work correctly. So in

conclusion, integrate quality management

with contract management. Follow these

steps. Follow this process to set up and

manage your quality assurance process

and I can guarantee your projects will

become more successful.

Inspection and test plans are an

essential construction management tool.

However, the reality is most people

write and use them incorrectly. That's

why in this video, I'm going to explain

to you everything you need to know about

construction, inspection, and test

plans. So, in this video, I'm going to

go through what is an inspection and

test plan, how they're used, what they

contain, the structure of one, how to

write one to use them effectively to

make sure you're using them to minimize

defects and avoid errors, and finally,

we'll go through an example ITP. So an

inspection and test plan or ITP for

short is a document that outlines the

procedures, tests and inspections

required to ensure that a construction

activity meets the specific quality

standards and requirements. So if we

think about pouring the concrete

foundations for a building, there's a

series of activities involved in this

process. We need to order the concrete.

We need to set up a concrete pump. We

need to place the concrete. We need to

finish the concrete. And then we need to

check that it's all been installed

correctly. The inspection and test plan

documents all the steps in this process

and checks against each of these steps

what could possibly go wrong and how do

we check it's done correctly. So it'll

check the concrete mix correct, is the

placement method correct, is the

formwork being stripped after a certain

amount of time. All these things are

documented in the inspection and test

plan. The ITP contains every single step

in this process and ensures they're each

done correctly and provides evidence and

records that the works have been

completed correctly. So inspection and

test plans are required for all

significant construction works. Things

like piling, condute installation,

concrete pores and any permanent

construction works. But what about

temporary things? What about things like

traffic management or establishing site

facilities? Well, typically you wouldn't

do an ITP for these sorts of activities

because they're non-permanent and

they're not getting handed over to the

client. Sure, you might have a checklist

you follow to ensure things are done

correctly, but it wouldn't follow the

same strict and stringent ITP process.

All ITPS need to be prepared before the

construction works begin. And

importantly, they need to be approved by

your client or relevant stakeholders

before the works begin. So that's a

critical point to note. We write an ITP,

we document how we're going to check

everything's been done correctly, and we

need to get our client to review these

to ensure that they're happy with them.

Okay, so now we understand what an

inspection and test plan is. Let's look

at an actual ITP. So, ITPS follow very

specific structures. You'll have a

heading with the project details. So,

some background, the project name, the

scope of the inspection and test plan,

what work packages it refers to, what

drawings it refers to, any applicable

standards, who wrote it, the date it was

prepared, that sort of information. Then

you'll have say some definitions. So the

symbols, who is doing the inspections,

the different inspection activities and

don't worry, I'll attach a copy of this

to the course not so you can refer to it

yourself. Then ITPs

follow a specific structure where you

have the test activity which will be the

series of steps to complete the

construction work. So you might have

pre-works where it's checking the

drawings are correct, making sure

permits are in place, checking that the

works have been surveyed, the

procurement of materials, so buying all

the equipment we need. So for example,

for this activity, we need to buy

conduites, what applicable standards

refer to the conduites, and how we going

to check with purchase to correct

conduites, construction activities, and

against each of these activities, we've

got the specifications that apply to it.

So what specifications relate to

checking this work's done correctly?

What test method are we going to use?

How often are we going to do the

testing? What are the acceptance

criteria? And who is responsible for

this? So that's how ITPs are structured.

They step go through all the steps in

the process, the different construction

activities, then the specifications that

apply to that activity, the test method

that's going to be used, the timing and

frequency of the testing, the acceptance

criteria, and who's responsible for for

performing those checks. So now we

understand what an ITP document is, what

they look like. The next thing we need

to understand is how to write an

inspection and test plan as a

construction project. engineer or

manager, you're certainly going to have

to produce some of these. So, it's

important to understand how to actually

write one. The steps in writing an

inspection and test fad will be number

one to review the drawings and

specifications of the scope you're

writing the ITP for. Develop the

construction methodology. So, understand

the steps in the process building one.

List out all of these steps. Identify

which detail and information does the

drawing show for each of these steps and

understand what can go wrong. If you

understand what can go wrong, you

understand what needs to be checked to

ensure it's done correctly. Fill out all

the relevant sporting information. So,

the relevant drawing and specifications,

the frequency, these sorts of things,

and then submit it to the client for

approval and get them to provide some

feedback and comments. So ultimately

when you're preparing an inspection and

test plan, what you really want to be

documenting are the checks we do around

the things that can go wrong. That's the

ultimate goal of why we're preparing the

document. We want to create a big list

of everything that could possibly go

wrong for that specific construction

activity and then check that we're not

not going to make those mistakes. So for

example with concrete works we could

incorrectly get the survey set out. So

we might the surveyor might be working

off the wrong set of drawings or the

drawings might have a wrong height on

them. Could use the wrong concrete

material. We might procure a type

concrete that's not applicable to that

scope. We could use the wrong placement

method. There might be some standard

where we can't allow concrete to drop

more than 2 m. It might not be compacted

or vibrated properly and get air

pockets. We could use the wrong type of

formwork or the formwork might not be

correctly braced so the concrete

collapses. We could have the

reinforcement move during the pour so we

no longer get the correct cover on the

reinforcement. We might miss installing

casting items. Maybe there's a service

penetration because we haven't checked

those are installed before we called the

concrete. We missed doing them or we

missed installing casting items like

bolts. When you think about it, for any

construction activity, there's a lot of

things that can be done incorrectly. So,

our job when we're writing the ITP is to

come up with a list of all the things we

need to check to ensure that we're not

going to be making these mistakes. Each

of these mistakes we could possibly make

are going to relate to a step in the

construction process. So the basis of

our ITP is all the steps in the process

we follow to deliver the works. Now

regardless of the specific construction

activity, there's some broad steps that

any construction works we're going to

follow. So these I like to think of as

pre-works. The stuff we do before we

start the construction activity, the

actual construction activity, and then

the close out activity. So the pre-works

will be things like design. So checking

the drawings and specifications

correctly. If we're procuring materials

from a supplier, they might have given

us shop drawings. We might need our

designers to approve these shop

drawings. So they're all the design

activities. We'll need to buy materials.

So basically, we want to check we bought

the correct materials and they match the

specifications. And we also had any

handover from previous tread. So for

example, if we're installing underground

electrical cables and civil contractor

has put in the conduites, has the civil

contractor checked that all the

conduites are free from debris and

they've been roped correctly. So they're

all the handover activities. Then we

move into the construction. So this is

really step by step the construction

activities involved in that task and

checking against each of those what

could go wrong and then the closeout

activities. So any final testing we do.

For example, for concrete, we might get

concrete testing done, documentation of

any asbuilt drawings or changes to

design and then hand over to subsequent

trades or final acceptance by the

client. So those are the steps we want

to document for every single activity.

Next to each of the steps in the

construction work, we document the

relevant specifications. So for each of

these steps, there'll be a specification

that governs whether it's done

correctly. So these specifications might

be from project specifications,

notes on drawings or relevant standards.

For example, if we're installing

concrete reinforcement, there'll be a

specification that says the cover we're

allowed on the reinforcement and then

that's what we need to check. So we're

allowed 50 mil of cover in the

specifications. We check that we've got

50 mil of cover. We allowed 100 mil. We

check we've got 100 mil. So once we've

documented the steps in the construction

work, the relevant governing

specification, the next thing we need to

document test method. So what is the

test or check we're doing to ensure the

works are done correctly. So these could

be specific to a discipline. So be

concrete testing or compaction testing

for earthworks or they could be generic.

So visual inspections, recording photos

or getting material dockets. Next, we

need to define the timing and the

frequency of these checks. So, how often

will this testing be undertaken? So, it

could be time based. We might do the

checks every day or every week or it

could be activity based. More common for

construction works, there'll be activity

based checks. For example, every lot of

earth work. So, if we're installing

underground conduites, it could be every

20 m of trenching. Or we might do it per

concrete pore. So every concrete pour

we'll do a pre-pour inspection. We'll do

an inspection while they're placing the

concrete and then we'll do a series of

postpour checks. So more likely your

timing and frequency is going to be

activity based. And then we need to

define our acceptance criteria. So what

is the standard the testing has to be?

For example, for our concrete testing it

might need to achieve a strength of 32

MPa within 28 days. for our if we have

installed an electrical cable and we're

doing an insulation resistance test

might need to achieve greater than 50

megga ohms when we do the test. So these

could be test results, they could be

subjective verification by an expert.

They could be records like photos or

they could be certain desirable

criteria. Really depends on the specific

check we're doing or the specific test

as to the acceptance criteria. The final

thing for each of these different steps

in the construction process, we need to

define who is responsible for approving

it. So these could be internal to our

company or these could be external

experts we engage or it could even be

the client who has to check. So it might

be subcontractors doing it for us. It

might be an engineer or a project

engineer, could be a supervisor, could

be the client or their owner's engineer

or it could be another relevant

stakeholder. So it's important to define

for that specific activity who is

responsible for checking and approving

the checks. Now when we're defining who

is responsible, we also define what

level of oversight they give the step.

So there's three different types of

responsibility. Could be a hold point

where works cannot proceed past this

point until that person's approved it.

So, for example, on a concrete paw for a

pretty poor inspection, it might be a

hold point for the client's structural

engineer. So, the client might need to

go out, inspect the reinforcement before

they give approval to Paul Congre. It

could be a witness point where they just

have to be told about it, but they don't

necessarily need to inspect it. Or it

could be a review point where they

review it after the fact. So it really

depends on defining what level of

inspection the responsible party needs

to undertake. Okay. To make this all a

bit more realistic, let's go through and

do an example of a conduit installation

or a technique. So if you don't know

what condute installation is, it's

installation of underground pipes that

people use to install and pull

electrical cables through. So it

involves trenching, laying the condute,

and then back filling and compacting. So

we're going to go through and do an

example inspection test plan of condute

installation. So you can see people

practically what's involved in an ITP.

Okay, let's start with what would be the

input to this document. So we've got the

design, the drawings and specifications

that show where the trench is going and

the details of the trench. So, I've got

simplified example here that shows a

cross-sectional view of the trench which

shows the conduites in orange. There's

three 100 mil electrical conduites.

They've got 600 mil cover and there's

bedding sand around the conduites. And

then we also need to install a marker

tape which shows where the conduites

are. The methodology is they're going to

excavate. They're going to lay the

conduit and then back fill. There's

specifications around the materials

we're allowed to use. We need to have an

excavation permit in place before we do

any works. And we need to do compaction

testing and mandrel testing. So mandrel

testing is when you pull a sort of like

a plastic ball through the conduites to

ensure they're clear of debris and that

there's space in them to pull cables

through. So we need to do compaction

testing and mandle testing. Okay, let's

start with our table from our ITP. So

this is the structure we're going to

have to populate. We're going to have

our pre-work. So these will be checking

the drawings are correct, ordering the

materials, our construction works which

will involve those steps I went through,

excavating, installing the conduit to

back filling and then any closeout

activities. So now we go through and

populate this table with every step in

the process and then all the other

relevant information against each of

these steps. So for the design check,

we've got the issue for construction

drawing set. We need to check that this

is prior to performing works and the

acceptance criteria is before starting

works we have an issue for construction

set of drawings and approved RFIs

requirements around the procurement of

materials. So we need to procure the

conduit the conduites we procure have to

comply with AS3000 the design

requirements and the project

specifications. We're going to check

this each delivery and the acceptance

criteria is we're going to collect every

single delivery docket we get conduites

and attach these to our ITP and the site

engineer is responsible for this. Then

we've got our construction activity. So

the trench excavation will be the

activity is excavating the trench to the

correct design depths the relevant

specifications

and we're going to every 20 m we're

going to check this is done prior to

condute insulation and we're going to

get the surveyor to check the depth of

the trench against finished service

level. So every 20 m the surveyor is

going to check that the depth is correct

against the finished service level. So

as you can see relevant specifications,

the testing we're doing, how frequently

we're doing the testing, what the

acceptance criteria is, and who's

responsible for the checks. But yeah, so

once we've written our ITP and prepared

it, who has to approve it? So

internally, the project quality team or

any managers we have would typically

approve it. Then we need to send it

externally to the client to approve.

This is critically important because we

want the client to review how we've

written the ITP and make sure they're

happy with the checks we're doing

because at the end of the day, at the

end of the job, we're going to submit

all the ITPS for them with their

acceptance and that's how we're going to

prove to them we've correctly delivered

the project. So, it's important that

they are allowed to make any comments

that they're happy with the level of

testing we're doing, that they believe

it also complies with the standards, but

it's going to make closing out the job

at the end of the project a million

times easier. And then once we move into

construction, all we have to do is

complete the ITPs as we're completing

the construction works. Simple as that.

The effort we put into managing process

is in correctly writing the ITPS

documenting all the checks correctly and

then all we're doing as we move into

construction is going through step by

step ticking off doing all the checks

getting all our delivery dockets

organizing all our testing getting

photos and records. It's easy as that.

Then when we're done at the end of the

job we submit them to our client and we

can prove we've correctly completed the

works. We're going to minimize the

number of defects we have. Any defects

we do get, we'll easily be able to

address and we'll have records of where

those defects start.

In this video, I want to teach you how

you can become a better construction

project manager by more effectively

managing non-conformances.

Non-conformances can increase project

costs by 10% and delay the schedule by

around 7% based on a study by the

construction industry institute. So, in

an industry with razor minimum profit

margins, non-conformances are a good

place to put your time and attention and

focus on effectively managing them to

ensure your projects are a success.

Okay, so in this video, we're going to

be covering what a non-conformance

report is, the difference between a

non-conformance and a defect, the

components of an NCR, how to prepare an

NCR, and then finally go through an

example NCR. Okay, so an NCR is a formal

document used to identify, track, and

resolve instances where a project does

not conform the specified standards,

requirements, or plans. So we've already

defined a defect as any failure to meet

the project requirements. An NCR is just

a significant defect. So if a defect is

significant to the operation of the

plant, to the functioning of what we're

building, or even commercially

significant, so if it's a large dollar

value item, we would turn that into a

non-conformance report. So a defect is

any failure to meet the project

requirements. And defects can be both

minor and major. Minor defects might be

something like missing labeling or

electrical cabling. While a major defect

could be an incorrect cable installed

that needs to be cut out and replaced

and it has a significant cost and

prevents operation of the plant. So it's

significant also to the operation. NCRs

are a formal process we go through to

capture significant defects. Depends a

bit on the company and project specifics

of how they choose to manage them.

However, NCRs have the characteristic

that they're significant. So, going into

more detail on this, you should raise an

NCR when a defect is commercially

significant. So, it could have

implications with the contract we have

with our clients or the contract we have

with our subcontractors. It's going to

take some time to fix or it's going to

have a significant cost. Additionally,

we should raise a defect when we want to

proceed with some sort of investigation

root cause analysis to work out why this

defect has come up or we should raise an

NCR when we want to change the project

standard. So, because of we can't put

over raising close out a defect the

normal ways by just rectifying it to

meet the original standard. If we want

to raise an RFI to the design, change

the original standards, then we should

also create an NCR. NCRs have several

different components. So, first off,

we'll need to identify and define the

NCR. So, talk about what the scope is

and what happened. We then need to

analyze the root cause. So, work out

what happened and what the underlying

cause of the defect was. We'll need to

work out how we're going to resolve the

defect. and then we'll need to work out

how we're going to prevent the same

thing happening again. So, first off,

when we identify an NCR, so NCRs like

defects will be identified during

inspection and testing. So, as we go

through and complete our ITPS, if

there's any failures to meet the project

specifications that will create a

defect, the significant defects become

MCRS. Or we could identify them through

an audit. So, we might go out and do

systematic audits and checks of

processes or products. And we could also

identify in sales like this. They can be

identified by a client, by the

contractor or by subcontractors. So

really anybody involved with or working

on the project can identify NCRs. So the

next component of the NCR is the

analysis. We need to analyze what

happened, why it happened, and what we

can do to fix it. So we identify the

cause of the NCR. We identify who's

responsible. Now this is important

commercially. Correct. identifying the

responsibility of rectifying the defect

cuz remember we said NCRs with

significant defects. So the significant

cost and time associated with them. So

appropriately identifying who is

commercially responsible for fixing it

is important. And we also want to

identify why did the NCR happen. Could

it was it due to incorrect design

drawings? Was it due to incorrect

procurement of materials? Or was it due

to incorrect workmanship? We then need

to come up with a resolution for the

NCR. So there's a couple of different

things we could do and depending on what

we choose to do about the NCR will

require different approvals from

different parties. The first one,

easiest way to fix it would be to rework

the defect to meet the original

standard. We simply redo the activity to

meet the original project specification.

The second thing we could do is we could

accept the defect as it is without

repair or we could repair it with

concession. So we could repair it to

meet a new different standard. These are

different because number one reworking

to meet the original standard. We would

need no change to the project

requirements which means we need no

approval from the design or no approval

from the client because all we're doing

at our own cost. We're fixing the defect

to meet the original project

specifications. Options two or three

where we accept the defect as it is or

we repair it to meet a new standard will

require some level of rework to meet a

new standard. In that case, we need to

get approval from the client and

approval from the designers to change

the project specifications to ensure

they're happy with it and to ensure they

accept it. Okay, let's wrap up with

going through an example of a

non-conformance report. So, this is the

type of form you'd fill out when raising

an NCR. We'll go through the different

structure of the form and talk about the

specific example NCR we're talking

about. So, this NCR was part of an

imaginary project called the Western

Road project and it occurred on 27th of

May, 2021. So at the top we're just

filling out the details of the NCR the

facts what happened the relevant

documents all these sorts of things. So

the NCR name was underbore missing

tracer wire and the engineer responsible

the work package was the combined

services trench so installation of

underground conduites and the

subcontractor was under boring solution.

the design package and reference. So the

drawings that documented the work that

was being undertaken and any relevant

standards and specifications. There's a

relevant quality lot. So what quality

lot was the work being undertaken under?

And then there's a description of the

NCR. So let's look at the description.

So the standard design details for the

underbore as detailed in the drawing

show 300 mil electrical conduites and

one 100 mil communications condute.

Additionally, a 5 mm steel tracer wire

was meant to be installed as part of the

bore. However, under boring solutions,

the contractor drilled the bore, pulled

through the electrical conduits.

However, they failed to install the

tracer wire. The bore was sealed. They

finished the work and only after did

they realize the tracer wire was

missing. We've also got it as a product

NCR. So, you can have a product NCR or a

process NCR. Product NCR is a failure to

meet specifications relating to the

product we're delivering. Process NCR is

a failure to follow process. So this is

related to the product. So the product

is the finished underbore. The design

showed steel trace a wall and we failed

to install this. So what are we

proposing to do about it? So we're

proposing to repair with concession. So

we're not reworking to meet the original

standard. We're reworking to meet a new

standard and so this is something that

would have to get appro approved by our

client and the design team. So we're

asking to install a 5 mil tracer wire

within one of the spare 100 mil conduit.

So the original design showed that the

steel tracer wire was installed

separately to the conduites. However,

we're asking to install it within the

electrical conduites and we're giving an

explanation for why this is okay to do

and how we're going to install labeling

as well to show why it's been done like

this. We've got a cause of the NCR which

was people. The subcontractor failed to

review the drawings properly and the

contributing cause was the contractor

did not properly understand the design.

The process improvements is that we're

going to update our inspection and test

plans to ensure that future underbs we

have a representative from our own team

on site checking that this is done

correctly. So we've got corrective

action what we're proposing to do about

the defect. We've got gone through the

cause the contributing causes and how

we're going to improve processes in the

future. We then take this NCR. We then

submit it to the design team and the

client to get their approval to ensure

they're happy with doing it. Once

they're happy with the proposed

corrective actions, we then go out

physically do the works, close it off,

and then we could successfully close the

NCR. So through this process, you can

see how we've encountered an issue with

the installation and we're going through

a process to resolve this to ensure

ultimately our client is happy with the

product we're producing.

This video is going to be all about how

to more effectively manage construction

project defects. The goal of this video

is to teach you about the defect

management process on construction

projects so you can reduce the number of

defects on your projects and

significantly reduce the overall cost

and the time it takes for you to deliver

the project. According to research by

the construction industry institute

rework due to defects can cost between 4

to 6% of the total project budget.

That's why in this video we'll define

defects or talk about what they are.

We'll talk about why they matter, why

they're critical to manage as part of

achieving project success, talk about

the different types of defects, and then

talk about the process to manage,

eliminate, and reduce construction

project defect. So, starting off with

the definition, put simply, a defect is

any failure to meet specified

requirements and standards for the

project. A defect is as simple as that.

It's any failure to meet the specified

standards or requirements. So some

examples of typical defects on

construction projects. On a road

project, we might have poor line

marking. On electrical cables, we could

have missing labels. In a concrete

structure, we could have cracking. In

the basement of a building, we could

have water ingress. Or on structural

steel, we could have missing torque

marks on the bolt. So these are just all

small typical examples of the types of

defects you come across on different

construction projects. So all of these

different items have the same

characteristic. They're failure to meet

specified standards of the project. So

we go out, we deliver a construction

project. As part of the quality

management process, we're checking and

verifying that what we're delivering

meets the standards that a defect is any

failure to meet these specified

standards. The ultimate goal of a

quality management system is to

eliminate defects, to have zero defects,

to hand over a finished project that

complies with all the specifications and

standards, and there's no deviations

from these requirements. So, why do

defects matter so much on construction

projects? Well, to answer this question,

you need to understand the 8020 rule. If

you've ever worked on a construction

project, you'll find that managing the

works, 80% of the works take 20% of the

effort and then the final 20% takes 80%

of the effort. There is always a ton of

small items at the end of the project

that just consume so much time,

attention, and resources to close out.

And closing these out successfully is

critical to getting paid on time, to

finishing the project successfully,

handing over to our client. And time and

time again, you see construction

projects fail, even though for the

majority of the work, they've been

delivered successfully. However, through

the closeout phase, there's all these

legacy defects that quickly chew through

the project's profit margin. Extending

on this, we can categorize the reasons

defects matter. And I'm going to explore

each of these in more detail down to

safety, value delivered, the customer

and stakeholder satisfaction, contracts,

cost, and time. So the first reason

managing defects is critical to managing

construction projects successfully comes

down to safety. The origination of any

design requirements or specifications

that go into the project documents often

come from safety standards. For example,

the strength of concrete on a bridge is

critical to holding up all the cars

traffic that will go across it. If we

don't meet those concrete strength

requirements, we can't prove that the

bridge is actually safe for all those

different people to use. If we think of

another example, insulation on

electrical cables. If we don't have

proper insulation on our cables, we

could have an electrical fault that

could start a fire. So ultimately

through the quality management process,

we ensure that what we deliver complies

with the specifications and standards,

which directly ensures that what we're

building is safe for people to operate

and to use. A real world example of this

was the Surfside condominium collapse in

Florida and the US. So failed

waterproofing on the construction of a

12story building led to corrosion in the

steel reinforcement with the structure

ultimately collapsed and killed 98

people. So you can see deviations from

the original standard which was

waterproofing of the concrete led to a

legacy issue that caused corrosion to

steel reinforcement and ultimately the

integrity of the structure of the

building leading to a collapse that

killed 98 people. So when we're talking

about defects, we're not just talking

about money. We're also talking about an

ethical responsibility to ensure that

what we're building is safe for use. The

next reason defects matter is that the

elimination of defects directly leads to

additional customer value. Let's think

about this. The project specifications

and standards document what we're

getting paid to build. Ultimately, each

of these standards, each of these

specifications directly relates to the

value we're creating for the customer.

So, if we have defects in the product

we're producing, we're ultimately

producing something that isn't as

valuable. So, eliminating defects

ultimately increases the amount of value

delivered by the project. This then

relates to my next point, which is the

less defects we have, the more

stakeholder satisfaction we have. So

defects will ultimately impact the

perception of the project by the client.

So even if they're aesthetic and minor

defects, we could build something that's

perfectly fit for use, perfectly safe to

use. However, if it's got a whole lot of

cracking in the concrete, scratches on

the walls, ultimately the way our client

sees it, the way our client perceives it

is that we ultimately haven't delivered

something valuable, they've got a poor

quality product. So they go to

satisfaction and defects are also

directly related. Next, defects have

important commercial implications. So

when we're talking about the contractor

building the project and they're

ultimately responsible for delivering

the project in line with the

requirements and specifications, this

requires them to produce product that is

free of defects because ultimately

they're getting paid to deliver what the

project specifications and requirements

say they need to do. So ultimately

there's significant contractual

implications through contracts. Defects

can impact payment and they can also

impact contract completion. So getting

your security back, closing out the

project at the end of the job. You see

this a lot typically around payment on

construction projects. So payment is

always an issue on construction

projects. Cash flow is the lifeblood of

the construction industry and payment is

a powerful motivator. So regularly on

projects you see contractors make

payment claims and principles reject the

claims not because they haven't

necessarily done the work but because

they haven't done the work to the

required standards and they can't prove

that they have done so. The principal is

meant to pay the contractor based on the

value of work they've completed and

often there's a dispute around valuing

this work based on what both parties see

as outstanding work or outstanding

defect. So defects will always relate to

payment on construction projects. This

then directly leads on to the next issue

which is cost. So rework ultimately

costs money. Cheapest way to deliver a

project is to do it once. Do it right

the first time, not to come back and do

the same task again because you messed

it up the first time. So the less

defects we have, the less money we're

going to spend. Defects can consist of

both incomplete work, so work we didn't

do the first time because we didn't have

the materials, because we didn't have

the access for whatever reason, but also

defects can consist of rework where we

haven't done the work correctly, so

we're coming back and doing it again.

Finally, defects matter because they

impact the duration of the project. So,

quickest way to deliver a project in the

same way that the cheapest way to

deliver a project is to do everything

correctly and completely the first time.

If we have defects, if we have

incomplete work, if we're coming back

and doing things twice, it's going to

suck up our resources and it's going to

push out the duration of the schedule.

So, the quickest way to complete a

project is to do it without defects,

without rework. Okay, let's now talk

about all the different categories of

defects. So, what are all of the

different types of defects that exist on

construction projects? So the first one,

we can categorize defects based on their

cause. Whether they're caused by

incorrect design, incorrect construction

methodology, the wrong materials being

used, missing equipment, these sorts of

things. So defects can be broken down

based on their cause. We can break down

defects based on their significant. So

are they aesthetic only? Is it paint

markings on a wall or is it a

significant defect that impacts the

operation of the asset? Is it a missing

electrical switchboard? So, we can break

them down based on the significance. We

can also break them down based on who's

responsible. Is it the responsibility of

a subcontractor who's done something

wrong? Is it because it's an incorrect

design? Is it the responsibility of the

designers to fix and get an answer to?

Then finally, we can break them down by

the type. Are they due to incomplete

work which we're waiting on materials to

do, or is it because of an incorrect

installation? So some these are some of

the different ways we can categorize and

break down defects on a project. So how

do we manage defects? We know defects

are a problem. We know they cause

significant

harm to a project success. What can we

do to manage them more effectively?

Well, the quality management process

ultimately exists to eliminate defects.

So through the quality management

process, we're directly addressing the

presence of defects on a project. Our

goal is to deliver a product that

fulfills the project requirements. So

the quality management process is there

to identify and then close out and

ultimately try to eliminate defects. So

let's look at the quality management

process and where defects are addressed

and managed through this process. So it

starts off with as inputs the quality

management process. We get the project

requirements, the design drawings and

any contract requirements. We then

develop a quality lot structure. So this

will be a list of all the work we have

to do on the project. The same as a work

breakdown structure. And against each of

the individual construction

requirements, we develop inspection and

test plans. So an inspection and test

plan is a document we use to check and

verify that the work has been done

correctly. Once we've developed our

inspection and test plans, we'll go out

and we'll complete the construction

works. Against each of the activities,

we do our inspection testing. where we

fail inspection and testing, we record

that as a defect, a non-conformance, a

failure to meet the project

specifications. These go into our punch

list. We then work through our punch

list, closing out all of the individual

defects. And then when we've

successfully completed the inspection

and testing for some work, we've closed

out the defects relevant, we can

successfully close out project work for

that portion of the project. So that's

the quality management system. we use to

ensure we're identifying defects,

recording them, and closing them out,

and then handing over a product that's

free from defects.

What's involved in completing and

handing over a construction project so

you finish successfully, make your

client happy, and get paid on time? In

this video, I'm going to explore the

completions management process on

construction projects. A study by KPMG

found that 69% of construction projects

fail to be completed on time, often

caused by defects and rework. So project

completions management is a critical

part of construction project management

and understanding the completions

management process is going to help you

more successfully deliver projects and

accelerate and grow your career in

construction project management. So in

this video I want to talk about what is

project completions, why it matters, the

difference between quality management

and completions management, the

different types of project completions,

the requirements to complete a

construction project, and some tips on

how to achieve project completions on

time. So what is project completions?

Well, throughout the course of a

construction project, we take a set of

drawings and specifications. We build

the project according with these

drawings and specifications and then we

come to the end of the project. What we

need to do here is we need to take the

finished product we've built. We need to

hand it over to our client. So we need

to get them to accept it. We need to

finish the project and we need to hand

it over successfully to our client and

finish our responsibilities. The client

ultimately wants to make sure they're

getting what they paid for and they want

to make sure there's a smooth transition

to the next phase of the assets life

cycle which is the operation maintenance

and usage phase of the asset. So the

project completions management process

is how we as the builder as the

contractor we facilitate this process

for them. So project completions if we

want to give it a more professional

concrete definition. So project

completions is the process through which

deliverables are finished, inspected and

handed over to the client, ensuring the

project meets the contract requirements

and quality standards. So now that we

understand what completions is, the next

question I want to answer is why does

completions matter? So the first reason

completions matter is cost. Poorly

managed project completions leads to

increased defects and reworks for us the

contractor to incur. An extended

allocation of project resources to

closing out the project. So these are

things like management staff and

supervisors that need to stay on the

project for an extended period of time.

And the final one is we'll incur

liquidated damages and contractual

penalties if we fail to hand the project

over on time to our client. So a client

will hit us with contractual cities

which will also hurt the project's

bottom line. The second reason project

completions matter is because of

contract. So directly related to cost is

contracts. So there's contractual

requirements around project completions.

Contracts will specify a certain date we

need to finish the project. The

practical completion date of the project

and the completions management process

is there to ensure we finish the project

on time. We're contractually obliged to

meet these dates. And as I just said

before when I was talking about costs,

if we fail to meet these dates, our

client is justified in hitting us with

liquidated damages and delayed penalty

costs. The reasons completions matter is

it matters to the client. So the on-time

completion as per the requirements is

one of the key metrics the client will

look at in terms of justifying project

success. The client wants to be able to

use the asset by the date in the

contract. So incomplete project work

will also damage our reputation in the

eyes of the client and it will damage

the perceived value of the project. So

now that we understand why project

completions is critically important the

client in terms of securing new work the

cost of the project and we're

contractually obliged to ensure we

achieve it. And now I want to talk about

the relationship between project

completions and project quality

management because quite often I see

people blur the two into one broader

topic. However, quality management

completions management are related but

different. So project quality management

as we know is the verification and

validation that what we built matches

project requirements.

Completions requires that the quality

activities have been completed

correctly. That's the core requirement

of project completion. So project

completion is to hand over the project

successfully. We need to have completed

all the quality activities. So we need

to have checked that everything we've

built matches with the project

requirements and we can provide evidence

of this to our clients. So now we

understand why completions matter and

how it fits into project quality

management. Let's talk about the

different types of project completion.

There are several different types and

definitions of project completions that

exist and they vary depending on the

degree of outstanding works and how the

finished asset is accepted for use. So

what are the different types of project

completion? Well, the first one we've

got is substantial completion. So

substantial completion is where we get

operational use of the asset and the

client can use whatever we've built

except for some minor aesthetic defects.

Second type is final completion. So

final completion is where the project is

fully complete with no punch list and

we've accepted and can take final

payment from the client. Third type is

conditional completion. So this is where

completion occurs under certain

conditions. For example, if it's a

building, we might get a temporary

certificate of occupancy contingent on

us fixing some important outstanding

works or we might get partial completion

where this is certain parts of the asset

get accepted and finished for use.

However, we still need to finish other

parts. So, the the piece of

infrastructure we've developed is

partially usable. So now that we

understand what completions is, the

different types of ways we can achieve

project completion, let's talk about

what's required for project completions.

What do we need to do to successfully

hand over the project to the client? And

we'll talk about the sources of these

requirements and the types of different

requirements. What are the different

completions requirements? Well, the

first one is dependent on the contract

model. There might be a contract model

where we're designing, building

something, and maintaining it for 2

years. So then our completions

requirements come in after 2 years of

maintenance. It will depend on the

project specific. So the type and nature

of the project. If we're building a

power plant, our completions

requirements will depend on being able

to export electricity. If we're building

a train station, it will depend on

opening that train station to the

public. It will depend on specific

client requirements. So this client

might have specific requirements or

systems that we need to use to achieve

completions. For example, they might

have an asset management system. And as

part of our project completions, we need

to upload all the different assets we

built for the system. Then finally,

there'll be internal processes that

govern completions requirements. For

example, to close off a project, our

company might require that the

electrical license holder has done an

inspection of the project and is happy

with it. So these are all the different

sources of completions requirements.

Now, let's look at what are the

deliverables we need to complete to hand

over a finished product. And to me, this

is the crux of where the topic is. So,

I'm going to go through all of these

different ones and look at what specific

requirements exist around achieving. The

first one is construction complete. So,

this is the physical completion of the

construction works and making the asset

ready to use. So if we're talking about

a building that will come down to a

certificate of occupancy, talking about

a solar farm, this will be exporting

power to the grid. As part of finishing

the construction works, we also need to

complete our quality assurance. So these

are the checks and verifications we make

to make sure what we've built is

correct. So that's how we prove that we

have in fact finished the construction

works. This will come down to inspection

and testing, documentation, recording

everything, getting our client to sign

off any hold of witness points, and

compiling and submitting all of this

documentation. We'll also need to

complete handover walkthroughs. So,

these are joint inspections with the

client to show them what we've built and

get them to sign off and accept that

they're happy with it. These

walkthroughs, we give the client an

opportunity to inspect the works and

raise any defects that they've picked up

so we can add them to our punch list.

And as I was saying when I spoke about

handover walkthroughs in project quality

management that design issues often

arise. So it's important to have a

member of the design team present on

these walkthroughs. Commissioning is

also an important part of project

completions depending on the nature of

the project. Now for a bridge project,

you're not going to have a commissioning

process. However, for any mechanical or

electrical projects, you'll

commissioning will be a large part of

the project. So, this will be function

testing the installed systems to ensure

they operate as project requirements.

Commissioning will contribute to the

punch list. So, any defects picked up

through the commissioning process will

also need to be closed out. And there

may be some weakness testing. So, some

testing that the client needs to

witness. We also need to close out all

of our defects. So these will be

identified during a quality management

process, commissioning or handover

walkthroughs. We need to close out all

the different punch list activities so

that a client accepts to finish work and

any outstanding minor cosmetic defects

we might be able to close out after

practical completion. But that would

require acceptance from the client. To

get completions, we'll also need to

prepare and submit our asbuilt drawings

to the client. So these are the set of

drawings and specifications we maintain

during construction. we documented any

changes on. We send these back to the

design team. They'll draft a new

revision of the asbuilt drawing set

which we'll also need to submit to our

client. In certain circumstances,

depending on the completion

requirements, but I've seen it on quite

a few projects, clients will want an

asset register. So, they'll want a list

of everything we've installed documented

and recorded so we can submit to them

showing serial numbers, manufacturing,

lead time, supplier, contacts, all these

sorts of things. We may also need to

hand over spare parts. So, say we've

procured a certain type of light

fitting. We've ordered 100 of these

light fittings. The contract may specify

we need to hand over 5% of the installed

spare parts. So, we'd have to hand over

five light fittings. And this just helps

the client when they're going into

maintenance that if they have a fault

that they've got spares available to

change them out. In addition to spare

parts to replace, the client may also

require us to provide any special tools

or maintenance equipment to run the

asset. And we may also need to prepare

and submit an operations maintenance

manual. So this would be detailed

maintenance instructions for how to run

the asset, how to manage whatever we've

built. So this will document things like

the frequency, the need to perform

inspections, the different types of

inspections and tests, corrective and

preventative maintenance, how to do

fault fighting or certain supplier

context. So this is basically a big

document that shows clients how to run

the asset, how to maintain it, and how

to use it. documents all the supplier

contacts and basically just makes the

way for them to go from the construction

phase to the operations maintenance

phase much easier and smoother. In

addition to the operations and

maintenance manual, they might also want

us to conduct a series of training

sessions. So these will be training

sessions to familiarize the operations

and maintenance team, the usage team

with the plant. So we'll have to show

them how to use it, how to operate it,

the different types of faults. We might

have to give them a list of loginins and

passwords, if we've created any software

that they'll have to use. Basically,

just all these sorts of types of things.

So, it's really again about making the

process for the client from moving to

the construction phase, the operations

and maintenance phase as easy, simple,

straightforward as possible. Depending

on the contract requirements, we might

have maintenance or a defect liability

period we need to work through. So this

is where us as the contractor for a

certain period of time are responsible

for providing continued maintenance and

defects rectification. This might be a

2-year period where we need to come to

site and come back to rectify any

defects or faults arising from the

construction activities. And while this

won't impact our initial project

completion at the expiration of the

maintenance period, we'll need to

perform another completions process to

show that we've completed this

maintenance correctly. So again, this

will depend heavily on the specific

requirements in the contract. Depending

on the specific project requirements,

there could be a whole range of other

completions requirements like

sustainability requirements, green star

requirements. We need might be some

building or plant tuning where we're

helping with figuring the commissioning

and the operations to maximize the plant

output. You might have to give them

certain permits, licenses, certificates

of occupation or hand over a pack of the

different warranty information for all

the different spots. Any of these things

will depend highly on the project

specifics. But as you can see, all this

documentation is there to make the

transition from the construction phase

to the operations and maintenance phase

as easy as possible. To manage

completions effectively, we need to

submit everything to complete the job.

So that's why the completions management

process is all about identifying

everything we need to submit and

starting working on it as early as

possible to hand it over on time. So my

tips to make sure you hand over your

construction project on time is to treat

completions as an individual function,

an individual set of activities and

document these in the project schedule.

Document all of these completions

requirements where they're going to be

reported on and where people are going

to see them and they're going to see if

they're slipping. Document these

requirements early and make every effort

to submit them progressively. It's the

only way you're going to hand over your

project on time is to start thinking

about completions in the planning phase.

Document all the requirements and work

through the process methodically. The

same as any other function, the same as

any other task on the project.

So, we've pretty comprehensively covered

quality and completion systems and how

they work. Now, let's talk about where

things tend to go wrong. How do mistakes

within the system cause issues with

time, money, and credibility? By far the

biggest mistake I see is people

underestimating the importance of

document control. A manager once said to

me, "Document controller is the most

important person on the project." It's

always stuck with me and increasingly as

I progress in my career, I see more and

more how true this comment was. The

amount of avoidable mistakes and chaos

I've seen from people building off the

wrong sets of drawings, avoidable

reworks, cost blowouts, hours lost

chasing missing test reports,

construction projects delayed from

missing drawings, incorrectly sent RFIs.

All these issues just cause absolute

nightmares and chaos on projects.

Construction projects generate hundreds

if not thousands of documents. And if

you need a system to manage and check

their correct and maintain version

control cuz if you don't, it will cause

you absolute nightmares. The second

mistake I see all the time is people

over complicating a quality assurance

system. Every project you go on has

someone who says, "We do things

differently here. We're using this

special fancy system, but all they're

really doing is reinventing terminology

and over complicating something that's

really not that hard. Quality assurance

system is really about defining what

testing we're going to do, doing the

testing, and submitting it at the end.

Doesn't need to be any more complicated

than that. You don't need to come up

with your whole range of different

terminology and words. All we're really

doing is checking things against

requirements in a systematic way. It's

not rocket science. So, always try to

keep it simple. The third mistake I see

a lot is that people just let quality

assurance get out of hand. Quality

assurance systems don't fail overnight

with some dramatic failure. What happens

is they tend to slip a little bit each

day when people are busy and before you

know it, you miss one inspection. You

skip a few photos. You forget to file a

checklist. And then suddenly, you're

writing NCRs because you haven't

followed the process. You're searching,

spending hours searching for missing

test reports. Your client's not paying

you or withholding pay payment because

you can't submit a check. Your

management's getting cross at you and

you're burning days in admin and stress.

The lesson is just to stay on top of it.

Make it a regular practice. Quality

assurance is all about discipline, not

scrambling. Next big mistake I see is

people ignoring requirements. Now this

is very much to do with commissioning,

but people not to tend to think about

handing over the project till the end of

the project. But often getting all these

requirements together takes a lot of

time. For example, spare parts. You have

to order the spare parts. They have lead

time. You need to organize vendor

training. All these different

requirements tend to take a lot of time

to get together. And people don't think

about them until the very end of the

project. And suddenly they're waiting

months to provide the final

documentation. And if you don't track

these from the very start of the

project, you'll never hand over on time.

So the fix is to define the

deliverables, the requirements your

completions system has to achieve.

Assign responsibilities early and then

simply follow these up regularly. Set it

up at the start, monitor it and control

it and you'll finish on time. The next

mistake is people goldplating the QA

system. People get excited when they

write ITPS. They want to make everything

perfect. They say, "Oh, we're going to

take a photo of the trench every 20

mters showing the depth at the bottom,

the width, blah blah blah blah blah."

All of a sudden, sounds great in

practice. Then all of a sudden, you're

in the field and you've got to take

2,000 photos of trenches. You've got to

file them to store them. And because

you've written it in the RTP, the client

signed off on it, you've said you're

going to do it, it's effectively now

requirement of the project, it just ends

up wasting no time, and you get nothing

for it. doesn't actually improve the

quality objectives of the project.

Doesn't do anything to improve the out.

So the the main takeaway is only track

what matters. Keep things as simple as

possible. Focus on the core objectives

of the quality management system

producing evidence you can apply

preventing mistakes. Keep it as simple

as possible. Don't get over excited and

it will be much easier for you to stay

on top of it. The next mistake I see

when it comes to quality, and it relates

to what I was saying about the snowball

effect and letting things get getting

out of hand, is people skipping the

process. Cutting corners feels efficient

in the moment, but it will always come

back to bite you later. You install

something before sign off. Tweak the

design but skip the RFI. You borrow a

certification from another job.

Something will come up. Something will

come back to bite you and it will be 10

to 100 more times work to fix than the

work you avoided by cutting the corners.

In my experience, shortcuts always lead

to future problems. The next big mistake

I see that happens during the tender

phase is not defining quality assurance

and completions requirements in contract

which basically will lead to scope

growth. So having to do testing or

completions things that we didn't allow

for in the budget or estimate or getting

into disputes about client of what we

have to do to hand over the project.

Quality assurance completions buying

spare parts doing additional testing all

costs money and takes time. So it needs

to be defined during the tender stage

like any other project task. Most

quality assurance issues aren't

technical. They're management mistakes.

Keep it simple. Start early. Stay on top

of it. And don't leave all the paperwork

till the end. Quality assurance is about

discipline, not being smart, creative,

or doing things over the top. It's about

staying on top of it, dotting your eyes,

and crossing your tees.

What gets measured gets managed, but in

construction, it's only half the story.

Projects generate mountains of data and

information. Invoices, schedules, site

diaries. But even with all this

information, teams still often miss

early warning signs. Project controls

isn't about analyzing data. It's about

analyzing the right data, the right way

to communicate a message and get a

result that improves the profitability

of the project. In this complete course

on construction project controls, we're

going to teach you how to track progress

against the budget and schedule. Use

simple tools like earn value management,

spot cost overruns before they snowball,

use project controls to influence

project teams and decision makers, and

apply these skills to real projects with

step-by-step examples.

So, I first want to start with the

allimp important question of why do

project controls matter? And guess what?

Here's the honest truth. You can deliver

a project profitably without ever

knowing your budget. You don't actually

need to track costs to finish a project

under budget. Controls don't build

projects. Controls don't pour concrete

or install underground services. They

don't fix quality problems. All they do

is measure and report. So why bother in

the first place? Well, there's a famous

quote that says, "What gets measured

gets managed." When people know costs

attract line by line, they think twice

about waste. When progress is being

measured objectively and you don't you

need to front up to management next week

to explain why your task is behind and

what you're going to do about it, you

treat things differently. Objective

tracking forces accountability. So the

real reason project controls matter is

because they change behavior. They shift

the mindset of the project from focusing

on getting it done to getting it done

under budget and ahead of schedule. The

thing is, bad news isn't always a

problem. Bad news delivered late is a

problem. Without controls, you only know

you've overspent when you can't do

anything about it. With controls, you

can spot a cost or schedule blowout when

you've only done 5 to 10% of the work.

Without it, you only know when you've

hit your budget. Project controls give

you the power to see problems before

they arise, change behavior, and do

something about it. They focus attention

on busy projects. Managers drown in

paperwork and data. Through project

controls, we distill these raw data into

useful insights that people can act on.

We know we're behind, we're burning cash

too fast, or we need to resequence the

works. We take the data and the project

controls process tells us what we need

to do. Good project controls directs

attention to the right problem at the

right time. On top of that, project

controls supports claims and disputes.

When variations happen, project controls

provide evidence of what's happened and

what the true impact is. They turn he

said, she said situations into here's

the data. So what if we don't use

controls? What happens? Well, we do

extra work without ever knowing. We

waste money we don't have. Plans become

meaningless. And surprises become claims

and disputes. And there's a ton of

evidence to back this up. Multiple

studies have proven beyond a doubt that

better project controls lead to better

project outcomes. So why do controls

matter? Well, fundamentally, project

controls change the way people behave.

They make you proactive not reactive and

they protect your profit, your time and

your reputation.

Let's move on to talking about what

actually is project controls. So project

controls to best understand the

definition we first need to talk about

the two stages of a project. Any project

can really be broken down into two main

stages. The planning phase and the

execution phase. Planning is where we

decide what we're going to do, how to do

it, how much it's going to cost, and

when it's going to be done. Execution is

actually doing the work. Planning is

characterized by assumptions, estimates,

and guesswork. No plan ever exactly

matches reality. When the execution

phase of the project is the reality,

it's what actually happens. The best and

most useful way to think about project

controls if particularly if you've done

any sort of systems engineering is the

feedback loop between the planning and

the execution. The goal of project

controls is to ensure we follow the plan

we agreed to. We measure what's actually

happening, not what we thought would

happen, what's actually happening. You

know when and why you're drifting off

the plan and you take action to correct

course before it's too late. It's the

feedback loop that links the planning

phase with the execution phase. Without

project controls, you have a plan and a

project but no clear feedback loop

between the two. So if we want to give

it more specific proper definition, the

project controls is the system for

planning, measuring, analyzing and

correcting project performance in terms

of cost, time and scope. Now some people

include quality, some people don't. But

for simplicity and because I've spoken

about quality in other courses, I'm just

defining project controls as correcting

and managing project performance in

terms of cost, time, and scope. It

answers, are we doing what we plan to

do? If not, how far off are we? And what

can we do about it to get back on track?

And fundamentally, I keep coming back to

this point that project controls is all

about changing behavior by enabling

smarter decisions. Okay, next up I'm

going to fly through some core concepts

around project controls. So, we said

project controls was about scope,

schedule, and cost. Well, scope control

is about what's in and out of scope.

Schedule control is about ensuring we

finish on time. We stick to the original

plan finish date. Cost control is about

tracking how we're spending money

against our budget. So, they're the

three elements of the project we're

controlling. Now, in the planning phase,

we determined what we were going to do,

how much we're going to spend, and how

long it was going to take. These plans

are captured in documents referred to as

baselines. These are the approved

reference points for what we're going to

deliver, how much we're going to spend,

and how long we're going to take. The

key baselines are the cost baselines,

which is the total approved budget

broken down by scope or or cost code.

the schedule baseline which is the

planned timeline showing when each

activity would happen and the scope

baseline which is the agreed

deliverables and the work breakdown

structure. Basically the baselines are

the benchmark. They're the ruler against

which we're going to measure

performance. Are we going over our

baseline or are we not? The core concept

around baselines or the core tool we use

to develop our baselines is the work

breakdown structure. So work breakdown

structure is a deliverable orientated

breakdown project scope into manageable

chunks. It connects scope to cost to

schedule in an ideal world. It ensures

you know what to track and where

problems are happening. Basically it's

just breaking down the project scope

into pieces and the gold standard of

project controls is having an integrated

work breakdown structure. So, we break

the project scope down into pieces and

against each piece, we know what work

we're doing, how long we have to do it,

and how much it's going to cost. If I

show you an example of a work breakdown

structure, let's imagine on a road

project, we break it down into

earthworks, structures and bridges,

utilities, and road works. That would be

level one. Then we could have WBS level

two where we take each of these core

domains, we break them down further. So

for earthworks, we break it down into

scrub and clear, bulk earthworks,

drainage, and subgrade. For our

structures, we've got piling, columns,

abutments, the deck slab. So basically,

we're breaking down the project scope

into smaller and smaller pieces. The

fully decomposed project scope is

referred to as the work breakdown

dictionary, which is where we have all

our individual work packages. Again, the

gold standard is that we use the same,

and this is surprisingly hard. It's much

harder than you think it would actually

be, but you have the same work breakdown

structure for your scope, your schedule,

and your cost. So, the same activity,

you can look at how long you you'll be

able to see it in the schedule, how

long's allowed for it, when's it planned

to start and finish, and what our budget

for it is. So, for example, we have a

switchboard foundation. We've got the

task which is the construction of the

foundation for switchboard 112 including

all earthworks and concrete. We have a

budget of $25,000 and we have a duration

of 3 weeks. Okay. So the next allimp

important concept is after establishing

our baselines are is measuring

performance. That's the next core

concept of project controls. The idea is

that we measure what we're actually

doing. How much work we said we were

going to do is our baseline. How much

work we're actually doing. we get

through performance measurement. So

there's different tools we can use to do

this. We could use earn value management

which combines scope, cost and schedule

into clear performance metrics like CPI,

cost performance index and schedule

performance index. Now we're going to

talk about these much more detail later

on. And then we can also have progress

measurement tools like rules of credit

systems, quantity tracking and site

reports. So, for example, our plan might

tell us for our trenching, we were meant

to do 500 m over 2 weeks. We're tracking

our progress. We might know that we've

only done 100 m in week one. Clearly, we

have a problem because we've done 20% of

the work in 50% of the time. Now, how

can we track progress? Well, we've got

productionbased tasks. So, these are

basically tasks that can be expressed in

terms of a single core quantity. For

examping example trenching or cable

installation where we can measure it ba

based on how many meters we trench or

how many meters of cable we can install.

Then we have progressbased tasks. These

are tasks that can't be expressed in

terms of a single quantity. For example,

procurement is classic example of this

where we're not going to measure

procurement based on how many words of a

scope of works we write out. No, we're

going to measure it based on some sort

of rules of credit system. Okay. So

performance measurement is all about

measuring what's actually happening.

Forecasting is where we use the data

from the present to predict what's

likely to happen in the future with more

accuracy than when we originally planned

the project and established our

baseline. So it's using today's

performance to predict our final cost

and completion dates. Forecasting

basically gives us earning warn early

warning signals of when we're going to

blow our budget or delay our schedule.

So for example, where we tracked we done

100 meters of trenching in one week, we

can clearly see that we're not going to

finish the trenching activity by week

two unless we fundamentally change the

way we're doing something. Reporting is

then the process where we turn these raw

d this raw data into actionable reports.

It's how we keep our stakeholders

informed. It's how we get agreement on

key issues. It's basically how we get

agreement of what we're going to do

about issues. example 100 meters in week

one. We can express this as we're 20%

complete when we should be 50% complete

which is giving us a forecast completion

date of five of week five rather than

week two. We put this in context. So we

say that this is a critical path

activity. It's if it's delayed it's

going to push out our overall completion

date and we need to do something about

it or maybe it's not a critical path

activity. So we're happy to take longer

than we originally planned and it's not

a big deal. A treatment is then when we

decide to do something to correct

performance. For example, with our issue

with our trenching, we've identified a

devian a deviation and we need to come

up with a solution to fix the problem.

How can we fix our issue? We can add an

additional crew which will ensure we

finish on time but increase our cost. We

could change the finish state if it's

not a critical path activity. Treatments

typically require a trade-off. we either

increase our cost to finish faster or

reduce the cost but take more time. So

treatments always have to be taken

within context. And again, I'm going to

explain all these more and what to do in

specific situations later on. Then

finally, we've got change control, which

is a system we use to manage scope

changes and variations. So why it

matters? It's basically going to help us

prevent uncontrolled increases to the

project scope referred to as scope creep

without cost and time blowouts. Okay. So

in summary, the core concepts of project

controls. Project controls keeps the

plan and the execution of the project

link. It's our feedback loop to ensure

that we stick to our original baseline

and change things as required. The

baseline defines the plan. The scope,

schedule, and cost baseline defines what

we said we were going to do in the start

of the project. The work breakdown

structure is the core way we do this by

breaking down the project into component

pieces. Performance measurement is how

we measure what we're actually doing.

Forecasting is how we predict the

future. Reporting is how we express and

explain this to management and key

stakeholders. Treatments are what we do.

We've got a deviation from the plan. And

change control is how we manage

uncontrolled changes to project scope.

Mastering these building blocks and

we'll develop a simple repeatable system

to deliver projects with fewer surprises

and more profit.

Next up, I want to talk about where

project controls fits in amongst all the

other domains of construction project

management like estimating, scheduling,

design management, and quality. It's

really essential that you understand

where project controls fits in because

it's not a standalone function. It ties

heavily into other domains like

estimating, scheduling, design

management, contract management, quality

management, and procurement. So, we're

going to go through each of these

different knowledge areas, the main

domains of project management. We're

going to talk about exactly how project

controls ties into these. Okay. So,

first up, we've got estimating. So

estimating is building the cost plan,

developing the budget. It is how we

forecast what we're going to spend to

deliver the project. So then the control

side of it would be then tracking our

actual expenditure against this budget,

forecasting the final cost and

identifying cost overrun. So the key

point here is estimating is the function

sets the budget. Project controls is how

we check whether we're staying within

it. Okay. Similarly with scheduling,

we've got the same relationship between

the two of them. The schedule builds the

plan of how we're going to deliver the

project, when everything's going to

happen, and then the project controls

function is checking that we're

following this plan and adjusting it as

needed. So, it's tracking our actual

progress versus our plan progress.

Again, scheduling sets the timeline.

Project controls checks that we're

sticking to it. Okay. The next one we've

got is design management, which we could

also think of as scope, definition, and

control. The design defines what we're

going to build. So, what we're going to

build, the scope of the project is going

to drive the cost and the schedule.

Fundamentally what we're doing through

project controls is we're monitoring

whether both the actual design

deliverables are on time and completed

in accordance with the schedule but then

we're also tracking changes to the

design. So changes to the scope and how

they impact the cost and the schedule.

The key thing we're trying to avoid here

is scope creep. So scope creep is doing

extra work without an adjustment to our

schedule or budget. And design

management is defining the scope in

detail. Project controls ensures that

we're managing changes to the design.

Okay, next up we've got contract

management. So contract management sets

the way you can think about contract

management is it sets the legal and

commercial boundaries of the framework.

The contract tells us who's doing what

and how much they're getting paid, how

long they have to do it, under what

terms. Project controls tracks whether

contractors are delivering as per their

contract verifying progress claims

monitoring the contract cost and

schedule impact. So again very related

when we're considering that the contract

is fun the source of truth with defining

what we have to do. Again contracts ties

very closely with design management and

scope control. Project controls is

monitoring the performance. So how we're

performing against the contract

requirements. Okay. Next up, we've got

quality management. So quality

management is the process of how we

verify and validate that we're building

in accordance with the design and

specification. So the work we're doing

meets the agreed upon standards, the

inspection and testing process. Now some

people include quality control within

the broader topic of project controls. I

believe there are distinct and different

topics where quality is about the

physical inspection and testing when the

impact on project controls. It's going

to track cost and time impacts, defects,

rework. It's going to report whether our

quality trends and how they're impacting

project performance. For example, how

much we're spending fixing defects. So

quality management is about validating

the deliverables. Project controls is

going to assess the impact of the

quality control activities on time and

cost. Okay, next up we've got risk

management. So risk management is the

process through which we plan for

uncertainty and develop mitigation

plans. It's really how we consider

uncertainty in the planning and delivery

of the project. Project controls is

going to track how actual risks that

eventuate or what we're spending to

mitigate risks impacts our budget and

schedule and it's going to adjust and

we're also going to need to adjust our

forecast

based on emerging risks. So as we

identify new risks, we have to hold

specific contingency for them that's

going to impact our forecast. So risk

management is about looking ahead,

trying to identify uncertainty, plan for

it and manage it. Project controls is

about dealing with what's actually

happening. And the next one we've got is

procurement management. So procurement

is the process through which we acquire

the external goods and services and

subcontractors we need to deliver the

project. And within the broader topic of

procurement, we typically also talk

about subcontract administration. So

managing these vendors. Now considering

around 70% of typical project costs.

Obviously it's going to vary hugely

depending on the scope and type of

project you're doing is going to be

sourced to external vendors. So a lot of

the money we're spending, a lot of the

actual duration to complete the project,

the work that's being done is going to

be done by external vendors. Subcontract

administration managing these vendors

ties very closely into the broader topic

of project controls. So project controls

is really going to be assessing and

forecasting how effectively we're

managing our external vendors, tracking

the expenditure, the duration versus the

budget and then it's going to ensure

timely completion of the work. So

procurement is about buying the work.

The project controls tracks if our

vendors are delivering on time and on

budget. Okay. So the key point I wanted

to make is in reality there is huge

overlap between all these topics.

Scheduling control and project controls

are effectively the same thing. Cost

control whether you say it fits under

estimating and cost management or you

say whether it fits into project

controls is really irrelevant. The idea

is you really need an integrated

approach to manage this. You need to

understand how estimating relates to

project controls. We're also going to

use estimating in our forecasting of our

cost to complete. how all these domains

tie together and whether you call it

cost control, schedule control or

project controls, fundamentally what

we're trying to do through project

controls is link our plan to reality.

Project controls is our feedback system

to ensure that we're managing the work

in accordance with the plan and if

things are changing, we're dealing with

them.

So now we understand broadly how project

controls fits in with the other domains

of construction project management.

Let's move on to giving you a

step-by-step framework to implement and

administer project controls on a

project. So, the first step of project

controls and the most overlooked one is

feasibility. What is feasibility? Well,

it's the tender team handing over the

project to the delivery team and the

delivery team saying they accept it.

What it means by accepting it, it means

they're saying they're willing to do it

for that budget and that duration. So

first step is the tender tender team

give the project to the delivery team.

The delivery team review the estimate,

the schedule and the scope and they say

they're happy to do it for that price.

If they can't, they need to come up with

a plan of how they're going to recover

the profit. At this stage, the

contract's signed. It's awarded. There's

no going back to the client and asking

for extra money. It's a fixed lump sum

contract. The delivery team need to

review the estimate and the schedule and

the scope. They need to understand

exactly how to deliver the project and

if they think there are shortfalls in

the budget and the schedule, they need

to come up with a plan of how to recover

the cost. Now, it's important point to

note here is that not all projects are

going to be able to do this. There are

mistakes people make in estimates.

People under quote jobs, but you

shouldn't accept that from the outset.

You should always have a profitability

plan. So, the t the delivery team take

ownership of the project. They they do

their own checks. They say we can do it

at this cost and this budget. We're

flagging a shortfall of 50 grand and

we're going to recover that extra money

through these planned variations or

these value engineering opportunities.

It's about basically them taking

accountability for the project. They

feasibility check the estimate and the

schedule. They develop a winning price.

They turn it into a workable delivery

plan and give you a fighting chance of

making money. Now in parallel with this

process the teams need to develop their

baselines. Now a baseline it's important

to point out that a baseline is

different to the tendered deliverables.

So a budget is not the same as an

estimate. An estimate is a forecast cost

to deliver the work. It's structured

around how much It's structured around

the calculation, filling out the client

pricing schedule, presenting it to the

client, working out how much your costs

are going to be, and it's fundamentally

used to win the job. It's presented as a

calculation. Budget is how you track and

allocate expenditure to manage your cost

during the project. It's the approved

baseline that you're going to use for

cost control. If you look at this

diagram on the left, the total payment

from the client is fixed. That's your

revenue. That's the price we've agreed

to the client. If we said we're going to

do it for $10 million, that's how much

they're going to pay us. Of this,

there's margin. So, profit margin and

corporate overheads. And then also cost

baseline, our cost to do the work. Of

these costs, we can break them out into

direct and indirect. So, what we're

actually going to spend as well as risk

and opportunity. We then break out our

direct and indirect into cost codes.

Now, hopefully the budget that goes into

a cost code is what we think we're going

to need to spend to do the work.

Hopefully, that's less less than our

actual direct and indirect cost from the

estimate. And then within that, we would

have procured scope. So, within procure,

so say for example, we have a budget for

procuring formwork. It's $20,000, but we

get a quote from a supplier for $17,000

to buy all the formwork. That's the

procured scope. So the estimate is the

calculation of the cost to do the work.

It's how we come up with our total

payment from the client. Our budget is

our controlled plan of how we're going

to spend money. And the cost codes is

the breakdown of the budget into all the

buckets of how we're going to spend

money. To give you an example, you might

have a concrete structure in the

estimate that's made up of plant, labor,

materials,

and subcontract costs. Within this,

there's going to be an allocation for

formwork. There's going to be an

allocation for steel fixing. there's

going to be an allocation for concrete

pump and concrete placement. Your budget

wouldn't have a cost code for materials

for every single structure because you

don't buy the materials per structure.

You buy the materials for the site as

needed. You might buy all the formwork

at once. So you should have a sitewide

material code, but you might have a

labor specific cost for that structure.

So the point here is fundamentally how

you spend and track money is different

to how you calculate the costs of

something. Now similar to this is the

tender schedule. So the schedule we

developed during the tender will be

different to the delivery schedule. So

tender schedules are generally high

level. They show that you can meet the

client deadlines. They're usually broad

and optimistic. The delivery schedule

will be developed post award during the

feasibility stage by the delivery team.

Needs to be more detailed showing your

real resource needs. And the fundamental

purpose of these two schedules are

different. Tender schedule is to verify

that we can meet the client dates and

present them with a plan that shows we

know what they're doing. Delivery

schedule is a detailed plan of how we're

going to do the work that's used for

planning the project. Typically, you

also remove contingencies. So, a net

schedule would be the schedule, your

plan of how you're actually doing the

work. The wet schedule is the one the

client sees that might have additional

contingencies shown in it. The delivery

schedule then becomes the schedule

baseline for tracking time. Now a

critical point here is your budgets and

your schedules should align. For

example, if your budget for the formwork

for structure has 600 man hours, your

schedule should show something like six

guys for 2 weeks which equates to around

600 man hours. So the two should align

and again this is why you need a a

consistent work breakdown structure. You

need the same cost codes as activities

in your schedule and it will make

tracking, managing, controlling the

project a thousand times easier. Okay.

So once your baselines are established,

you've done your feasibility, you've

worked out your cost to deliver the

project, you got your budget and your

delivery schedule, you can develop your

control system. So the control systems

are these feedback loops that link the

plan, the baselines to reality. So we

need to work out and finalize how to

track costs. We need everything broken

into cost codes, buckets of money. And

then against each of these cost codes,

we want baseline quantities and units of

measurement. For example, steel fixing,

we might track per ton of steel.

Earthworks, we might track per meter

cubed. Again, we want the same thing for

our schedule. Our baseline schedule, our

activities, and baseline quantities and

unit of measure. Again, ideally your

schedule and your budget should be

showing the same activities with the

same units of measurement. It's going to

make your life a lot easier. Then you

want a way to measure performance. The

key metrics, the reporting format that

you're going to use to summarize and

present this in. You want to have

identified particularly with the

schedule, the critical path, so the

series of activities that if delayed

will delay project completion and your

risk in opportunity and contingency. And

these are the things you're going to

report against. Then you need to set up

a system for recording data. So labor

you might track with time sheets. Then

you need a system for recording data. So

this might be with time sheets that

you're using to track labor hours

against cost codes. You might have a

daily site diary. You might do weekly

progress work walks to inspect it.

Basically you need some consistent and

repeatable way to collect data from the

field. And then all you're doing is

comparing the data you're collecting to

your baselines and addressing variances.

Basically, you want a clear breakdown of

the project scope that makes sense,

realistic, and there's agreed

measurement rules. Now, fundamentally,

how we put this into practice is going

to vary slightly depending on whether

it's subcontracted work or

self-performed work. So, subcontracted

work is where we engage an external

vendor or supplier to do the work on our

behalf. The key here is their taking on

the cost and productivity risk. So, we

engage someone on a lump sum to dig a

1,000 meter trench and they budgeted to

do 20 m a day, but they're only doing 5

m a day. That's not our problem. They've

signed a lump sum contract to do the

work. Where it is our problem though is

if in terms of the schedule performance,

they're not meeting their schedule and

we don't have any sort of recourse like

liquidated damages. So, what are the

subcontract management? It's really

going to be how well you set up the

subcontract and you align the objectives

of the subcontract with the objectives

of the project. Meaning that they've

agreed to a finish date that matches

your finish date or betters it and their

budget or the cost what you have to pay

them to do the work is less than your

budget. So, when you subcontract, you're

passing on the cost risk to the

subcontractor and they're car carrying

the full financial exposure for doing

the work. You still have to track their

performance. You want to particularly

track their schedule performance with

subcontractors, requiring regular

progress meetings, checking what they're

claiming on their payment claims versus

how much work they're actually doing.

You then need to administer the

contract. So, manage variations and

changes to scope. That's how you

primarily control your costs with a

subcontractor by basically not paying

them extra to do the same amount of

work. Control their payments. You make

sure you're only paying them for the

work they're doing that they've

completed correctly. And you're also

analyzing their performance.

Particularly with a schedule, you always

want to be paying attention to how much

work they're actually doing, the

quantities they're giving you. Are they

correct? Are they accurate? And the

core, the fundamental principle with

managing a subcontractor is to trust,

but verify. Yes, you want to trust them,

but you want to check everything they're

doing as well. Now, self-perform works

where we're engaging our own laborers,

plant, materials. We're taking on the

production risk, full cost risk for the

work. Obviously, we have to track it

much carefully. Primarily the way we do

this is we need to track every dollar

we're spending and compare it to how

much work we're getting done. So we're

tracking every labor hour we're

spending, all the hire and idle time for

the plant and equipment, what materials

we're buying, what wastage we're

getting. Basically, we're tracking every

single dollar we're spending in a cost

tracker and comparing it to how much

work we're getting done. So, if our

budget rolled up was $50 a meter per

trenching and we're spending $75 a meter

to do this to do our trenching, then

we're obviously going to blow our

budget. Again, we also want to be

tracking our schedule performance, how

much work we're getting done versus how

much we plan. This stuff is super simple

and straightforward, but it's about

having a system where you're capturing

all this information, then making the

very simple comparison.

So principle with self-perform is you

need to measure and manage everything

that's happening when subcontracts the

cost risk and hopefully the time risk is

also outsourced through a contract. So

you're really just tr you're trusting

them to do your work but you're checking

everything they're doing now. So if

you're tracking your cost, you're

tracking your performance. Fundamental

to this is measuring your quantities. So

quantities are just an objective way of

tracking how much work is getting done.

Did we do 100 meters of trenching? Did

we do 200 m? Did we do 100 m cubes of

concrete? Or did we do 500 m cubes of

concrete? It's just an objective way of

measuring how much work is actually

getting done versus what we plan. They

provide an objective record for our

cost, whether we got value for money

from what we've spent for our schedule.

Are we physically meeting the planned

output? For example, if we've spent 50%

of our concrete budget but only poured

10% of the plan structures, then

obviously we're going to blow our budget

without having an objective way of

tracking the quantity of work done. It

fundamentally is subjective and it

relies on guesswork. So it might not be

accurate. Practically, how do you want

to do this? At a regular period of time,

a regular interval, you just want to do

a physical count or check of how much

work's been done. How many meters cubed

of concrete we did? How many lineal

meters of trenching? How many tons of

steel did we install? Now, not all tasks

can be represented by a quantity.

Particularly, these are non-physical

tasks or tasks that involve a complex

series of steps. For example,

procurement. Procurement isn't a task we

can measure with some single metric. It

might be it might have defined stages.

For example, for buying a building

that's getting prefabricated, there

might be a 12week fabrication period, 2

weeks for FAT testing, 2 weeks for

delivery. That 12-week fabrication

period, we might break down into four

milestones. And against all the

milestones in the process, we put a

percentage complete. And then we're just

tracking are they meeting the

milestones. But again, it's the same

principle. We're just using a percentage

here rather than a physical quantity to

track it. So we've measured our

quantities. The next thing we need to do

is we need to maintain our schedule. Now

this is probably one of the biggest

issues I see on projects regularly that

a good schedule is developed during the

planning phase. Yes, it has some issues

but because it doesn't perfectly reflect

reality, people just ignore it. No one

continues to update it and it slowly

becomes worse and worse and worse until

what the schedule's showing doesn't

reflect what's actually happening in the

work. So the core principle here is at

regular intervals you want to be giving

feedback to the planner or updating it

yourself and keeping the schedule rather

than a static document that a live tool

that's used to plan and manage the work.

You want to be using actual start and

finish dates keeping percentage complete

accurate checking for impacts of the

critical path reevaluating the critical

path and using current data in the

schedule to free forecast the finish

dates and adjusting the sequence if

needed. The finish date, the actual

finish date of the project should be the

finish date in the schedule. And it's

important to note why this is so

important is that the schedule is a

critical input to cost control. A large

proportion of total project costs will

be driven by the duration of the

project. For example, staff salaries. If

you've got a project manager, they're

getting paid monthly. The project goes

from 6 months to 9 months, then you're

paying an extra 3 months of their

salary. These indirect costs are going

to form a significant portion of the

overall project cost. So the only way

you're going to accurately know how much

it costs to finish the project is if you

have an accurate schedule and you're

accurately forecasting the duration of

the works. Okay. Next up with all this

data we need to do something with it

which is fundamentally where we're going

to analyze and treat variances. All

we're doing is we're collecting all this

data. We've got our baselines. We

compare what's actually happening to our

baseline and then we analyze it and we

need to do something about it. So

fundamentally to analyze it the core

principle of how we do it whether we use

the entire system or just components of

it is using earned value management. So

earned value management is really a

fundamental project management concept

where you compare cost and time. There

three core principles to it. There's our

actual costs, which is how much we're

actually spending. There's our planned

value, which is how much we plan to

spend at that point in time. And then

there's our earned value. So earned

value is the budgeted cost of work

completed. Our plan value is how much we

plan to spend up to that certain point

of time. And our actual cost, as the

name suggests, is how much we're

actually spending. The comparisons that

we do is we look at schedule variance,

which is the difference between our

planned value and our earned value. If

we plan to have done more work than we

have up to this certain period of time,

then we're behind schedule. We also

compare our actual cost with our earned

value. What's the budgeted cost of the

work we've completed? How much have we

actually spent? If we spent more than

the budget for doing that same amount of

work, then we're over budget. basically

tells us where we have issues. Do we

have issues with schedule performance or

do we have issues with cost performance?

We can then analyze this further and

basically what we want to do is identify

the root causes. Is it productivity

issues? Are there a lot of quality

defects? Are we wasting a lot of

materials? Is our subcontractor

performing badly? Are they overclaiming

on variations? Now, you always want to

look to improve no matter what. Whether

even if you're under budget, you can

always do better even or even if you're

ahead of schedule. The principal way

that we look to improve performance is

by always asking ourselves the question,

how can we do it faster and cheaper?

There's 100 ways to build any same

project. We want to come up with the

best possible way to do it. We want to

do it safely obviously, but we also want

to come up with the fastest and cheapest

way of doing that. The principle we use

to do that is divergent thinking. So

divergent thinking is understanding that

there's 50 problems to a solution. We

need to brainstorm what all those

problems are, assess them, and then come

up with the optimal way to do it. If we

are over budget or behind schedule, we

need to apply treatment. So treatment is

basically addressing a variance. Now

whether it's subcontracted or

self-performed, the level of control we

have over the problem will be different.

But the principles behind it will remain

the same. Obviously, if we've signed a

contract with a subcontractor and their

practical completion date is behind the

date that we need to finish the work,

we're limited with what we can do. We've

outsourced that to someone else and

we've signed a bad contract. But again,

the principles I'm going to talk about

are the same. So, if a task is behind

schedule, the question is always, is it

on the critical path or near the

critical path? Is it part of the chain

of events that if delayed delay project

completion? If it is, we should spend

more money or take on more risk to

finish it faster. The way we do this is

with there's really two principles to

doing this, which is crashing or

fasttracking. So crashing is where we

add additional resources, spend more

money on it over time to get the work

done faster, and it results in an

increase in cost to complete the

activity. Fast tracking as you can see

in the diagram is where we overlap

tasks. So say we had the original plan

was we finish all the trenching before

we start the conduit installation. Fast

tracking is where we overlap the task.

Now doesn't necessarily increase cost

but it increases the risk of delays. Say

the condute installation crew catches up

to the trenching crew and then we have

standown due to that. So that's

increasing risk but it's not necessarily

increasing cost. If an activity has

float, meaning it's not on the critical

path, we don't have to spend more money

or take more risk to finish it faster.

That's why it's so essential you

understand the critical path of the

project because it influences how you

deal with variances to the schedule.

Now, if a task now in terms of cost, if

a task is self-performed, we have a lot

more control over it. We can look at its

specific root cause about it and we can

try to address it. But again,

potentially if it's an underestimated

task, there's not much we can do about

it. We might just have to cop it. When

we have a subcontracted task that's over

budget, it's because of variation. So

the subcontractor is claiming for

additional work. Might be because it was

procured badly and there are a whole lot

of variations. Then it comes down to

contract management and how can we

manage these variations in a way that we

spend the least possible money to get

the most work done. or it might be the

subcontractor is over over claiming and

being unreasonable and we just have to

administer the contract better. So over

overbudget subcontracted packages it's

going to come down to contract

administration and contract negotiation

to how we manage that. Now the final

part in this step-by-step system is

reporting and forecasting. Similar to

what I was saying at the start of this

course that anyone can dump a whole lot

of data and information and cost codes

and percentages into a table and show a

ton of information. The core thing you

need to get good at as a project

controller is how do you turn the raw

data into a story that clearly,

succinctly, and easily explains what's

happening right now, why it's happening,

what's going to happen next if nothing

changes, and what you plan to do about

it. You need to find a way to turn this

into a dashboard that clearly explains

the key metrics, the key messages.

Because at the end of the day, if you

present someone too much data, they

don't do anything about it. All the

previous steps, tracking quantities,

tracking cost, all that stuff is wasted

effort. Data without action is wasted

effort. So the core thing we want to get

out of all this data, all this

information is some change to behavior.

We want management to agree with our

plan to o to to add additional resources

to finish that task faster. So the

questions you should be asking yourself

is what insights actually matter? What

can we do something about? What do we

have control over? What's changed? What

corrective actions are we taking? And

what levels of details matter? You

should never present someone with a

problem. You should always present

someone with solutions. So the data the

analyst analysis you do identifies the

problems. Your job is to come up with

the solutions and present it in a way to

come up with the best possible solution

to the challenge. The end of the day

it's not about data. It's about decision

making and fundamentally what action are

you taking to improve project

performance.

So now we broadly understand the steps

in the process to monitor and control a

project again to implement this feedback

loop so our plan matches reality. Let's

now explore the specific tools and

techniques you can use to put this into

action. Previous step we spoke broadly

about the steps. We spoke about cost

tracking updating your schedule and so

on so forth. This section we're going to

get into the specific mechanisms of how

you do that. So the first tool we're

going to talk about is a cost tracking

sheet or a cost forecasting sheet. Now

this is how we know exactly where our

money is going and where you're heading

financially. Generally you want one

spreadsheet or one tool. There's

softwares that do this as well where you

track every dollar you're spending. You

capture those in your cost codes and

against each cost code you have a

forecast cost to complete the project.

Again, like we spoke about in the

previous step, we're going to break our

scope into cost codes or work packages.

We then track the budgeted cost. So, the

original cost, any adjustments to that

from variations, say we get in a

variation to extra work, we need to

adjust our budget accordingly. We then

track our committed costs, so any

purchase orders or subcontracts.

and in addition to that our actual cost

through invoices, payroll, material

purchases. Using this information we can

forecast our final cost which will also

rely on quantities of work complete and

production rates which gives us our

total cost to complete the work. In

addition to this, we can use this

information to prepare cash flow

forecast and basically predict at the

point in time when these costs are going

to hit. So I'm now going to show you an

example cost tracking sheet that you can

use. Okay. So this is an example cost

tracking sheet where you can see on the

left hand side there are a series of

cost codes where all the project scope

is broken down into buckets of money. So

we've got project management and

supervision, site setup and amenities,

inductions, safety briefings, temporary

works, fencing. We've got the concrete

works, the formwork for the footings

which has a budget of 600 hours and a

rate of $100. And adding these all

together, we've got the total cost to

deliver the project. Importantly, this

is cost. So profit and corporate

overheads have been pulled out of this.

So what we build a client would be more

than that because we'd also have our

profit and our margin or whatever our

lump sum fixed fee is. So, we've got our

cost codes with our budgets, which are

broken down by quantity and a unit of

measure and a rate. So, for example,

steel fabrication, we've got 75 tons at

$2,800 a ton, which gives us a budget of

$210,000. This is what is in a bucket of

money. On top of that, these buckets of

money will be adjusted through

variation. So, say for example, the

client has delayed us and we got a

variation or an extension of time for

four additional weeks at a rate of

$10,000. We've got a variation amount of

$40,000 of costs allocated to that. So,

our new budget for project management

supervision is $160,000. Our original

budget plus the variation amount. Now,

against each of these costs, we want to

track. So, the cost code, we want to

track our cost to date. So everything

we've spent so far. The way we do this

is with a cost tracker. Cost track is

super simple. Basically every

expenditure we have gets tracked in

this. Say we have a subcontractor

construct IQ that has done a week of

work and we've paid them $6,200 and

they're providing project management and

supervision support. At $6,200 gets

allocated to cost code 101. You can see

the cost to date on cost code 101, which

is our project management supervisions,

is $6,200.

Now, you could put anything in here. You

can put, say, for example, we buy

formwork materials and we've got our

budget for formwork materials. Then we'd

put in the invoice for formwork and then

it would get allocated to the cost code.

Now we can then also in the same sheet

against each of our cost codes we want

to forecast our cost to complete.

Typically we would do this based on two

things. A quantity to complete and a

rate to complete. Say for example our

project management supervision code.

We've got a quantity to complete of 22

and a rate to complete of 13,225.

So, say we're actually spending $13,225

a week on our overheads and we've got 22

weeks left to do. That gives us a

forecast cost to complete of the

quantity to complete multiplied by the

rate to complete. So, that is how much

money we need left to do the work. And

then our cost at completion is the sum

of our actual cost, what we've spent to

date, plus the cost to complete, which

gives us then our cost at completion and

then our gain and loss. So why is this

in the red? Well, because we're saying

we need to spend $297,000 across the

project to do this work, but our budget,

including the variation, is only

$200,000. So we're going to spend

$97,000 and $97,150

more than our budget and we've got an

explanation there. So we need an

additional project engineer and the

supervisor rate we had in the estimate

was too low too too low and there's

project durations also increased. So

basically to forecast we want to do that

for every single one of our cost codes.

We needed to know the quantity to

complete and the rate at completion. So

you can see some of these other cost

codes are showing again. For example,

I'll use this one as an example. That is

the formwork for the slabs. Our budget

was8 850 hours at $100 an hour. Our

quantity to complete, say we

subcontracted it out to a subcontractor.

The quantity to complete is one lump sum

subcontract fee at $64,974.

Now, it's just an example, might be

something different. Then that would

show a gain on that cost code. You sum

all your gains and losses together and

you get an overall financial position.

So for this project, as an example,

we're $240,000

over our cost. That doesn't necessarily

mean we're going to lose money on the

project, but our profit margin might be

50% in which case that gain or loss,

which is about 12%, we could we would

still make money on the project. They're

just showing us where we are against our

baseline cost. That's cost tracking and

forecasting. Cost tracking forecasting.

It's generally at a static point of

time. We might use the schedule to

forecast cost. For example, that project

management supervision cost code. We

said there were 22 weeks left on the

project. That would come from schedule.

But we can enhance our cost management

using time phase costing and cash flow

forecasting. Basically, this is taking

our cost forecast and adding the

dimension of time to it. So, not only do

we know how much we're spending, we know

when we're planning to spend it. And

basically, this helps us manage our cash

flow. Now, most construction companies

go broke because of cash flow issues,

not necessarily profitability issues.

You might be starting a project, you

might have to put down security, then

you might have to pay a month a month's

work for the first month's work. Then,

you put in a bill to your client for

that. Then, you get paid 30 days after

that. You've actually put up two months

of work before you've got any money in

your bank account. So, managing cash

flow on construction projects is

essential. How can we track costs and

schedule work together? Well, your

schedule defines when the work will

happen. Your budget defines how much

work

how much this work will cost. When you

combine these, you get a timephase cost

plan showing how money will be spent

over time. On a construction project,

this is referred to as an S-curve. An S

curve is a visual representation of when

we're spending, our cumulative total

spend across time. So you can see they t

generally take the shape of an S because

when the project starts, you're ramping

up. You're not doing a lot of work. You

might not have many people on site.

You're just getting the site sheds

delivered. These sorts of things. You're

not spending much money. Then you hit

your bulk construction period where you

have lots of people on site. You're

spending a lot of money. And then you

phase out as people demobilize. You tidy

up, finish defects, and dem. So that's

why you generally get the S the S shape.

What this represents and we could talk

about this a bit more when we talk about

earn value management in more detail but

you're basically showing your actual

costs your planned progress and then

your actual progress which is your

earned value. So how much work you've

actually gotten done. Ideally you want

the budgeted cost of your work you've

completed to be higher than your actual

cost and that to also be higher than

your plan progress because that means

you're ahead of schedule and ahead of

budget. So how do you develop an S

curve? Well, now we're going to look at

a cash flow forecasting spreadsheet that

will show you how to do it. Okay, so how

do we do a cash flow forecast? Super

simple. It's basically we need to track

when we're getting paid and when we're

spending money. That's all it is. The

point here is that you might have

multiple clients, you might have

multiple projects, you might have

multiple different payment terms. So the

challenge here is getting the structure

right and the right information. So, for

example, if you have client one that

you're doing

$72,000 of work in April and you have

30-day payment terms. So, day zero, you

do months worth of work in that first

month. Let's imagine you've spent

$72,000 on labor at $72,000 out of your

bank account in April. But you can only

build a client for that at the end of

April and they only pay you at the end

of May. So that $72,000 of work you did

in April, you're getting paid for it in

May. Now, you might have a profit

margin, so it might be less. You might

have might only do $65,000 worth of work

and then get paid $72,000 the next

month. But the key there is that you

fronted up that $65,000 in April and

it's only gone back into your bank

account in May. So basically, all you

have to do is to set up a table like

this. You have to put in when you're

likely to receive payment based on the

work you're completing and the payment

terms with the client. Then you

basically put in when and how much money

you're spending and then it'll give you

your net cash position. Okay, so that's

cash flow forecasting and cost tracking

all about money. Let's talk about how

you practically monitor and control

schedules. Well, in reality, you don't

need to be able to do it by hand in

2025. If you're going to be using some

sort of scheduling software, whether

it's Microsoft Project or Primma Vera

P6, when you develop your schedule, this

is where you build develop the plan. And

then as you deliver the project, this is

where you track percentage complete

against each activity and put in the

actual start and finish dates. Again,

it's the core thing you want to do when

you're using a schedule is you want to

make sure the schedule stays an accurate

plan that reflects reality. So now I'm

going to show you Smart Sheet, the tool

I use, which is way easier to use in

Microsoft Project. I'll just show you

the types of facilities and functions

you'd be using. Okay, so here's Smart

Sheet. It's all the scheduling softwares

are the same. Doesn't matter which one

you use. Basically, you're going to have

a Gant chart where you're going to have

your tasks, your durations, your start

and finish dates, and then it's going to

express itself in a bunch of lines

showing when these activities occur. So

to monitor and control the schedule,

super easy. All you have to do is add in

new tasks as they come up, adjust the

linkages as they come up, and then enter

your percentage complete. If I say that

task is 100% complete, then it gets

marked off as 100% complete. And then

it's giving me some sort of overall

project performance metric, which I'm

sure you can adjust by putting in

appropriate budget or manhour

allocations to get a proper percentage

complete. So that is pretty much as

challenging as it gets. You're just

updating that and then as required you

need to update the actual start and

finish date. So if this activity isn't

actually starting till the 12th of June,

you can see it throws out the entire

schedule. Now the other thing you want

to pay attention to which is a very

powerful tool these scheduling softwares

have is they help you understand the

critical path. Critical path is the

series of activities that if delayed

delay project completions. It's

basically the tasks with zero float. Now

all you have to do to do this is well

because this is a manually set date

that's why that's showing that. So I

actually put that back. Basically it's

now highlighted. This sequence of tasks

are pushing out the finish date of the

project. Mobilization bulk earthworks

detailed excavation concrete pour. These

are the activities that we have to pay

attention to. These are the activities

that if for whatever reason they're

going to take longer than planned, it's

worth us spending more money taking on

more risk. because they're what's

actually driving the overall completion

of the project. So, primarily using

scheduling software for project

controls, all you're really doing is

maintaining, keeping the schedule up to

date, updating with the percentage

completes, which should come from your

quantity tracking and monitoring the

critical path. A little bit more detail

on the critical path. It's basically

identifying which activities control the

finished state of the project. And

critical path analysis is a fundamental

project controls tool you need to

understand because it tells you what

activities matter in your schedule. You

can use scheduling software to do it. An

important point to note is critical path

changes during the project. And if

something is near the critical path, it

has a float depending on the length of

your project. If it has a float 5 to 10

days or less, for all intents and

purposes, it's on the critical path. No

schedule is 100% accurate. So if

something has next to no float, it's on

the critical path. The other thing you

need to always pay attention to is when

you're talking about the critical path

is you need to understand whether an

activity on the critical path is on the

critical path because of resourcing or

because it's got a fixed duration. For

example, procurement of a building that

has a 20we lead time that's on the

critical path. That's different to a

trenching activity that's taken 20 weeks

because we've only got one crew on it.

That same trenching activity, we could

put four crews on it and finish it in

five weeks. That same building, we can't

go to four building manufacturers and

get it done in 5 weeks. It takes 20

weeks to build. So, it's also important

when you're talking about the critical

path, you need to be crystal clear on

what's a resource-driven activity, which

means you can always easily add more

resources. What's the proper fixed

duration? Because if something has a

fixed duration, it's got much more risk

associated with it. Okay. So the next

tool and technique is quantity tracking

which I've already spoken about at

length but basically it's just measuring

quantities. You can use survey data. You

can go to physical counts yourself. You

can get input from supervisors or

workers. Really depends on the nature of

the project. It's not rocket science.

It's super simple. But it's basically

having a point in time setting up a

system and every week, every month or

whatever it is, you simply record the

quantity of work complete and you

cross-check that with your subcontractor

claims and any other information you

have. But basically, you have to track

your quantities for this any of this

system to work at all. The next, and

I've spoken about this a couple of times

already, that subcontractor management,

considering 70% of project costs

typically outsourced, is essential to

effective project controls. Project

controls without subcontractor

management is pointless. You need to be

able to control the costs of your

subcontracted work through variations,

risk, and the duration of their works.

In practice, that's done through the

process of contract administration. How

do you do it? Well, it starts in the

procurement phase where you set up a

clear subcontractor scope. It's crystal

clear what their pricing, what their

deliverables are, when they need to

finish, and that aligns with our finish

dates. You need regular progress

reports, regular progress meetings. You

need to give them access to the site,

manage it, coordinate it with them

effectively, verify the percentage

completes they're giving you with

regular site checks, validate any

payment claims, and track variations,

and manage the scope tightly. Again,

core principle is don't let and forget.

trust but verify. So all of these

different tools and techniques, cost

tracking, updating your schedule, they

really tie in to a broader project

management concept called earn value

management, which a lot of people over

complicate but is super simple. Earn

value management is a project controls

method that combines schedule, cost, and

progress into a single system

measurement. You use all of it, you can

use parts of it. Basically, if you

understand the fundamentals, you

understand 95% of project controls. So,

earn value management at its core

compares what you plan to spend verse

what you should have spent for the work

done and what you've actually spent.

Helps answer the questions of are we on

budget? Are we on schedule? If not, by

how much? And what does that mean for

our final cost and completion dates?

There's tons of formulas derived from

these core inputs, but again, most of

them are common sense and you can Google

them in 10 seconds. But if you

understand broadly what these three

things are, the planned value, the

actual cost, and the earned value, you

understand 95% of project controls. So

important principles about earn value

management is earn value management only

works if you have a clear cost baseline

linked to each schedule activity or work

package because you're using a baseline

of cost to compare between different

activities. If you have different units

of measurement, different activities,

different ways of measuring things. You

need some sort of baseline to do this

which is where we use the baseline of

cost which is the set project budget for

the task. Each activity has a planned

quantity and a unit cost resulting in a

planned cost. These planned costs are

spread over the project timeline. The

time phase them similar to an S-curve.

You see they got the same shape and they

create a planned value for each point in

time. So if we look at this

diagrammatically, you can see our earned

value is the budgeted

value of the work we're completing. So

what is the say we've spent 50% of our

say we say we've done 50% of the work

the earned value would be 50% of the

budget our planned value which is our

schedule baseline and our cost baseline

plotted over the full duration of the

project and at any point in time so

today in the graph that tells us how

much work we should have done the

difference between our planned value how

much work we should have done how much

work we've actually done is our schedule

variance a cost variance is the

difference between our actual cost

remember in our cost tracker that would

be the sum of all our dockets, invoices

and so on verse what our earned value

is. So the difference between the green

line and the yellow line. If we use this

information to forecast our completion,

our schedule slip is going to be the

difference between our forecast

completion date and our plan completion

date. our cost slip or our variance in

cost is going to be the difference

between our forecast cost to complete

and our baseline cost. So if I give you

some more better definitions than me

just ranting about earn value management

then planned value also called the

budgeted cost of work scheduled. This is

the approved budget for the work

scheduled to be done by today. Remember

earn value management it's always about

taking a point in time and comparing

these three metrics. For example, you

plan to for pour 500 m cubed of concrete

by this week at $400 per meter cubed.

Our planned value at this point in time

is $200,000. So we should have spent

$200,000 and we should have done 500 me

cubed of concrete. Remember, we're

taking the metric of concrete measures

cubes and we're converting it to a

dollar value, our plan value, which

helps us to compare it to other

activities and to get an overall project

picture. Our earned value is the

budgeted cost of work performed. How

much of what based on how much work

we've done, how much of our budget

should we have spent? So, we actually

poured 400 m cubed of concrete using

that same unit as the previous example,

$400 a me cubed. Our earned value is

$160,000. So what does this mean? We've

earned less than our budget than we

should. So this is representative of

this. We're here. We've only done

$160,000 worth of work. We should have

done $200,000. So we're behind schedule.

Actual cost. The actual cost is just

tracking everything we spent so far to

do that work. So this is what you

actually spent so far on the work. So,

for example, if the total cost to pour

400 m cubed so far is $180,000,

our actual cost is $180,000. So, we've

spent $180,000. We should have spent

$160,000,000.

Again, this is similar to this

representation. Our actual costs are

higher than our earned value.

Particularly from this, we can calculate

two key metrics. Schedule performance

index and cost performance index. So

schedule performance index is the ratio

of our earned value how much work we

should have done and how much work sorry

our earned value the budgeted cost of

the work we've completed over our plan

value done less work than we should have

it's less than one we've done more work

than we should have it's greater than

one so we're using that example above

our earned value was $160,000 our plan

value is $200,000 so our schedule

performance index is8 we're behind

schedule our cost performance index our

the budget budgeted cost of the work

we've completed is higher than our

actual cost then our cost performance

index is going to be greater than one.

So using the numbers we calculated if

our cost performance index is $160,000

divided by $180,000 we get a CPR of89

which means we're spending more money

than we originally planned to. So these

two metrics just give you an overall

position in terms of schedule and cost.

Last tool which is essential for any

smooth running construction project is a

site diary. So a site diary is a daily

daily record of what's happening on

site. Good site diary should track all

the hours for the crews they're working

the materials the plant what every

resource on the project is doing and it

should allocate them to a Costco. So our

excavator is being used for trenching in

zone A. Those 10 hours of excavator

usage get allocated to the cost code for

trenching in zone A. You also want to

track any materials delivered, any

invoices, the key activities done, any

issues with subcontractors as well, and

any issues such as weather or access,

which can be vital for substantiating

pay which can be vital for

substantiating variation claims to